| GBMS 2.0 | COUNTRY |
| --- | --- |
|  | ALL |
| Document TYPE | LANGUAGE |
| PROCESS DESCRIPTION based on G-TMP A01007 rev.05 | EN |

Design, Develop and Qualify Solution

G-PRD L03000 rev.00

REVISION HISTORY

| Rev. | Date | Author | Approver | Authorizer | Revision Description |
| --- | --- | --- | --- | --- | --- |
| 00 | Sep 2026 | O. Scheck | R. Castagna | M. Guerricchio | First Issue (*) |

(*) This document replaces the following GBMS documents:

- G-PRD R0200 RS Requirements Management

- G-PRD R0400 RS Design & Development

- G-PRD S0100 S&T Requirements & Interface Management

- G-PRD S0300 S&T Product Development

- G-PRD S0400 S&T System Design

- G-PRD S0500 S&T Cybersecurity

- G-PRD S0700 S&T Verification & Validation

DOCUMENTS TREE

- G-TRN L03000 Design, Develop and Qualify Solution Transition Rules

  - G-PRD L03000 Design, Develop and Qualify Solution

    - G-KPI L03001 Design, Develop and Qualify Solution KPIs

TABLE OF CONTENTS

1	SCOPE	5

1.1	Process Cluster	5

1.2	Purpose	5

1.3	Applicability	5

1.4	Effective Date	5

2	TERMS	6

2.1	Acronyms and Abbreviations	6

2.2	Definitions	8

2.3	GBMS Reference Documents	12

3	PROCESS OVERVIEW	13

3.1	Entry and Exit Criteria	14

3.2	Inputs and Outputs	14

3.3	Work Environment Standard	14

3.4	Verification Steps	15

4	ACTIVITIES	16

4.1	Manage Contributions for Bidding (DDQ-01)	16

4.2	Plan and Coordinate Solution Development (DDQ-02)	17

4.3	Capture and Manage Requirements (DDQ-03)	18

4.4	Capture and Manage Interfaces (DDQ-04)	19

4.5	Design Solution (DDQ-05)	19

4.6	Make-or-Buy Solution Items (DDQ-06)	20

4.7	Integrate, Verify & Validate Solution (DDQ-07)	21

4.8	CyberSecure Solution (DDQ-08)	22

4.9	Manage Obsolescence within Solution Development (DDQ-09)	22

4.10	Design for Sustainability (DDQ-10)	23

4.11	Design for Environmental Compliance (DDQ-11)	24

4.12	Leverage Artificial Intelligence (DDQ-12)	25

4.13	Manage Engineering Discipline (DDQ-13)	25

5	TAILORING GUIDELINES	26

6	MEASURES	27

7	R.A.C.I.	28

8	INPUT AND OUTPUT DETAILS	31

8.1	Input Details	31

8.2	Output Details	36

# SCOPE

## Process Cluster

☐ Steering ☐ Support  ☒ Execution ☐ Customer Facing

## Purpose

This process aims to transform customer and internal stakeholder requirements into a solution through coordinated design, development and qualification activities ensuring fitness for intended use.

## Applicability

Refer to the table below for the applicability of this document.

| Legal Entities | All RSBU Legal Entities |
| --- | --- |
| Line of Business (LoB) | All Lines of Business |
| Project/Bid Type/Criteria | - Delivery projects (external customer projects), - Portfolio projects (internal development projects, e.g. product / platform development) |
| Additional Criteria and Notes | This process does not apply to Research and Innovation (R&I) Projects and Initiatives governed by G-MNL A15001. |

## Effective Date

This document is applicable as soon as it is published.

# TERMS

## Acronyms and Abbreviations

| AI | Artificial Intelligence |
| --- | --- |
| ALM | Application Lifecycle Management |
| BEP | BIM Execution Plan |
| BIM | Building Information Modelling |
| BM | Bid Manager |
| CAD | Computer Aided Design |
| CBS | Cost Breakdown Structure |
| CCB | Configuration Control Board |
| CRA | Cyber Resilience Act |
| CE | Conformité Européenne (European Conformity) |
| CM | Configuration Manager |
| CMP | Configuration Management Plan |
| DPP | Digital Product Passport |
| EBOM | Engineering Bill of Material |
| EMC | Electromagnetic Compatibility |
| EMP | Engineering Management Plan |
| EMS | Engineering Master Schedule |
| EPPPS | Externally Provided Product Process or Service |
| ESPR | Ecodesign for Sustainable Products Regulation |
| FMECA | Failure Modes, Effects, and Criticality Analysis |
| FBS | Functional Breakdown Structure |
| GBMS | Global Business Management System |
| HSE | Health, Safety, and Environment |
| ICDD | Interface Control and Definition Document |
| IM | Interface Manager |
| IPR | Intellectual Property Rights |
| JV | Joint Venture |
| KPI | Key Performance Indicator |
| LBS | Location Breakdown Structure |
| LCA | Life Cycle Assessment |
| LCC | Life Cycle Costs |
| LoB | Line of Business |
| MWPM | Main Work Package Manager |
| NC | Nonconformity |
| OBS | Organisation Breakdown Structure |
| OS&M | Operation, Service and Maintenance |
| PAM | Project Approval Meeting |
| PBS | Product Breakdown Structure |
| PE | Project Engineer |
| PHA | Project Handover Assessment |
| PJC | Project Controller |
| PJP | Project Planner |
| PLM | Product Lifecycle Management |
| PM | Project Manager |
| POM | Project Operations Manager [VHC] |
| PQM | Project Quality Manager |
| PRM | Project RAMS Manager |
| PTS | Purchase Technical Specification |
| QMP | Quality Management Plan |
| R&D | Research and Development |
| R&I | Research and Innovation |
| RAM | Reliability, Availability, and Maintainability |
| RAMS | Reliability, Availability, Maintainability, and Safety |
| REACH | Registration, Evaluation, Authorisation and Restriction of Chemicals |
| RoHS | Restriction of Hazardous Substances |
| RM | Requirements Manager |
| RS | Rolling Stock |
| RSBU | Railway System Business Unit |
| RTM | Requirements Traceability Matrix |
| SCIP | Substances of Concern in Product |
| SCPM | Supply Chain and Procurement Manager [SRS] |
| SIL | Safety Integrity Level |
| SLA | Service Level Agreement |
| SMI | Site Modification Instruction |
| SoW | Scope of Work |
| SQAP | Software Quality Assurance Plan |
| SRS | Signalling and Rail Solutions (LoB) |
| TRL | Technology Readiness Level |
| UNIFE | Union des Industries Ferroviaires Européennes |
| URD | User Requirements Document |
| V&V | Verification and Validation |
| VDD | Version Description Document |
| VHC | Vehicles (LoB) |
| WEEE | Waste Electrical and Electronic Equipment |
| WBS | Work Breakdown Structure |
| WP | Work Package |
| WPL | Work Package Leader |
| WPM | Work Package Manager |
| WPR | Work Product |

## Definitions

| Circular Economy | Economic system that uses a systemic approach to maintain a circular flow of resources, by recovering, retaining or adding to their value, while contributing to sustainable development (ISO 59004:2024). |
| --- | --- |
| Circularity Aspect | Element of an organization’s activities or solutions that interacts with the circular economy (e.g. durability, recyclability, reusability, repairability, recoverability). Circularity aspects should be considered in relation to the principles, as well as the organization’s objectives, goals and actions, for the implementation of a circular economy (ISO 59004:2024). |
| Circularity Assessment | Evaluation and interpretation of results and impacts from a circularity measurement. Assessment includes consideration of the sustainability aspects and can apply complementary methods such as life cycle assessment (ISO 59004:2024). |
| Circularity Measurement | Process to help determine the circularity performance through collection, calculation or compilation of data or information (ISO 59004:2024). |
| Commissioning | Phase before handover to a Customer, in which a product is final tested under operational conditions to verify it functions according to its specifications (ISO 22163:2023). |
| Component | A constituent part of Product (Software or Hardware) which has well-defined interfaces and behaviour with respect to the Software or Hardware architecture and design. |
| Customer | Person or organization that could or does receive a product or a service that is intended for or required by this person or organization (ISO 9000:2015). |
| Engineering Discipline | A defined area of engineering competence (e.g. requirements management, architectural design, software engineering) that provides specialised expertise, resources, methods, processes, and tools to support the Solution Development lifecycle, while continuously improving quality, efficiency, competitiveness, and organisational maturity. |
| Interface Manager | The person responsible to promote, plan, and manage the interface resolution process and to document the interface agreements. |
| Maintenance | Combination of all technical and management actions intended to retain an item in or restore it to a state in which it can perform as required (ISO 22163:2023). |
| Nonconformity | Non-fulfilment of a requirement (ISO 9000:2015). |
| Organisation | Person or group of people that has its own functions with responsibilities, authorities and relationships to achieve its objectives (ISO 9000:2015, ISO 14001:2015, ISO 45001:2018). |
| Product | A Product is intended to be sold, directly or indirectly to customers for satisfying their expectations and meeting their operational requirements. A Product can be a generic solution, a system, an equipment (hardware or software) or a service. |
| Project | Unique process, consisting of a set of coordinated and controlled activities with start and finish dates, undertaken to achieve an objective conforming to specific requirements, including the constraints of time, cost and resources (ISO 9000:2015). Types of Solution Development projects: - Portfolio project (internal development project, e.g. product / platform development) - Delivery project (external customer project) |
| Project Engineer | The Project Engineer leads and is accountable for the overall technical solution. For detailed definition and responsibilities see document G-TRN A08001. |
| Project Management | Planning, organizing, monitoring, controlling and reporting of all aspects of a project, and the motivation of all those involved in it to achieve the project objectives (ISO 9000:2015). |
| Reference Solution | Is based on concrete, selected products and their features (URD level), and defines the standard solution for new markets. In contrast to the Solution Target Architecture it defines concrete products, including current and upcoming requirements and their roadmap. The Reference Architecture shall be the basis during bid phase. |
| Solution | A consistent set of systems, sub-systems, products, equipment and services provided to the customer to meet their requirements. The Solution also includes Enabling Systems to deploy, maintain or operate the system. The Solution intends to maximize the use of Products to reach the required level of competitiveness and attractiveness. |
| Solution Development | All development lifecycle activities which are required to create a Solution from bidding or product portfolio definition through execution and final acceptance including planning, requirements and interfaces management, design and implementation, integration, verification and validation, delivery, and applicable specialised domains. |
| Solution Item | Constituent element of a Solution, including products, components, systems, subsystems, or services, that is specified, developed, procured, or integrated to fulfil defined requirements and contribute to the overall functionality and performance of the Solution. |
| Solution Development Team | Inter-functional and cross-organisational team responsible for the end-to-end definition, development, integration, verification, validation, and internal delivery of a Solution across its full development lifecycle, from bidding and concept definition through execution and final acceptance. The Solution Development Team brings together the competences required to manage the Solution in a coordinated and integrated manner, ensuring continuity and accountability across all development lifecycle activities, including planning, requirements and interfaces management, design and development, integration, delivery, and applicable specialised domains. The team operates through Work Packages (WP) as the execution structure, with team members functionally reporting within the team for delivery activities, while relying on competences, staffing, and professional development provided by the hierarchical organisation. For Customer Projects, the Solution Development Team is embedded within and reports to the Project Team Organisation, ensuring that Solution delivery is performed and coordinated within that organisational framework. The Solution Development Team is led by the Project Engineer for Delivery Projects and Portfolio Projects. The structure of the Solution Development Team follows the rules and guidelines as outlined in document G-TRN A08001. |
| Solution Target Architecture | A strategic solution target architecture describing, in an abstract way, the mid- and long-term evolution of a Solution. It contains standard interfaces, user level requirements and features, dependencies between subsystems and strategic positions and justifications. |
| Subsystem | A significant part of the system allowing a consistent part of the function of the system. |
| Supply Chain | System of organisations, people, activities, information and resources involved in transforming materials and knowledge in a product or a service for the customer (ISO 22163:2023). |
| System | A whole or a part of an integrated technical system based on the scope of work of a specific contract. |
| Technical Authority | The Technical Authority is a senior technical individual who analyses, challenges, validates and approves the technical solution and the technical delivery process proposed for Bids or Projects, ensuring technical risks have been minimized with proper mitigation plans through the critical phases from bid to completion of project execution. |
| Technical Event | Any event potentially affecting the configuration. Event such as defect on produced part, result of incidents analysis, Deviation, Waiver, Customer Change Request, Supplier Change Request, Internal Change Request, Supply chain shortages. |
| Waiver | A formal post-production decision documenting and authorizing a non-conformance of the Physical Item with respect to the approved product configuration baseline. |
| Work Breakdown Structure | A hierarchical decomposition of a project into smaller, manageable components called work packages. |
| Work Package | A deliverable or project work component at the lowest level of each branch of the Work Breakdown Structure. |

## GBMS Reference Documents

References apply to the latest approved revision.

| G-KPI L03001 | Design, Develop and Qualify Solution KPIs |
| --- | --- |
| G-TRN A08001 | RSBU Project Team Organisation Transition Rules |

# PROCESS OVERVIEW

See §8 for input and output interface details.

## Entry and Exit Criteria

| ENTRY CRITERIA | EXIT CRITERIA |
| --- | --- |
| - Bidding support request, portfolio project development order, award of a contract or formal authorization to proceed - Changes impacting the solution baseline (e.g. change requests, updated standards, regulatory changes, defect resolution needs) | - Solution delivered to and approved by the Customer - Completion of contractual lifecycle obligations (e.g. end of warranty period). |

## Inputs and Outputs

| INPUTS | OUTPUTS |
| --- | --- |
| - Bidding Documents - PM Execution Baseline and Contractual Interfaces - Product Portfolio Deliverables - Supporting Plans - R&I Deliverables - Configuration Deliverables and Change Triggers - BUY Items Deliverables - Test, Field and Compliance Deliverables - Additional Requirements - RAMS Requirements and Deliverables - Industrialisation, Production and HSE Deliverables - Quality Audit, Advice and Reports | - Engineering Pre-Qualification Deliverables, Engineering Bidding Deliverables - PM Governance and Planning Output - Plans - Technical Documentation - Configuration Change Needs - BUY Needs and Deliverables - Reports - Industrialisation Needs - Solution Items, Product Lifecycle Data and IP Protection Needs |

See §8 for input and output details.

## Work Environment Standard

- Artificial Intelligence (AI) Tools and Services

- Application Lifecycle Management (ALM) Tools

- Cybersecurity Management and Risk Assessment Tools

- Design and Engineering Tools (CAD, system design, simulation, calculation, engineering analysis)

- Development and Testing Tools

- Product Lifecycle Management (PLM) Tools

- Technical Document Management Tool

Engineering tools used throughout the Solution Development lifecycle shall be classified, qualified, and managed in accordance with applicable standards and corporate procedures. Where required by applicable CENELEC standards, appropriate tool classification and qualification activities shall be performed based on the intended use of the tool and its potential impact on the resulting work products and the Solution.

Artificial Intelligence (AI) tools and applications shall be approved and used in accordance with applicable regulations, corporate policies, governance requirements, and engineering procedures.

All Engineering tools used throughout the Solution Development lifecycle (including supporting and enabling tools) shall be approved for use and shall be appropriately documented (including tool name, version type & number, license, vendor, intended use).

## Verification Steps

Process correct implementation is verified by means of quality audits.

# ACTIVITIES

## Manage Contributions for Bidding (DDQ-01)

(Reference L2 docs: to be assigned)

During the bidding phase, the conceptual Solution is defined, considering reuse aligned with product portfolio and the defined Reference Solution, and the Technical Bid documentation is developed and consolidated. These activities start with Bid Qualification and continue through to Bid Submission, ensuring that the proposed Solution is described in a consistent manner, is feasible, and aligned with customer expectations and the intended Solution delivery approach.

Throughout the Solution Development lifecycle, the Solution Development Team interfaces with Solution Policy and Product Portfolio Management to ensure that the Solution remains aligned with the portfolio strategy, reference solutions, and product / platform baselines. Solution Policy and Product Portfolio Management provides guidelines, reference solutions, and applicable product data that support both bidding and Solution Development activities.

The Solution Development Team shall perform the following activities:

- Analyse customer and stakeholder needs, operational context, and constraints.

- Identify applicable requirements, including RAM, safety, quality, cybersecurity, sustainability, environmental compliance, export control, and any other relevant regulatory aspects.

- Develop and evaluate alternative Solution concepts, perform trade-off analysis, maintain justification records, and ensure convergence towards a coherent and feasible Solution concept.

- Define the high-level architecture, Solution Items, and interfaces, taking into account key engineering aspects (e.g. RAM, safety, cybersecurity, sustainability, effective lifespan) and product portfolio strategy to maximize reuse.

- Identify and validate key assumptions, risks, and constraints affecting feasibility.

- Provide technical inputs, cost drivers, effort and schedule estimations.

- Assess and document the applicability of existing product / platform baselines. Where no applicable baseline exists, the relevant Solution Items shall be identified as new; where reuse is applied, the reuse level and any required update to the baseline shall be justified and recorded.

- Where existing product / platform baselines are reused, assess and document compliance with the applicable requirements.

## Plan and Coordinate Solution Development (DDQ-02)

(Reference L2 docs: to be assigned)

Following project initiation, Solution Development activities are planned and coordinated across the development lifecycle to ensure controlled, consistent, and aligned development of the Solution. This includes establishing the Solution Development approach, organising the Solution Development Team, and defining the framework for execution, governance, and development lifecycle control, including Solution Development milestone reviews at the end of each applicable development phase (e.g. bid handover phase, planning phase, specification phase, architecture phase, design phase, implementation phase, integration & verification phase).

The Solution Development Team interfaces with Solution Policy and Product Portfolio Management to ensure that the Solution remains aligned with the portfolio strategy and roadmap, reference solutions, and product / platform baselines. Solution Policy and Product Portfolio Management provides guidelines, standard solutions, and applicable product data that support and enable Solution Development activities.

The Project Engineer (supported by the Solution Development Team) shall perform the following activities:

- Define and maintain the overall Solution Development approach, including methods, tools, development lifecycle (e.g. waterfall model, iterative model, Agile model) and practices for design, implementation, integration, verification, and validation.

- Define Solution Development scope based on Solution decomposition.

- Define Solution structure by reviewing scope, inputs, constraints, and planning assumptions.

- Refine, maintain, and manage the Solution decomposition into progressively more detailed Solution Items and associated Work Packages. For complex Solutions, establish multiple levels of Solution Items with clearly defined deliverables, responsibilities, assigned Work Package Managers / Leaders, and coordinated teams across the Solution Development lifecycle to ensure alignment of the overall Solution.

- Define integration, verification, validation, and qualification strategies.

- Plan design, implementation, integration, verification, validation, and qualification activities.

- Plan sustainability and circularity assessment activities so that their results are available in time to influence the design choices they are intended to inform.

- Manage assigned Solution Development activities in accordance with the established Solution Development framework.

- Define, plan, and conduct Solution Development milestone reviews (e.g. requirements definition, design, implementation, test, production / deployment readiness).

- Conduct Solution Development milestone reviews to verify, in a formal, documented, and cross-functional manner, that planned activities and expected maturity targets for the relevant phase have been adequately completed and achieved.

- Define, assess, and manage the Solution maturity level throughout the development lifecycle.

- Manage technical risks, issues, and dependencies across the development lifecycle.

- Manage company internal dependencies (e.g. technology readiness from Research & Innovation, roadmap from Product Portfolio), company external dependencies (e.g. from customer, subcontractors, suppliers, Project Management) and the associated risks and mitigation actions.

- Maintain traceability and configuration baselines within their scope to support controlled and traceable development of the Solution.

- Develop and maintain discipline-specific plans and contribute to overall engineering plans, ensuring consistency and alignment of engineering management and control plans.

## Capture and Manage Requirements (DDQ-03)

(Reference L2 docs: to be assigned)

Throughout the Solution Development lifecycle, requirements are captured and managed to define the Solution and its constituent Solution Items. This ensures that the Solution definition remains complete, consistent, and aligned with customer and stakeholder needs and acceptance criteria, supported by a controlled and progressively consolidated traceability framework.

The Solution Development Team shall perform the following activities:

- Capture, structure, analyse, and maintain the requirements that define the Solution and its constituent Solution Items ensuring full compliance with the Customer Requirements Specification.

- Develop and refine requirements content in coordination with relevant contributors.

- Maintain traceability between levels of requirements, design outputs, verification methods, and supporting evidence through the Requirements Traceability Matrix (RTM).

- Update the requirements repository throughout the development lifecycle and control evolution of the requirements baseline.

- Progressively complete and consolidate the Requirements Traceability Matrix.

- Ensure that the Solution definition remains complete, concise, verifiable, consistent, and aligned with its source needs, contractual obligations, regulatory constraints, and acceptance criteria.

- Ensure alignment to the product portfolio strategy and reuse optimization.

- Identify and formalise functional, non-functional, RAM, safety, quality, cybersecurity, sustainability, environmental compliance, environmental conditions, and regulatory requirements.

- Allocate requirements to Solution Items and associated interfaces.

- Identify and manage special or critical requirements requiring specific treatment due to their impact on safety, cybersecurity, regulatory compliance, performance, or customer acceptance.

- Support validation of requirements completeness and correctness.

## Capture and Manage Interfaces (DDQ-04)

(Reference L2 docs: to be assigned)

Throughout the Solution Development lifecycle, interfaces are managed to ensure the coherent integration of the Solution and its constituent Solution Items, resulting in a consistent and controlled interface baseline.

The Solution Development Team shall perform the following activities:

- Identify, define, manage, and resolve the interfaces required to ensure coherent integration of the Solution and its constituent Solution Items.

- Capture, document, and monitor interfaces in a structured manner.

- Develop interface definitions and manage the required interactions among the involved parties.

- Progressively consolidate interface data as the Solution definition matures.

- Identify, manage, and resolve open interface issues.

- Verify consistency and alignment between interface inputs and outputs.

- Ensure consistency of interface definitions with design, integration, and verification activities.

- Maintain interface specifications and agreements, ensuring that the agreed interface baseline is achieved and formally documented.

## Design Solution (DDQ-05)

(Reference L2 docs: to be assigned)

The Solution is developed based on the Reference Solution defined by Solution Policy and on the valid Solution Design Policy, implementing a coherent architecture and detailed technical definition, ensuring that requirements are transformed into implementable and justified design solutions, supporting subsequent integration, verification, validation and final acceptance.

The Solution Development Team shall perform the following activities:

- Translate applicable requirements, constraints, and interface conditions into the Solution architecture and design definition, starting from the Reference Solution, including relevant evolution steps in compatibility/compliance with the Target Architecture.

- Analyse requirements applicable to the Solution Items to be developed.

- Design the Solution in compliance with the applicable Solution Design Policy and provide the corresponding traceability.

- Produce the technical definition required for Solution implementation.

- Ensure consistency, compliance, and integration across the Solution.

- Develop the Solution architecture and progressively refine the detailed design definition in a controlled manner.

- Define Solution Items and internal interfaces.

- Perform analyses and trade-offs supporting design decisions, including trade-offs between circularity and other design drivers.

- Maintain design and justification records.

- Conduct and document design reviews and maturity assessments.

- Define the applicability and implementation of the valid Solution Design Policy, in alignment with Portfolio Evolution.

## Make-or-Buy Solution Items (DDQ-06)

(Reference L2 docs: to be assigned)

Solution Items are developed or procured to realise the Solution in accordance with the defined design, requirements, and performance expectations, ensuring readiness for integration into the Solution.

The Solution Development Team shall perform the following activities:

- Analyse and prepare Make-or-Buy proposal for review and decision making including an assessment of technical, commercial, strategic, and Life Cycle Cost (LCC) considerations, and maintain justification records.

- Develop or procure the Solution Items required to realise the Solution.

- Ensure alignment of all Solution Items with the defined design, applicable requirements, and performance expectations.

- Ensure all technologies used in the Solution have passed the relevant Main Gate in Research & Innovation and have a level of maturity over TRL 5.

- Perform hardware development, software development, and integration activities for internally developed Solution Items.

- Provide suppliers with the applicable Product Technical Specification and related technical inputs, including the applicable circularity requirements (e.g. recycled and renewable content, material and substance declaration).

- Provide component requirements, updates, and associated specifications required for the definition, codification, and maintenance of Solution components to the relevant Commercial Component Management and Industrialization Teams.

- Ensure that externally supplied items are codified according to the Commercial Component Management process.

- Use codified components and associated component status information, including lifecycle data provided by the Commercial Component Management Team, when selecting, developing, procuring, and maintaining Solution Items.

- Request and coordinate prototype, test equipment, compliance assessment, and other industrialisation support activities from the relevant Industrialization Teams, as required.

- Manage supplier technical interactions and monitor supplier deliverables.

- Ensure that developed and procured Solution Items satisfy the applicable requirements and specifications and are ready for integration, verification, and validation.

## Integrate, Verify & Validate Solution (DDQ-07)

(Reference L2 docs: to be assigned)

Throughout the Solution Development lifecycle, integration, verification and validation activities are performed to demonstrate that the Solution meets applicable requirements and fulfils its intended use, providing the basis for acceptance.

The Solution Development Team shall perform the following activities:

- Perform requirements review to define integration, verification, and validation strategy.

- Perform verification method analysis and complete Requirements Traceability Matrix (RTM) with evidence of compliance.

- Perform integration, verification, and validation activities across the Solution Development lifecycle to demonstrate compliance with the Solution requirements.

- Verify that the Solution definition, work products, and realised Solution meet applicable requirements.

- Validate that the Solution is fit for its intended use.

- Plan and execute review, analysis, inspection, demonstration, and test activities.

- Coordinate product qualification activities for the Solution with the relevant Industrialization Teams, including EMC, shock & vibration, thermal management, climatic / environmental testing, reliability engineering and prediction, and other applicable qualification activities, and incorporate the results into the verification and validation evidence.

- Collect and maintain evidence supporting compliance, completeness, and acceptance.

- Ensure traceability between requirements, verification activities, and results.

- Identify issues during integration, pre-verification, verification, and validation activities.

- Address identified issues and perform re-assessment as necessary.

- Consolidate results into a complete, consistent and traceable body of evidence supporting Solution acceptance.

## CyberSecure Solution (DDQ-08)

(Reference L2 docs: to be assigned)

Throughout the Solution Development lifecycle, cybersecurity activities are defined and implemented to ensure that the Solution is developed, maintained, and accepted in accordance with applicable cybersecurity requirements, constraints, and standards. Cybersecurity shall be implemented in compliance with the applicable Solution Design Policy.

The Solution Development Team shall perform the following activities:

- Define, plan, and implement cybersecurity activities throughout the Solution Development lifecycle.

- Ensure that the Solution is developed and maintained in accordance with the applicable cybersecurity context, requirements, constraints, and recognised standards (e.g. CRA).

- Perform cybersecurity assessments across the relevant levels of the Solution.

- Identify, evaluate, and manage cybersecurity risks.

- Prepare and maintain the cybersecurity management reporting as the Solution definition matures.

- Produce outputs required to demonstrate that cybersecurity risks are controlled and aligned with acceptance criteria.

- Support the integration of cybersecurity requirements and considerations into design, development, integration, and verification activities.

## Manage Obsolescence within Solution Development (DDQ-09)

(Reference L2 docs: to be assigned)

Throughout the Solution Development lifecycle, obsolescence is managed to ensure continuity, maintainability, and long-term availability of the Solution and its constituent Solution Items.

The Solution Development Team shall perform the following activities:

- Obtain, review, and consider obsolescence analyses and obsolescence notifications provided by the relevant Obsolescence Management Teams involved in Commercial Component Management, SRS Industrialisation, and RS Obsolescence Management.

- Ensure availability and use of relevant lifecycle and obsolescence data for Solution Items.

- Integrate obsolescence-related inputs into the Solution definition and baseline.

- Assess and manage impacts of obsolescence status on design, integration, and maintainability, including risks related to component availability and component lifecycle constraints.

- Evaluate reuse, refurbishment and remanufacturing of components, and lifetime extension as obsolescence mitigation options, and make the resulting lifetime data available for circularity performance assessment.

## Design for Sustainability (DDQ-10)

(Reference L2 docs: to be assigned)

Throughout the Solution Development lifecycle, sustainability and circular economy principles are integrated into the design and development of the Solution and its constituent Solution Items to minimise environmental impact, optimise resource efficiency, and support long-term lifecycle performance. Sustainability shall be implemented in compliance with the applicable Solution Design Policy and the overall corporate sustainability strategy. This activity complements “Design for Environmental Compliance” by focusing on proactive design optimisation rather than regulatory compliance.

The Solution Development Team shall perform the following activities:

- Assess sustainability and environmental requirements, including applicable regulatory, corporate, and customer requirements, confirmation of compliance status for reused Solution Items and product / platform baselines, and maintenance of the associated traceability.

- Assess lifecycle environmental performance through LCA and use the results to identify environmental hotspots, minimise environmental impacts, and support design decisions, trade-offs, and Solution improvement activities.

- Define circularity objectives and scope of analysis, including the identification of circularity-related impacts, risks, opportunities, assessment boundaries, and material flows relevant to the Solution.

- Apply circular economy principles by prioritising rethink, reduce, reuse, repair, refurbishment, remanufacturing, recycling, and lifetime extension strategies where appropriate, and by improving circularity performance, including circular material inflows and outflows.

- Integrate environmentally conscious design by considering resource efficiency, energy consumption, material selection, recyclability, maintainability, repairability, modularity, upgradability, and end-of-life recovery throughout the Solution lifecycle.

- Manage product circularity data, including material composition, recycled, reused, and renewable content, recovery potential, design life, critical raw materials, hazardous substances, and applicable Digital Product Passport information.

- Define and evaluate carbon reduction measures by identifying opportunities to reduce lifecycle environmental impacts and greenhouse gas emissions and assessing their technical, operational, and economic implications.

- Integrate sustainability into Solution decisions by incorporating sustainability and circularity considerations into design reviews, trade-off analyses, Solution baselines, and continuous improvement activities.

- Provide sustainability and circularity inputs to Solution Policy and Product Portfolio Management, Industrialization, Supply Chain, and other relevant stakeholders to support lifecycle performance assessment, reporting, and decision-making.

## Design for Environmental Compliance (DDQ-11)

(Reference L2 docs: to be assigned)

Throughout the Solution Development lifecycle, environmental requirements are managed to ensure compliance with applicable regulations and standards, as well as suitability for the intended operating conditions. Environmental Compliance shall be implemented in compliance with the applicable Solution Design Policy.

The Solution Development Team shall perform the following activities:

- Identify, implement, and maintain applicable environmental regulations, standards, and requirements for the Solution and its constituent Solution Items.

- Ensure that environmental and product compliance requirements applicable to the target market are obtained from the relevant Industrialization Teams and incorporated into the Solution requirements and definition (e.g. REACH, RoHS, WEEE, ESPR, and Digital Product Passport requirements).

- Integrate environmental requirements into design, development, verification, supplier selection, and change management activities.

- Address aspects related to materials, restricted substances, energy efficiency, emissions, recyclability, end-of-life and environmental performance by obtaining and considering relevant compliance and environmental assessment data from the relevant Industrialization Teams, such as material declarations, substance declarations, recyclability and recoverability assessments, and life cycle assessments (LCA), as applicable.

- Consider environmental requirements and assessment results in technical decisions and during supplier and component selection.

- Ensure continued conformity of the Solution and its Solution Items.

- Perform verification and validation activities to provide evidence that environmental constraints are met.

- Produce and maintain environmental documentation, data, compliance evidence, and documented substantiation of environmental and circularity claims associated with the Solution, in accordance with applicable regulations.

## Leverage Artificial Intelligence (DDQ-12)

(Reference L2 docs: to be assigned)

Throughout the Solution Development lifecycle, Artificial Intelligence (AI) technologies shall be considered and used where beneficial to improve quality, productivity, efficiency, innovation, and support decision-making in engineering and development activities. AI usage shall be performed in accordance with applicable regulations, standards, contractual obligations, and corporate policies (e.g. EU AI Act, intellectual property requirements, export control regulations, corporate AI governance and information security policies).

The Solution Development Team shall perform the following activities:

- Evaluate and apply AI technologies where appropriate across the Solution Development lifecycle, including planning, requirements management, design, implementation, verification, validation, documentation, and knowledge management activities.

- Use approved AI tools and services in accordance with project objectives, applicable regulations, contractual obligations, corporate policies and authorised engineering environments.

- Ensure that AI supports, but does not replace, engineering judgement and professional responsibility, and that qualified personnel retain responsibility for engineering decisions and approvals.

- Verify AI-generated outputs for correctness, completeness, consistency, and suitability before their use in engineering activities or deliverables.

- Protect confidential, proprietary, and regulated information when using AI technologies.

- Identify and manage technical, quality, safety, cybersecurity, intellectual property, and compliance risks associated with AI usage.

- Ensure that AI-assisted outputs are subject to the same review, verification, validation, approval, and configuration management requirements as any other engineering work product.

## Manage Engineering Discipline (DDQ-13)

(Reference L2 docs: to be assigned)

Engineering discipline is managed to continuously enhance organisational competitiveness across the Solution Development lifecycle, including quality, lead time, costs, and attractiveness of products and solutions.

The relevant Heads of Engineering Disciplines (supported by the Project Engineer and the Solution Development Team) shall perform the following activities:

- Define the strategy and priorities of the engineering organization within their perimeter aligned with global engineering vision, strategy and goals.

- Ensure engineering competitiveness by defining and driving the competitiveness improvement plan and the maturity of their organization, based on business challenges and weaknesses found from competitiveness KPI and root cause analysis of problems found on bids and projects.

- Ensure adoption and proper utilization of globally defined processes, practices, and tools.

- Provide engineers with an efficient engineering environment made of:

  - An efficient workspace that allows collaboration and focus.

  - Competitive Process, Practices and Tools and efficient IT infrastructure that runs the tools (provided by IS/IT organization).

  - An efficient support and coaching organization to support the deployment of process, practices and tools.

- Ensure knowledge capitalization and sharing.

- Ensure skills recruitment, evaluation and development, including engineers career development and associated records are appropriately maintained.

- Ensure accountability on bids, portfolio and customer projects deliverables, including the best allocation of resources to bids and projects.

- Develop organisational maturity and foster a customer focused mindset throughout the engineering organisation.

- Propose potential peer assessors to the global pool and enable assessors’ availability for peer assessment participation.

- Define and deploy an engineering Make-or-Buy methodology in order to contribute to the achievement of competitiveness objectives.

- Contribute to the global processes and tools evolution and definition.

# TAILORING GUIDELINES

Project tailoring defines the controlled adaptation of the Solution Development process to the specific context, scope, complexity, and risk of a project. It ensures that roles, activities, milestones, and deliverables are appropriately adjusted to project needs while preserving compliance with applicable international and national standards, corporate processes, contractual obligations, and fundamental engineering principles.

Project Tailoring may include:

- Roles

  - Allocation of multiple roles to one person for small projects, provided this does not conflict with independency requirements imposed by applicable standards (e.g. CENELEC)

  - Removal of roles which are not needed in the current project context due to limited scope (e.g. omission of the HW WPM role where no HW development is included in the scope)

- Milestones and Solution Development Reviews

  - Combination of multiple review milestones (all checkpoints from the combined milestones remain applicable but are assessed together)

  - Adjustment of review scope to align to the scope of the project (e.g. HW checkpoints or milestones omission where no HW development is included in the scope)

- Activities and Deliverables

  - Reduction (where out of scope) or combination of Solution Development lifecycle activities

  - Merging of documentation and deliverables

Typical Tailoring Scenarios include:

- Roll‑out Projects: focus on reuse and deployment; reduced design effort; verification focused on integration and site-specific validation

- Bug Fixes & Small Functional Extensions: limited scope; focus on impact analysis, implementation, and regression testing

- Maintenance & Service Contracts: continuous activities; simplified governance; periodic reviews instead of formal milestones

Project Tailoring Documentation and Approval

- Tailoring shall be documented in the Engineering Management Plan (for delivery projects) or in the Development Project Management Plan (for portfolio projects)

- Tailoring of the standard process shall be justified and traceable

- Tailoring decisions shall be reviewed and approved by:

  - Project Engineer

  - Project Quality Manager

Changes to approved tailoring decisions during project execution shall be subject to the project's formal change control process, including impact assessment and approval prior to implementation.

Project Tailoring shall:

- Preserve traceability, verification, and safety principles

- Remain transparent and auditable

- Not compromise compliance with applicable standards

- Not compromise compliance with global processes and applicable tools

# MEASURES

Please refer to G-KPI L03001 that defines the KPIs associated with the process.

# R.A.C.I.

| Activity ID & Name | R = Responsible | A = Accountable | C = Consulted | I = Informed |
| --- | --- | --- | --- | --- |
| DDQ-01 Manage Contributions for Bidding | Solution Development Team | Project Engineer (PE) | Technical Authority, Bid Manager (BM), Project Quality Manager (PQM), SRS Project RAMS Manager, VHC Project RAM Manager, VHC Project Safety Manager, Relevant Functional Managers |  |
| DDQ-02 Plan and Coordinate Solution Development | Project Engineer (PE) | Project Engineer (PE) | Technical Authority, HSE Referent, Project Controller (PJC), Project Quality Manager (PQM), SRS Project RAMS Manager, VHC Project RAM Manager, VHC Project Safety Manager Project Manager (PM) | Project Risk Manager, Project Team, LoB Product Portfolio Management |
| DDQ-03 Capture and Manage Requirements | Solution Development Team | Project Engineer (PE) | Technical Authority, HSE Referent, Project Quality Manager (PQM), SRS Project RAMS Manager, VHC Project RAM Manager, VHC Project Safety Manager | Project Manager (PM) |
| DDQ-04 Capture and Manage Interfaces | Solution Development Team | Project Engineer (PE) | Technical Authority, HSE Referent | Project Manager (PM) |
| DDQ-05 Design Solution | Solution Development Team | Project Engineer (PE) | Technical Authority, HSE Referent, Project Quality Manager (PQM), SRS Project RAMS Manager, VHC Project RAM Manager, VHC Project Safety Manager | Project Manager (PM) |
| DDQ-06 Make-or-Buy Solution Items | Solution Development Team | Project Engineer (PE) | Technical Authority, Project Quality Manager (PQM), SRS Project RAMS Manager, VHC Project RAM Manager, VHC Project Safety Manager SRS Supply Chain and Procurement Manager (SCPM), VHC Project Operations Manager (POM) | Project Manager (PM) |
| DDQ-07 Integrate, Verify & Validate Solution | Solution Development Team (1) | Project Engineer (PE) (1) | Technical Authority, Project Quality Manager (PQM), SRS Project RAMS Manager, VHC Project RAM Manager, VHC Project Safety Manager | Project Manager (PM) |
| DDQ-08 CyberSecure Solution | Solution Development Team | Project Engineer (PE) | Technical Authority, Project Quality Manager (PQM), SRS Project RAMS Manager, VHC Project Safety Manager | Project Manager (PM) |
| DDQ-09 Manage Obsolescence within Solution Development | Solution Development Team | Project Engineer (PE) | Project Quality Manager (PQM), SRS Project RAMS Manager, VHC Project RAM Manager, VHC Project Safety Manager | Project Manager (PM) |
| DDQ-10 Design for Sustainability | Solution Development Team (2) | Project Engineer (PE) | Project Quality Manager (PQM), SRS Project RAMS Manager, VHC Project Safety Manager | Project Manager (PM) |
| DDQ-11 Design for Environmental Compliance | Solution Development Team (2) | Project Engineer (PE) | Project Quality Manager (PQM), SRS Project RAMS Manager, VHC Project Safety Manager | Project Manager (PM) |
| DDQ-12 Leverage Artificial Intelligence | Solution Development Team | Project Engineer (PE) | Project Quality Manager (PQM), SRS Project RAMS Manager, VHC Project Safety Manager | Project Manager (PM) |
| DDQ-13 Manage Engineering Discipline | Relevant Heads of Engineering Disciplines | Relevant Heads of Engineering Disciplines | Project Engineer (PE), Solution Development Team |  |

Note: “Head of” is not intended as the specific job title of an individual, rather it represents the link to the latest organisational structure.

(1) Assignment of accountability does not in itself compromise the independence of verification and validation activities. Accountability remains with the designated accountable role, while verification and validation responsibilities shall be assigned in accordance with the independence requirements of the applicable standards (e.g. CENELEC) and the allocated SIL.

(2) SRS Ecodesign Manager is not part of the Solution Development Team and must be consulted externally of the DDQ process.

# INPUT AND OUTPUT DETAILS

## Input Details

| ID | INPUT/INTERFACE |  | PROCESS CLUSTER |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | GENERIC | SPECIFIC | STEERING | SUPPORT | EXECUTION | CUSTOMER FACING |
| I1 | Bidding Documents | - Bid Information and tender documentation including technical documents, scope of work and time schedule - Bid Deliverables List - Bidding Deliverables and Templates - Consortium/JV Agreement with other entities - Draft Contract (if available) | - | - | - | - Bidding |
| I2 | PM Execution Baseline and Contractual Interfaces | - During Project Launch/Planning: Handover Dossier, Consolidated WBS and CBS, Budget, Second Level Schedule, Project Management Plan. - Iteratively during Project Execution: Updated WBS/CBS/budget, Risk/Opportunity/Contingency, Second level schedule, Authorization of Change, Authorization of Delivery to Customer | - | - | - | - Project Management |
| I3 | Product Portfolio Deliverables | - Portfolio data and roadmaps | - | - | - RS Product Portfolio Management | - |
|  |  | - Solution Strategic Plan (Reference Solution, Solution Target Architecture, Standardization Strategy, Technical Positions, and Solution Design Policies) - Product Line Roadmaps - Product Plans | - | - | - SRS Solution Policy and Product Portfolio Management | - |
| I4 | Supporting Plans | - Configuration Management Plan (CMP) | - | - | - Configuration Management | - |
|  |  | - Project Quality Management Plan (PQMP) - Quality Management Plan (QMP) - Software Quality Assurance Plan (SQAP) | - | - | - | - Project Quality Assurance |
|  |  | - Regional Integrated Plan | - | - | - RS Operations Integrated Planning | - |
|  |  | - **RAM Plan | - | - | - **RS RAMS - **SRS RAMS | - |
|  |  | - Safety Plan | - | - | - **RS RAMS - SRS RAMS | - |
|  |  | - Test & Commissioning Master Plan | - | - | - SRS Commissioning | - |
|  |  | - Test Plan (Type Test) - Test Programme (Type Test) | - | - | - RS Project Validation | - |
| I5 | R&I Deliverables | - Global Innovation Plan - Global Innovation Strategy |  |  | - Research and Innovation |  |
|  |  | - External R&I Orgs outcome sharing and dissemination - Sector Standardization Participation outcome dissemination | - | - | - Research and Innovation | - |
| I6 | Configuration Deliverables and Change Triggers | - “Red Markup” documentation for as built | - | - | - SRS Commissioning | - |
|  |  | - Approved/rejected Deviations/Waivers | - | - | - Configuration Management | - |
|  |  | - Authorised Technical Change Request | - | - | - Configuration Management | - |
|  |  | - Authorised WPR Problem Report | - | - | - Configuration Management | - |
|  |  | - CCB Reports | - | - | - Configuration Management | - |
|  |  | - Configuration Baseline | - | - | - Configuration Management | - |
|  |  | - Configuration Status Report | - | - | - Configuration Management | - |
|  |  | - Configuration Verification Reports | - | - | - Configuration Management | - |
|  |  | - Engineering Change Notice | - | - | - Configuration Management | - |
|  |  | - Marked-up Drawings | - | - | - SRS Construction | - |
|  |  | - Product Breakdown Structure (PBS) - Location Breakdown Structure (LBS) - Functional Breakdown Structure (FBS) | - | - | - Configuration Management | - |
|  |  | - Project Baseline | - | - | - Configuration Management | - |
|  |  | - Site Modification Request (SMR) | - | - | - SRS Commissioning - SRS Construction | - |
|  |  | - Unique identification of items / documents | - | - | - Configuration Management | - |
| I7 | BUY Items Deliverables | - Codified / Updated Commercial Component - Analysis Report & Solution - 3D Models, Symbol & Footprints | - | - | - Commercial Components Management | - |
|  |  | - Obsolescence Advice - Obsolescence Solution | - | - | - SRS Industrialisation | - |
|  |  | - Contracts / Purchase Orders for EPPPS (including KPIs, SLA and contractually required documents list) | - | - | - Procurement | - |
|  |  | - Purchase Order Documents | - | - | - SRS Supply Chain Management | - |
| I8 | Test, Field and Compliance Deliverables | - Field Operation Data / Problem Report | - | - | - RS Service and Maintenance - SRS Service and Maintenance | - |
|  |  | - On Site Test Report | - | - | - SRS Commissioning | - |
|  |  | - Dual-Use Compliance Report - Fire, Smoke & Toxicity Compliance Report - REACH / ROHS Compliance Report - REACH Declaration - UNIFE Material Declaration - SCIP Dossier and Number - CE Marking Technical Dossier - CE Marking Compliance Report - Product Safety Requirement for CE Marking - Life Cycle Assessment Report | - | - | - SRS Industrialisation | - |
|  |  | - Test Reports (Type Test) | - | - | - RS Project Validation | - |
| I9 | Additional Requirements | - Criteria for Industrialization & Concurrent Engineering Requirements | - | - | - RS Industrialisation | - |
|  |  | - Cybersecurity Governance Guidelines (including countermeasures, standards, threat intelligence). | - | - Information Technology | - | - |
|  |  | - HSE Requirements | - | - HSE | - | - |
|  |  | - LCA and S-LCA High Level Requirements | - | - | - RS Product Portfolio Management | - |
|  |  | - Legislative Requirements, Applicable Standards List (including mandatory standards at both Vehicle and System Level) | - | - | - RS Homologation | - |
|  |  | - Product Safety Requirements for CE Marking | - | - | - SRS Industrialisation | - |
| I10 | RAMS Requirements and Deliverables | - RAM Requirements, Safety Requirements - RAM Systems Specifications - Preliminary Hazard Analysis - Proposal for RAMS & LCC platform improvement - RAMS&LCC analyses (e.g. vehicle breakdown Preventive maintenance Plan, RAM demonstration plan) | - | - | - RS RAMS | - |
|  |  | - Preliminary FMECA - Hazard Log - Safety & Security Log Updated | - | - | - SRS RAMS | - |
| I11 | Industrialisation, Production and HSE Deliverables | - Energy Consumption Data | - | - Real Estate and Physical Security | - | - |
|  |  | - HSE Communication - HSE Monitoring Reports including Manufacturing Environmental Data - HSE Risk Assessment Report - HSE Documents - HSE Changes Review - HSE Suppliers/ Partners Audit and Qualification Reports | - | - HSE | - | - |
|  |  | - Prototype - Improvement Solution - Test Tool - Approval - Rejection for Industrialization | - | - | - SRS Industrialisation | - |
|  |  | - Special Processes Management Meeting Report | - | - | - RS Manufacturing | - |
| I12 | Quality Audit, Advice and Reports | - Quality Alert, Veto - Decision outcome of Phase Gate Reviews - Project Audit Reports - NC Report | - | - | - | - Project Quality Assurance |

** to be confirmed

## Output Details

| ID | OUTPUT/INTERFACE |  | PROCESS CLUSTER |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | GENERIC | SPECIFIC | STEERING | SUPPORT | EXECUTION | CUSTOMER FACING |
| O1 | - | - Engineering Pre-Qualification Deliverables - Engineering Bidding Deliverables | - | - | - | - Bidding |
| O2 | PM Governance and Planning Output | - During Project Launch/Planning: - Initial Contract and Risk Analysis review - Budget up to PHA/PAM - Functional Project Plans - Iteratively during Project Execution: - Regular review of Project progress and deliverables - estimation of changes by function | - | - | - | - Project Management |
| O3 | Plans | - BIM Execution Plan (BEP) | - | - | - SRS Construction - SRS Service and Maintenance | - Project Management |
|  |  | - Cybersecurity Management Plan | - | - | - **RS RAMS | - |
|  |  | - Development Project Management Plan (DPMP) | - | - | - Configuration Management - SRS RAMS - SRS Solution Policy and Product Portfolio Management | - **Project Quality Assurance - Project Risk Management |
|  |  | - Engineering Management Plan (EMP) | - | - | - Configuration Management - RS RAMS - SRS RAMS | - Project Management - Project Quality Assurance |
|  |  | - Engineering Master Schedule (EMS) | - | - | - RS Operations Integrated Planning | - |
|  |  | - Interface Management Plan (IMP) | - | - | - SRS RAMS | - |
|  |  | - Maintenance Plans | - | - | - RS Service and Maintenance - SRS Service and Maintenance | - |
|  |  | - Requirements Management Plan (RMP) | - | - | - RS Homologation - RS Project Validation - RS RAMS - SRS RAMS | - Project Quality Assurance |
|  |  | - Test Plan | - | - | - SRS Commissioning | - |
|  |  | - Time and Cost forecast for new/updated platform | - | - | - RS Product Portfolio Management | - |
|  |  | - Type Test Plan | - | - | - SRS Industrialisation - SRS Supply Chain Management | - |
|  |  | - Verification and Validation (V&V) Plan | - | - | - | - Project Quality Assurance |
| O4 | Technical Documentation | - Bill of Material (BOM) | - | - | - SRS Manufacturing - SRS Supply Chain Management | - |
|  |  | - Bill of Quantity (BOQ) | - | - | - SRS Construction | - |
|  |  | - BIM Digital Models | - | - | - SRS Construction | - Project Management |
|  |  | - Design for Construction | - | - | - SRS Construction | - |
|  |  | - Documents and Configuration Data | - | - | - Configuration Management | - |
|  |  | - Drawings and Test Specification | - | - | - SRS Manufacturing | - |
|  |  | - EBOM, Detailed and updated Technical Documentation for System & Subsystems including as-designed configuration: Descriptions, Specifications, Drawings, Electrical schematics, Calculations, Software documentation, etc. | - | - HSE | - RS Homologation - RS Industrialisation - RS Project Validation - RS Quality Control - RS RAMS - RS Routine Test and Acceptance - **RS Service and Maintenance | - **Project Quality Assurance |
|  |  | - Initial Product Breakdown Structure (PBS) (including reusable items and components) | - | - | - Configuration Management | - |
|  |  | - Interface Control and Definition Documents (ICDDs) | - | - | - SRS RAMS | - |
|  |  | - List of applicable Standards and Regulatory Requirements | - | - | - Configuration Management | - |
|  |  | - Maintenance Manuals | - | - | - RS Service and Maintenance - SRS Service and Maintenance | - |
|  |  | - Product Data Sheet | - | - HSE | - Procurement - RS Homologation - RS Industrialisation - RS Manufacturing - RS Operations Integrated Planning - RS Product Portfolio Management - RS Project Validation - RS Quality Control - RS RAMS - RS Routine Test and Acceptance - RS Service and Maintenance | - Project Management - Project Quality Assurance |
|  |  | - Product Technical Documentation | - | - | - SRS Industrialisation - SRS RAMS | - |
|  |  | - Project Requirements | - | - | - Configuration Management - RS Project Validation | - |
|  |  | - Requirements Traceability Matrix (RTM) | - | - | - RS Homologation - RS RAMS - SRS Industrialisation | - **Project Quality Assurance |
|  |  | - Safety & Security Log | - | - | - SRS RAMS | - |
|  |  | - Security OS&M Guidelines | - | - | - SRS Asset Operation - SRS Service and Maintenance | - |
|  |  | - Special Processes Specification | - | - | - RS Manufacturing | - |
|  |  | - System/Subsystem Architecture Definition and Requirements Specifications | - | - | - SRS Asset Operation - SRS RAMS | - |
|  |  | - Technical Documentation | - | - HSE | - SRS Asset Operation - SRS Industrialisation | - |
|  |  | - Test Procedures | - | - | - SRS Commissioning | - |
|  |  | - Test Specifications (for System & Subsystems, Type Tests) | - | - | - RS Project Validation | - **Project Quality Assurance |
|  |  | - Type Test Procedures | - | - | - SRS Industrialisation - SRS Supply Chain Management | - |
|  |  | - Updated Modularity Matrix | - | - | - RS Product Portfolio Management - **SRS Solution Policy and Product Portfolio Management | - |
|  |  | - Products-Projects Matrix | - | - | - SRS Solution Policy and Product Portfolio Management | - |  |
| O5 | Configuration Change Needs | - Technical Event | - | - | - Configuration Management | - **Project Quality Assurance |
|  |  | - Site Modification Instruction (SMI) | - | - | - SRS Construction - SRS Commissioning | - |
| O6 | BUY Needs and Deliverables | - Obsolescence Information | - | - | - RS Product Portfolio Management - RS Service and Maintenance - SRS Service and Maintenance | - |
|  |  | - Purchase Technical Specification (PTS) | - | - | - SRS Supply Chain Management | - |
|  |  | - Technical Documentation for EPPPS | - | - | - Procurement | - |
| O7 | Reports | - Cybersecurity Case | - | - | - **RS RAMS - **RS Service and Maintenance - SRS Asset Operation - SRS RAMS - SRS Service and Maintenance | - |
|  |  | - Type Test Report | - | - | - **RS RAMS - SRS Industrialisation - SRS RAMS - SRS Supply Chain Management | - |
|  |  | - Verification Report - Validation Report | - | - | - **RS RAMS - SRS Commissioning - SRS RAMS | - Project Quality Assurance |
| O8 | Commercial Component and Industrialisation Needs | - Commercial Component Codification / Update Request - Request for Component Analysis | - | - | - Commercial Components Management | - |
|  |  | - Request for Obsolescence Analysis and Advice - Request for Product Compliance Analysis | - | - | - SRS Industrialisation | - |
|  |  | - Request for Product Improvement / Test Tool - Request for Prototype | - | - | - SRS Industrialisation | - |
|  |  | - Software | - | - | - RS Project Validation - RS Routine Test and Acceptance | - |
|  |  | - Installation Kit | - | - | - SRS Commissioning | - |
|  |  | - IPR Proposals - Patentability Proposals | - | - | - Knowledge Management | - |
|  |  | - LCA & S-LCA data - **Product Circularity Data (material composition, recycled, reused and renewable content, potential/actual recovery, design life, critical raw materials) | - | - | - RS Product Portfolio Management | - |
|  |  | - Product best-practices | - | - Information Technology | - | - |

** to be confirmed