PROJECT AND SYSTEM ENGINEERING MANAGEMENT PLAN

ELEKTRA ÖBB

BL OBB 29.50 / OBB 2.16.0

| APPROVAL |  |  |
| --- | --- | --- |
|  | Name and Role/Job Title | Esignature |
| Written by | B. Koenig / SEM |  |
| Verified by | C. Janneschitz / QAM |  |
| Approved by | K. Ndue / HoD |  |

| LOG OF CHANGES |  |  |  |
| --- | --- | --- | --- |
| Revision | Date | Author | Change Description |
| 01PD01 | 10.07.2026 | B. Koenig | Initial Version |
| 02 |  |  |  |
| 03 |  |  |  |

Contents

1.	SCOPE	7

1.1	Identification	7

1.1.1	General	7

1.1.2	WBS managed as Solution	7

1.1.3	WBS managed as Work Packages	7

1.1.4	Other component versions this engineering solution is based on	8

1.2	System overview	9

1.3	Key points	10

1.3.1	Milestones for Solution	10

1.3.2	Deliverables	11

1.4	Relation with other plans	11

1.5	Baselines of Software Configuration Items and Documentation Labels	11

1.6	Document version history	12

1.6.1	Edition 01	12

1.6.2	Open points / Issues	12

2.	References and terms	13

2.1	Referenced documents	13

2.2	Process basis	13

2.3	Standards and procedures	14

2.4	Terms, abbreviations and acronyms	15

2.4.1	Terms, Abbreviations and Acronyms used in the project	16

2.4.2	Role abbreviations	17

3.	Solution engineering and development process	19

3.1	Organization of solution engineering	19

3.1.1	Solution core team	19

3.1.2	Solution team	19

3.1.3	External project roles	21

3.1.4	Configuration Control Board (CCB)	21

3.2	System engineering supplies	22

3.3	Input data	22

3.4	Preconditions / Related solutions	22

3.5	Technical objectives	22

3.6	Detailed First Level WBS for Work Packages	22

3.7	Special need for training of system engineering team	23

3.8	Constraints / Risks	23

3.9	Work Contained	24

3.10	Work not contained	24

3.11	Responsibility Assignment Matrix	24

3.12	Tools and Facilities	24

3.12.1	Management and Documentation Tools	24

3.12.2	Code Building Tools	26

4.	Process Control	27

4.1	Control of Solution Development	27

4.1.1	Deviation	27

4.1.2	Metrics	27

4.2	Monitoring and Control of System Engineering Activities	27

4.2.1	Periodic Internal Reviews and Meetings	27

4.2.2	Milestone Reviews and Audits	28

4.2.3	Reporting	28

4.3	Critical Technologies	28

4.4	Risk and Opportunities Control	28

4.5	Corrective Action Process	28

4.6	Independent Evaluation and Verification	28

4.7	Estimate/Re-Estimate	28

4.8	Planning	29

4.9	Value Analysis and Design to Cost	29

4.10	Peer Reviews	29

5.	Development scenario and tailoring of the System Engineering Process	30

5.1	Tailoring for this solution	30

5.1.1	Orient the Solution	30

5.1.2	Design the Solution	30

5.1.3	Develop the Solution	30

5.1.4	Integrate and Verify the Solution	30

5.1.5	Validate the solution	30

6.	System Engineering Support	31

6.1	Data and Configuration Management	31

6.2	Confidentiality	31

6.3	Export Control	31

6.4	Capitalization	31

6.5	Measurements and Analysis	31

6.6	Technical and Non-technical Requirements Management and Control	31

6.7	Validation of Requirements	31

6.8	Decision Analysis and Resolution	31

6.9	Subordinate Plans	31

6.10	Quality Assurance	32

6.11	Certification Support Activity	32

6.12	Stakeholder Management	32

APPENDIX A	Criteria for the Selection of Techniques and Measures	33

List of Tables

Table 1: Solution Identification	7

Table 2: WBS managed as Solution	7

Table 3: WBS managed as Work Packages	8

Table 4: Other component versions	8

Table 5: Milestones	9

Table 6: Deliverables	10

Table 7: Referenced Documents	12

Table 8: Standards and Procedures	13

Table 9 : Role abbreviations	17

Table 10: Core team	18

Table 11: Team	19

Table 12: External project roles	20

Table 13: CCB	20

Table 14: Preconditions	21

Table 15: Detailed WBS	21

Table 16: Management and Documentation Tools	23

Table 17: Code Building Tools	25

Table 18: Reviews and Meetings	26

List of Figures

Figure 1: Product Breakdown Structure	10

Figure 2: Manage Project (PRJ)	30

Figure 3: Product Line Engineering Process	30

Figure 4: Develop and Qualify the Solution (DDQS)	30

# SCOPE

Instruction: The process version (can be found here Document List - Quality - Confluence.AT) will be updated by a bookmark in chapter 2.2

The combined PSEMP, Project Management Plan (PMP) and System Engineering Management Plan (SEMP) describes the organisation, work packages, milestones and application of the Management System Release 2026-06.

## Identification

### General

| Cost collector / Project ID: | 100028260 |
| --- | --- |
| Solution: | ATRENDB53-E0 |
| Identification: | ELEKTRA PV OBB 2.16.0 / BL OBB 29.50 |
| SIL: | SIL-4 |
| Security Level: | SL-C 2 |
| Maturity Level: | ML 3 |

Table 1: Solution Identification

### WBS managed as Solution

| In Scope | WBS | Identification | SEM | SIL | Initial Product Version | Target Version | Target date |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | ATRENDB53-E0 | Lock Trac 6131 ELEKTRA OBB | B. Koenig / OEDRM | SIL4 | ELEKTRA PV OBB 2.15.0 | ELEKTRA PV OBB 2.16.0 | see section 1.3.1 |

Table 2: WBS managed as Solution

### WBS managed as Work Packages

A detailed view on all WBS elements is listed in section 3.6. If a WBS below is not in scope of this Solution element, the initial version (and unchanged target version) is stated anyway Instruction: List all WP the related WPM`s and Initial and Target Version. “the required and the committed target date for the WP. Track it as a Milestone in the related Project Plan.

.

|  | Solution Element: | ATRExxxxxx-E0 |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| In Scope | WBS | Ident. | SEM / WPM | Initial Version | Target Version | Target date |
|  | ATRENDB53-E0.P1 | Product Development | B. Koenig / OEDRM | ELEKTRA PV OBB 2.15.0 | ELEKTRA PV OBB 2.16.0 | TQR2 |
|  | ATRENDB53-E0.P1 | FL179 | J. Szoeke / OEDRD | ELEKTRA PV OBB 2.15.0 | ELEKTRA PV OBB 2.16.0 | TQR2 |
|  | ATRENDB53-E0.EBO2 | WPEBO2 | G. Barna / OEDCD | EBO2 OBB 01.99 | EBO2 OBB 02.00 | TRR1 |
|  | ATRENDB53-E0.OREST | WPOREST | R. Ungerboeck / OEDTC | 19.40 | 19.50 | TRR1 |
|  | ATRENDB53-E0.WP3PM | DDT | M. Edelbauer / OEDRD | OBB_29.40_DDT_01 | OBB_29.50_DDT_01 | TRR1 |
|  | ATRENDB53-E0.SEC | WPSEC | R. Hossa Rambo / OEDCD | SEA SW 2.1.2 | SEA SW OBB 2.2.0 | TRR1 |

Table 3: WBS managed as Work Packages

### Other component versions this engineering solution is based on

| Component | Version |
| --- | --- |
| Generic Product Version | PV GEN 2.20.10 |
| SEA Software | SEA SW OBB 2.2.0 |
| SEA Hardware | SEA HW 2.1.0 SEA HW 2.0.3 SEA HW 1.10 SEA HW 1.20 SEA HW 1.21_A SEA HW 1.21 |
| SEC Software Generic | SEC SW GEN 2.2.5 |
| SEC Hardware Generic | SEC HW 2.3.0 SEC HW GEN 2.2.3 |

Table 4: Other component versions

## System overview

Instruction: Describe if the solution / product version is provided and supported for use on e.g. Elektra 1 or Elektra 2.

This solution provides a safe and highly reliable solution to control the railway operation. The objective of this solution is to upgrade the existing functionality of product ELEKTRA OBB and data preparation tools OREST with the scope as defined as follows:

- Scope of Change (SoC) [5] contains features, change requests and defect corrections which are planned to be released.

The initial and target versions of this solution and their work packages for this engineering project are listed in Scope of Change (SoC) [5].Instruction: Update the Product Breakdown Structure and describe the system architecture here

Figure 1: Product Breakdown Structure

## Key points

Instruction: Check the Project Life Cycle 83530275-DDQ-AUT-EN for the relevant milestones (tailoring of milestones should be documented in the separate chapter “Tailoring”). KOM, LR, AR, CR are only relevant if a combined PSEMP is used, if this template is used for a SEMP please delete the corresponding milestones. As mentioned in the Project Life Cycle, AR can be performed before or after the FQR.

### Milestones for Solution

| Milestone | Target Date | Comments |
| --- | --- | --- |
| Kick Off Meeting (KOM) | 30.07.2026 |  |
| Solution Orientation Review (SOR) | 30.07.2026 |  |
| Launch Review (LR) | 30.07.2026 |  |
| Solution Requirements Review (SRR) | 24.09.2026 |  |
| Solution Functional Review (SFR) | 24.09.2026 |  |
| Preliminary Design Review (PDR) | 17.12.2026 |  |
| Critical Design Review (CDR) | 17.12.2026 |  |
| Test Readiness Review (TRR1) | 12.02.2027 |  |
| Technical Qualification Review (TQR1) | 24.06.2027 |  |
| Test Readiness Review (TRR2) | 22.07.2027 |  |
| Technical Qualification Review 2 (TQR2) | 23.09.2027 |  |
| Acceptance Review (AR) | 21.10.2027 |  |
| Final Qualification Review (FQR) | 21.10.2027 |  |
| Closure Review (CR) | 21.10.2027 |  |

Table 5: Milestones

### Deliverables

Deliverables in scope of this engineering project are listed below:

| Deliverable | Target Date | Comment |
| --- | --- | --- |
| Laboratory version for data preparation | TRR1 | verification already started, but not finished |
| Components of the Generic System | TRR1 |  |
| Data preparation rules / directives | TQR1 |  |
| Update of the customer documents "Maintenance and Repair" in case of changes | TQR1 |  |
| Update of the user documents "User Manual System Elefant-NT", “User Manual Webride” in case of changes | TQR1 |  |
| ClearCase views for data preparation containing delivered baseline and associated tools | TQR2 |  |

Table 6: Deliverables

## Relation with other plans

The PSEMP describes the application of the Management System   Solutions Engineering Processes (DDQS) to the design, development and deployment of the Solution ATRENDB53-E0.

This document will be updated as the Solution effort evolves.

A general overview of the Solution and Project documents hierarchy is shown in the Documentation Plan [1].

## Baselines of Software Configuration Items and Documentation Labels

The labelling is based on the definitions of the Configuration Management Plan and as defined in the Documentation Plan. The following labels have to be used:

- “BL_OBB_29.50” for all solution related documents, e.g. PMP, SEMP, CRS, PBS, CCB etc.

- “OBB_29.50” for the software

## Document version history

### Edition 01

Initial edition.

# References and terms

## Referenced documents

If not explicitly stated, the relevant version of a document is referenced in the Documentation Plan [1].

| Nr./Title | Reference | Version |
| --- | --- | --- |
| - PSEMP Project and System Engineering Management Plan | 3BU_15000_2453_DPAPA | latest |
| - Documentation Plan | 3BU_15000_2453_ADAPA | latest |
| - Risk Report | Sharepoint: TBD | latest |
| - Engineering Dashboard | Sharepoint: TBD | latest |
| - Quality Management Plan (QMP) ELEKTRA | 3BU_15000_5244_QMAPA | 11 |
| - Scope of Change (SoC) | 3BU_15000_2453_QEAPA | latest |
| - Design Validation approval (DVa) | n/a; see tailoring chapter 5.1.1 |  |
| - Product and Version Identification (BL-ID, CM) | 3BU_15000_2453_QTAPC | latest |
| - Software Development Tool Classification EN50128 | 3BU_15000_5135_AAAPA | 28 |
| - Configuration Management Plan | 3BU_15000_3338_QMAPA | 11 |
| - CBS | Sharepoint: TBD | latest |

Table 7: Referenced Documents

## Process basis

Instruction: Update the currently released GTS Management System Release based on QMS Change Management Plan 2017 https://e2.at.gts/confluence/display/TQ/Document+List

Info: In case the project is not closed before 30.10.2026, it is mandatory to change to the new CENELEC EN50716:2023 norm which supersedes EN 50128, if not it is recommended to mention already the new norm as well and adapt step by step to the new norm (updates regarding tables in the appendix of the new norm).

The project is set up with the Management System Release 2026-06 as process basis. Changes in this process basis (e.g. adaptation to a new service release of Management System) have to be analyzed, especially regarding the impact on already existing work products, and have to be documented and approved.

## Standards and procedures

| Nr./Title | Publishing Date/ Reference | Version/ Revision |
| --- | --- | --- |
| - ISO 22163:2023 Railway applications – Railway quality management system – ISO 9001:2015 and particular requirements for application in the rail sector | 2023 |  |
| - EN 50716:2023 (supersedes EN 50128) Railway Applications – Requirements for software development | 2011, 2020, 2021, 2023 |  |
| - EN 50129:2018 Railway applications Safety related electronic systems for signalling | 2018 |  |
| - ISO 9001:2015 Quality management system - Requirements | 2015 |  |
| - EN 50126‑1:2017+A1:2024 Railway applications. The specification and demonstration of reliability, availability, maintainability and safety (RAMS) Part 1: Generic RAMS Process Part 2: Systems Approach to Safety | 2024 |  |
| - EN 50121-4:2016 Railway applications Electromagnetic compatibility Part 4: Emission and immunity of the signalling and telecommunications apparatus | 2016 |  |
| - EN 50159:2010 + A1:2020 Railway applications – Communication, signalling and processing systems – Safety-related communication in transmission systems | 2010, 2019, 2020 |  |
| - Management System Process Manage Risks and Opportunities | Part of 87200984-00-PRJ-GRP-EN chapter 8.6 |  |
| - Design, Develop and Qualify the Solution | 87202127-00-DDQ-GRP-EN |  |
| - Management System Process DDQ-SW - Design, develop and qualify the Software solution | 87202125-00-DDQ-GRP-EN |  |
| - Management System Process DDQ-HW - Design, develop and qualify the Hardware solution | 87202126-00-DDQ-GRP-EN |  |
| - Management System Process CFG - Manage Configuration | 87202424-00-CFG-GRP-EN |  |
| - Management System Process Control Export | Part of 87201392-00-LEG-GRP-EN |  |
| - Management System Process Guarantee quality and manage continuous improvement | 87200214-00-QCI-GRP-EN chapter |  |
| - Information Classification Standard | 90000485-ESS-GRP-EN (CYB-STD-009) | 2.8 |
| - Project Life Cycle | 83530275-DDQ-AUT-EN | 005 |
| - Document Management Rules | 83530061-DOC-AUT-EN | 014 |
| - Milestone Template Solutions | 83530019-DDQ-AUT-EN | 013 |
| - Document List and Review Matrix for engineering projects | 83530224-DOC-AUT-EN | 012 |
| - Hitachi Glossary | 3BU 15000 8008 WDAPQ latest update: http://trss-at.at.gts/glossword |  |

Table 8: Standards and Procedures

## Terms, abbreviations and acronyms

For Terms and abbreviations see [S20]. Missing terms/abbreviations are added in the following tables.

### Terms, Abbreviations and Acronyms used in the project

| App | Applicable |
| --- | --- |
| BCWS | Budgeted Cost of Work Scheduled |
| CBB | Contract Budget Baseline |
| CCB | Configuration Control Board |
| CDR | Critical Design Review |
| DDQS | Design, Develop and Qualify the Solution |
| EL1 | ELEKTRA Generation 1 |
| EL2 | ELEKTRA Generation 2 |
| ESM | Electronic Storage Media |
| EV | Earned Value |
| FQR | Final Qualification Review |
| HW | Hardware |
| IVV | Integration, Verification and Validation |
| KOM | Kick of Meeting |
| M | Mandatory |
| N/A | Not applicable |
| O | Optional |
| PCM | Primavera Core Model |
| PCR | Problem Change Request |
| PDR | Preliminary Design Review |
| PEP | Personnel Efforts Planning |
| PMP | Project Management Plan |
| QMP | Quality Management Plan |
| RAMS | Reliability, Availability, Maintainability and Safety |
| SE | Solution Element |
| SEMP | System Engineering Management Plan |
| PSEMP | Project and System Engineering Management Plan |
| SFR | Solution Functional Review |
| SIL | Safety Integrity Level |
| SOR | Solution Orientation Review |
| SRR | Solution Requirement Review |
| SubIT | Subsystem Integration Test |
| SW | Software |
| TQR | Technical Qualification Review |
| TRR | Test Readiness Review |
| WBS | Work Breakdown Structure |
| WP | Work Package |
| WPD | Work Package Description |

### Role abbreviations

| ARC | Architect |
| --- | --- |
| CM | Configuration Manager |
| DM | Document Manager |
| DPM | Data Preparation Manager |
| HoD | Head of Discipline |
| IVQM | Integration, Verification and Qualification Manager |
| PDA | Project Design Authority |
| PLM | Product Line Manager |
| PM | Project Manager |
| QAM | Quality Assurance Manager |
| RAM-AM | Reliability, Availability, Maintainability Assurance Manager |
| SAM | Safety Assurance Manager |
| RM | Requirements Manager |
| TM | Test Manager |
| SEM | System Engineering Manager |
| SM | Senior Management |
| VAL | Validator |
| VER | Verifier |
| WPM | Work Package Manager |

Table 9 : Role abbreviations

# Solution engineering and development process

The Solution will be conducted according to GTS Management System (see also 2.2). As the GTS Management System is continuously improving, it has to be mentioned, that in the evolution of the Solution, for newly created documents within this project, the respective valid templates have to be used according to the up-to-date Management System. For maintenance and extension of existing documents the previously used template may remain.

## Organization of solution engineering

The description of the roles mentioned below can be found on the GTS Management System Portal.

### Solution core team

| Role | Resource | Deputy Resource |
| --- | --- | --- |
| PLM | M. Dum / OEP | K. Schnabl / OEP |
| PDA | G. Artner / OEDCD | T. Berger / OEDCD |
| SEM | B. Koenig / OEDRM | S. Vaziri / OEDRM |
| HoE | G. Schmidmayr / OE |  |
| HoOEDR | N. Krist / OEDR |  |
| IVVQM | M. Gvozdic / OEDRV | S. Bako / OEDRD |
| VER | H. Walenta / OEDRD |  |
| SAM | C. Buder / RS |  |
| RAM-AM | F. Moser / R | B. Pavlovic / R |
| QAM | C. Janneschitz / Q |  |
| VAL | B. Moayedifar / RV |  |
| PSM | T. Fischer / OEDCS | S. Cako / OEDCS |

Table 10: Core team

### Solution team

| Role | Resource | Deputy Resource |
| --- | --- | --- |
| ARC | R. Stemeseder / OEDRD | H. Mair / OEDRD |
| RM | M. Schneider / OEDCR | I. Miler / OEDCR G. Eber / OEDCR |
| CM | U. Larkin / OEDTC |  |
| DM | see *3) below table | n/a |
| DPM | L. Seifritz / OEDTD S. Futterknecht / OEDTC A. S. Preotescu / OEDTC | n/a |
| RAM-AM | F. Moser / R | B. Pavlovic / R |
| SecAM | J.M. Lauranson / OEDCS |  |
| WPM(s) | See Table 3 | SEM |
| PSM EBO2 | S. Peternel / OEDCS | S. Cako / OEDCS |
| SecAM EBO2 | T. Fischer / OEDCS |  |
| Software Engineer ELEKTRA | R. Stemeseder / OEDRD A. Markovic / OEDRD J. Szoeke / OEDRD H. Mair / OEDRD G. Zöhrer / OEDRD G. Schild / OEDRD L. Santner / OEDRD T. Fuchs / OEDRD A. Nemeth / TEJR | n/a |
| Tester ELEKTRA | M. Winter / OEDRV M. Böhm / OEDRV M. Neuwirth / OEDRV S. Varallyay / OEDRV I. Hegyi / OEDRD B. Sári / OEDRD R. Baranczó / OEDRD G. Reif / OEDRD V. Fehér / OEDRD D. Dévai / OEDRD N. Bondrea / RO *1 V. Voicu /RO *1 | n/a |
| Tester (SUBIT) | D. Preoteasa / RO | n/a |
| Software Engineer OREST | R. Ungerböck / OEDTC A. Alcsuti / OEDTC P. Gangli / OEDTC D. Orban / OEDTC S. Krasny / OEDT D. Molnar / OEDTC T. Neiger / OEDTC M. Pasztor / OEDTC L. Pocs / OEDTC J. Saunders / OEDTC S. Szili Kis / OEDTC N. Yaneva / OEDTC M. B. Nemeth / OEDTC G. Simon / OEDTC P. Margit / OEDTC E. Abd Almajeed Shebli Elshebli / OEDTC | n/a |

Instruction: All relevant team members additionally to the core team have to be documented in this table. The HSE Officer is specially needed for projects with onsite activities.

Table 11: Team

*1) Focuses on Security Testing

*2) Focuses on Security Engineering (incl. Network)

*3) The role DM is not executed by a single person. The major DM activities are spread to other roles:

- new ANV: can be obtained by SEM

- Document Index: is made by CM or SEM

- Formal check at release of a document: is made by QAM

- Other DM activities: are made by author of the document

### External project roles

| Role | Resource | Deputy Resource |
| --- | --- | --- |
| Safety Assessor | B. Pemmer / Arsenal RACE | n/a |
| Tools & Workbenches | W. Schütz / WP M. Edelbauer / OEDRD | n/a |

Table 12: External project roles

### Configuration Control Board (CCB)

| Role | Resource | Comment | M/O |
| --- | --- | --- | --- |
| PLM | see Table 10 | Budget, schedule, scope | M |
| PM | see Table 10 |  | M |
| PDA | see Table 10 |  | M |
| SEM | see Table 10 |  | M |
| WPM | see Table 11 |  | O |
| SAM | see Table 10 |  | M |
| IVVQM/IVQM/TM | see Table 10 |  | M |
| VAL | see Table 10 |  | M |
| QAM | see Table 10 |  | M |
| PSM | see Table 10 |  | O |
| RAM-AM | see Table 11 |  | O |
| Head of Operations Programm Manager AT | H. Wolfram / OPA | Budget, schedule, resources for priority conflicts regarding resources | O |
| Head of Engineering | G. Schmidmayr / OE | Budget, schedule, resources | M |
| Head of Deployment & Services | H. Eckstein / OD | schedule | M |
| Head of IxL Development | K. Ndue / OEDR |  | O |

Table 13: CCB

Other project team members are invited to the CCB as needed.

## System engineering supplies

Any reuse of a finished or purchased product will be stated in the Design Validation approval (DVa) [6].

## Input data

See Table 4.

## Preconditions / Related solutions

| Deliverable | Completion Date | Provider |
| --- | --- | --- |
| PV GEN 2.20.10 | Parallel to BL29.50 – Stable Version till TRR1 | PV GEN Project |
| EBO2 V. 2.0 | Till TRR1 | EBO2 WP |
| SEC 2.5 | Till TRR1 | SEC WP |
| OCS SBJ 3.6.0 | Till TRR1 | Tas Platform |

Table 14: Preconditions

## Technical objectives

The technical objective of this Solution is to upgrade the existing functionality of the product ELEKTRA Domestic and data preparation tool OREST and ELEPRO with developing change requests according to Scope of Change (SoC) [5].

## Detailed First Level WBS for Work Packages

See  CBS [10] Instruction: If the fixing of legacy PCRs is in scope of this project, then there should be an own sub WBS element for the concerned product in order to track these efforts.

## Special need for training of system engineering team

- Security Training for the project team.

- Special training for the security testing team.

 Instruction: Only list trainings if the team needs special know-how and therefore special training or if new team members are involved in the project.

## Constraints / Risks

Constraints which are not already considered in the Risk Report [2] are listed here.

## Work Contained

Engineering of the scope mentioned in section 1.2 according to the applying parts of the relevant standards listed in section 2.3.

Delivery of the baseline documentation, including the Safety Cases.

Delivery of the items listed in section 1.3.2.

## Work not contained

While the work contained is already stated in section 3.9, the following topics are explicitly mentioned as not part of this solution in order to sharpen the responsibility:

- Assessment Certification for the solution. Details have to be documented in Chapter 5.1.5 Validate the solution

Coordination and agreements with non- Hitachi Rail GTS Austria GmbH-internal customers.

Data preparation of non-testing railway stations.

Installation

Coordination and execution of Factory Acceptance Tests (Customer labor-/integration-tests).

Industrialisation of HW components.

Any HW, product or solution development not mentioned in section 1.1.2 or 1.1.3.

Any other kind of customer- / user-documentation as described in section 3.9. The following examples are all in responsibility of PDA of customer project):

  - Update of the user document “User Manual Interlocking Bulgaria"

  - Update of the user document “User Manual Interlocking Hungary

  - Update of the documents “Functional Requirement Specification" for Bulgaria and Hungary

Translation of documents from previous baselines into English.

Training of new and external (Romanian, Hungarian) employees.

## Responsibility Assignment Matrix

The responsibilities of the roles at a Milestone Review can be seen in Milestone Template Solutions [S18].

## Tools and Facilities

The following subsections provide a rough overview of the project tool setup. For version information and tool classification see document Software Development Tool Classification [8].

### Management and Documentation Tools

| Tool Category | Tool | Note |
| --- | --- | --- |
| Project Management | Primavera PCM |  |
| Task Management | iTask |  |
| Requirements Management | DOORS/RMF/POLARION |  |
| Management Traceability | DOORS/RMF/POLARION |  |
| Configuration Management | ClearCase Git |  |
| Change Management | CHARM JIRA |  |
| Documentation Management | ClearCase DWF Sharepoint |  |
| Documentation Generation | DOORS RMF Java Doc MS Office |  |
| Build environment ELEKTRA | ClearCase ClearMake |  |
| Build environment EBO2 | Git Maven |  |
| Build environment OREST | Git ANT and Maven Sonar Jenkins Bitbucket |  |
| Build environment SEC | Git and Subversion Maven Sonar Bitbucket Jenkins |  |
| IVV Management | DOORS, Excel (other Tools) Polarion |  |
| Security Management | OpenVAS OpenSCAR NMAP | Vulnerability Assessment Scanner Security Content Authentication Protocol |

Table 16: Management and Documentation Tools

### Code Building Tools

| Tool Category | Tool | Version | Note |
| --- | --- | --- | --- |
| Compiler | CHILL | 2.3.13 |  |
|  | GNU C/C++ | 7.3.0 |  |
|  | JAVA | 7.07 / 8.212 |  |
|  | PAMELA | 3.0.6 |  |
| IVV | GCOV | 4.9.3 |  |
|  | EPS | 05.29 |  |
|  | COTO | n.a. |  |
|  | Audit Tools | n.a. |  |

Table 17: Code Building Tools

# Process Control

## Control of Solution Development

The solution elements and assigned responsibilities are listed in Table 2.

### Deviation

The development of a Solution has to be planned and executed according to the DDQS Processes of GTS Management System No deviation to the description in Project Life Cycle [S16].

### Metrics

The used metrics for control of the engineering process are identified in the Engineering Dashboard [3].

The template for the engineering dashboard can be found on SharePoint Side Engineering Operation see following link: Engineering Dashboard - AT

## Monitoring and Control of System Engineering Activities

### Periodic Internal Reviews and Meetings

| Meeting | Responsible | Attendees | Frequency | Objectives |
| --- | --- | --- | --- | --- |
| periodically Core Team Meeting | SEM | Solution core team, ARC, WPM(s) Only on demand: CM and RM | weekly | Project status and action points. |
| Risk and opportunity review | SEM | SEM, PLM, PDA, IVVQM, RAMS-AM | Quarterly or on demand |  |
| Resource review | SEM | SEM, HoD Route Control Projects | monthly | Check utilisation and additional needs of solution team. |
| Cost tracking | Project controller | SEM, HoD Route Control Projects, Project Controller | monthly | Report of costs and progress to Financial Control Director. |
| Periodically Performance Project Review (PPPR) | SEM | SEM, HoD Route Control Projects, HoD Project Engineering, HoD Engineering | monthly | Report of costs and progress, KPI dashboard, required decisions from SM to HoD Project Engineering, HoD Engineering |

Table 18: Reviews and Meetings

### Milestone Reviews and Audits

Milestone reviews are done according Milestone Template Solutions [S18]. Audits will be conducted through the QAM – see Quality Management Plan (QMP) [4].

### Reporting

Reporting is done via the Engineering Dashboard [3].

## Critical Technologies

N/A

## Risk and Opportunities Control

The Risk and Opportunities Control in this Solution will follow the Management System Process Manage Risks and Opportunities [S8] and is monitored in the Risk Report [2].

## Corrective Action Process

Information about the Corrective Action Process can be found in the Quality Management Plan (QMP) [4].

## Independent Evaluation and Verification

Independent evaluation and verification will be done by

- the verifier and domain experts upon instruction of the verifier (VER);

- the validator (VAL);

- the safety manager (SAM).

## Estimate/Re-Estimate

The initial estimation is either an input for the phase “Orientation the Solution” or is done or verified during this phase. Re-estimation of remaining work is done during the progress of working packages typically on a monthly period. The method used for estimation is mainly “Expert estimations” based on past experience, educated assumptions and risk considerations.

## Planning

Planning is done in the tool PCM and can be found there with the identification listed in Table 1.

## Value Analysis and Design to Cost

Will be done in the Engineering Dashboard [3].

## Peer Reviews

The Peer Reviews in this Solution will follow the Document Management Rules [S17]. An overview of mandatory Documents and Reviewer has to be done according to Document List and Review Matrix for engineering projects  [S19].

# Development scenario and tailoring of the System Engineering Process

Instruction: The process has to be executed according to Project Life Cycle [S16]. Please adapt the figures according to your project scope.

The project will be conducted following the Management System processes Manage Project (PRJ) and Design, Develop and Qualify the Solution (DDQS) and their interfaces according to Project Life Cycle [S16].

Figure 2: Manage Project (PRJ)

This development process follows the initialisation by Manage Product Policy as described in Project Life Cycle [S16].

The Product Line Engineering (PLE) approach is applicable if there is a need to perform product evolution or product development without a concrete BID or if an enhancement, respectively change of a product is used for several customer contracts or markets. In this case PLE is a substitute for the process Manage Bid and guides the project over the whole project life cycle. The Product Line Manager (PLM) starts the PLE process with a Business Plan Decision Review (BP DR) and orders the product development with a Development Launch Decision Review (DL DR).

Figure 3: Product Line Engineering Process

Figure 4: Develop and Qualify the Solution (DDQS)

## Tailoring for this solution

### Orient the Solution

DVa does not apply for this project.

No deviation to the description in Project Life Cycle [S16].

### Design the Solution

No deviation to the description in Project Life Cycle [S16].

### Develop the Solution

No deviation to the description in Project Life Cycle [S16].

### Integrate and Verify the Solution

No deviation to the description in Project Life Cycle [S16].

### Validate the solution

No deviation to the description in Project Life Cycle [S16].

### Documentation Management

The naming convention for the name “Firstname Lastname” of the author, verified by, approver of a document can also be “F. Lastname”. Instruction: Define if external assessment of e.g. Release Candidate ELEKTRA INT is needed for the Solution till FQR. It has to be defined with PDAs of operative projects.

No deviation to the description in Project Life Cycle [S16].

# System Engineering Support

## Data and Configuration Management

Data and Configuration Management is carried out according to Management System Process CFG - Manage Configuration [S12], Document Management Rules [S17] and the specific Configuration Management plans Configuration Management Plan [9].

## Confidentiality

The rules as listed in Information Classification Standard [S15] apply.

## Export Control

Export Control is carried out according to Management System Process Control Export  [S13].

## Capitalization

Capitalization is handled in the context of the related Manage Product Policy process.

## Measurements and Analysis

See section 4.

## Technical and Non-technical Requirements Management and Control

For Requirement Management the tool DOORs/Polarion is used. The Requirements Manager ensures that requirements are

uniquely identified

unambiguous, testable and consistent

traced from origin through all systems

have all changes managed

The requirements manager manages changes throughout the life of the project. If requirements change, the impact will be reflected in the project plans, work products, and activities. Any inconsistencies between these customer- and/or system requirements and project plans, work products, and activities will be identified and resolved.

## Validation of Requirements

The validation is done in accordance with the Validation Qualification plans as listed in Documentation Plan [1].

## Decision Analysis and Resolution

Decision analysis and resolutions are part of design and review processes. The results are documented in design documents, review reports and in this document.

## Subordinate Plans

There are no subordinate plans. (or refer to the Documentation Plan [1]).

## Quality Assurance

The Quality Assurance in this Solution will follow Management System Process Guarantee quality and manage continuous improvement [S14]. Additional information can be found in the Quality Management plans as listed in Documentation Plan [1].

## Certification Support Activity

See Safety Management plans as listed in Documentation Plan [1].

## Stakeholder Management

Stakeholder management is defined in the corresponding PSEMP Project and System Engineering Management Plan [1]

- Criteria for the Selection of Techniques and Measures

The clauses of this document are associated within this annex to the clause tables (see A.2, Table A.1 to Table A.11) to illustrate the means of achieving conformance. There exist lower level tables as well, the detailed tables (see A.3, Table A.12 to Table A.21), which expand upon certain entries in the clause tables. The detailed tables only apply if the measure or technique was selected within the clause table (e.g., Table A.13 only applies if dynamic testing was selected when applying Table A.6, Table A.6 or Table A.7). There also exists an informative Annex D which is referred to from these tables.

Some techniques or measures appear in more than one table in this annex because they are applicable to more than one lifecycle phase. The recommendation for the usage of the techniques or measures may be different for different lifecycle phases.

With each technique or measure in the tables there is a requirement for each software integrity level. In this version of the document, the requirements for software integrity levels 1 and 2 are the same for each technique. Similarly, each technique has the same requirements at software integrity levels 3 and 4. These requirements can be:

- ‘M’
This symbol means that the use of a technique is mandatory.

- ‘HR’
This symbol means that the technique or measure is Highly Recommended for this safety integrity level. If this technique or measure is not used then the rationale for using alternative techniques shall be detailed in the Software Quality Assurance Plan or in another document referenced by the Software Quality Assurance Plan.

- ‘R’
This symbol means that the technique or measure is Recommended for this safety integrity level. This is a lower level of recommendation than an ‘HR’ and such techniques can be combined to form part of a package.

- ‘--’
This symbol means that the technique or measure has no recommendation for or against being used.

- ‘NR’
This symbol means that the technique or measure is positively Not Recommended for this safety integrity level. If this technique or measure is used then the rationale behind using it shall be detailed in the Software Quality Assurance Plan or in another document referenced by the Software Quality Assurance Plan.

The combination of techniques or measures are to be stated in the Software Quality Assurance Plan or in another document referenced by the Software Quality Assurance Plan with one or more techniques or measures being selected unless the notes attached to the table makes other recommendations. The combination shall conform to approved techniques and measures for all lifecycle phases. If such techniques or combinations of techniques, including all respective mandatory techniques, are used then the Assessor shall accept them as valid and shall only be concerned that the rationale for selecting the techniques and measures is sound and can be justified, then the Assessor may find this acceptable.

Table A.1 Lifecycle Issues and Documentation

| DOCUMENTATION | App | Basic Integrity | SIL 1 | SIL 2 | SIL 3 | SIL 4 | References of Doc Type |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Planning |  |  |  |  |  |  |  |
| 1. Software Quality Assurance Plan |  | HR | HR | HR | HR | HR |  |
| 2. Software Planning Verification Report |  | R | HR | HR | HR | HR |  |
| 3. Software Configuration Management Plan |  | HR | HR | HR | HR | HR |  |
| 4. Software Verification Plan |  | HR | HR | HR | HR | HR |  |
| 5. Software Validation Plan |  | HR | HR | HR | HR | HR |  |
| Software requirements |  |  |  |  |  |  |  |
| 6. Software Requirements Specification |  | HR | HR | HR | HR | HR |  |
| 7. Overall Software Test Specification |  | HR | HR | HR | HR | HR |  |
| 8. Software Requirements Verification Report |  | R | HR | HR | HR | HR |  |
| Architecture and design |  |  |  |  |  |  |  |
| 9. Software Architecture Specification |  | R | HR | HR | HR | HR |  |
| 10. Software Design Specification |  | R | HR | HR | HR | HR |  |
| 11. Software Interface Specifications |  | HR | HR | HR | HR | HR |  |
| 12. Software Integration Test Specification |  | R | HR | HR | HR | HR |  |
| 13. Software/Hardware Integration Test Specification |  | R | HR | HR | HR | HR |  |
| 14. Software Architecture and Design Verification Report |  | R | HR | HR | HR | HR |  |
| Component Design |  |  |  |  |  |  |  |
| 15. Software Component Design Specification |  | - | HR | HR | HR | HR |  |
| 16. Software Component Test Specification |  | - | HR | HR | HR | HR |  |
| 17. Software Component Design Verification Report |  | - | HR | HR | HR | HR |  |
| Component Implementation and Testing |  |  |  |  |  |  |  |
| 18. Software Source Code and supporting documentation |  | HR | HR | HR | HR | HR |  |
| 19. Software Component Test Report |  | - | HR | HR | HR | HR |  |
| 20. Software Source Code Verification Report |  | - | HR | HR | HR | HR |  |
| Integration |  |  |  |  |  |  |  |
| 21. Software Integration Test Report |  | R | HR | HR | HR | HR |  |
| 22. Software/Hardware Integration Test Report |  | R | HR | HR | HR | HR |  |
| 23. Software Integration Verification Report |  | R | HR | HR | HR | HR |  |
| Overall Software Testing / Final Validation |  |  |  |  |  |  |  |
| 24. Overall Software Test Report |  | HR | HR | HR | HR | HR |  |
| 25. Software Validation Report |  | HR | HR | HR | HR | HR |  |
| 26. Tools Validation Report |  | - | HR | HR | HR | HR |  |
| 27. Release Note |  | HR | HR | HR | HR | HR |  |
| Systems configured by application data |  |  |  |  |  |  |  |
| 28. Application Requirements Specification |  | HR | HR | HR | HR | HR |  |
| 29. Application Preparation Plan |  | R | HR | HR | HR | HR |  |
| 30. Application Test Specification |  | HR | HR | HR | HR | HR |  |
| 31. Application Architecture and Design |  | R | HR | HR | HR | HR |  |
| 32. Application Preparation Verification Report |  | - | HR | HR | HR | HR |  |
| 33. Application Test Report |  | HR | HR | HR | HR | HR |  |
| 34. Source Code of Application Data |  | HR | HR | HR | HR | HR |  |
| 35. Application Data Verification Report |  | R | HR | HR | HR | HR |  |
| 36. Application Integration Test Specification |  | HR | HR | HR | HR | HR |  |
| 37. Application Integration Test Report |  | HR | HR | HR | HR | HR |  |
| 38. Application Release Note |  | HR | HR | HR | HR | HR |  |
| Software deployment |  |  |  |  |  |  |  |
| 39. Software Deployment Manual |  | R | HR | HR | HR | HR |  |
| 40. Deployment Records |  | R | HR | HR | HR | HR |  |
| 41. Deployment Verification Report |  | R | HR | HR | HR | HR |  |
| Software maintenance |  |  |  |  |  |  |  |
| 42. Software Maintenance Plan |  | R | HR | HR | HR | HR |  |
| 43. Software Change Records |  | HR | HR | HR | HR | HR |  |
| 44. Software Maintenance Records |  | R | HR | HR | HR | HR |  |
| 45. Software Maintenance Verification Report |  | R | HR | HR | HR | HR |  |
| Software assessment |  |  |  |  |  |  |  |
| 46. Software Assessment Plan |  | - | HR | HR | HR | HR |  |
| 47. Software Assessment Report |  | - | HR | HR | HR | HR |  |
| For basic integrity, the content of the software verification plan can be limited to 6.2.4.9 a), b), c), d), f). For basic integrity the software Interface specification is only highly recommended for the boundary of the overall software (see also 7.3.4.18). |  |  |  |  |  |  |  |

Table A.2 Software Requirements Specification (7.2)

| - TECHNIQUE/MEASURE | App | Basic Integrity | SIL 1 | SIL 2 | SIL 3 | SIL 4 |
| --- | --- | --- | --- | --- | --- | --- |
| 1. Modelling |  | R | R | R | HR | HR |
| 2. Structured methodology |  | R | R | R | HR | HR |
| 3. Decision Tables |  | R | R | R | HR | HR |
| Requirements: 1) The Software Requirements Specification shall include a description of the problem in natural language and any necessary formal or semiformal notation. 2) The table reflects additional requirements for defining the specification clearly and precisely. One or more of these techniques shall be selected to satisfy the Software Integrity Level being used. |  |  |  |  |  |  |

Table A.10 – Software maintenance (9.2)

| - TECHNIQUE/MEASURE | App | Basic integrity | SIL 1 | SIL 2 | SIL 3 | SIL 4 |
| --- | --- | --- | --- | --- | --- | --- |
| 1. Impact Analysis |  | R | HR | HR | M | M |
| 2. Data Recording and Analysis |  | HR | HR | HR | M | M |

END OF DOCUMENT