PSEMP PV CH 2.42.0 / BL CH22.20

ELEKTRA

| APPROVAL |  |  |
| --- | --- | --- |
|  | Name and Role/Job Title | Esignature |
| Written by | L. Munoz / SEM |  |
| Verified by | C. Janneschitz / QAM |  |
| Approved by | G. Schmidmayr / HoD |  |

| LOG OF CHANGES |  |  |  |
| --- | --- | --- | --- |
| Revision | Date | Author | Change Description |
| 01 | 26.09.2024 | L. Munoz | Erstausgabe |
| 02 PD 01 | 11.04.2025 | L. Munoz | Update nach Scope of Change Ed02 and CMR Ed 01 |
| 02 RR | 16.05.2025 | L. Munoz | Ready for Release |

Contents

1.	SCOPE	7

1.1	Identification	7

1.1.1	General	7

1.1.2	WBS managed as Solution	8

1.1.3	WBS managed as Work Packages	8

1.1.4	Other component versions this engineering solution is based on	10

1.2	System overview	10

1.3	Key points	12

1.3.1	Milestones for Solution	12

1.3.2	Deliverables	14

1.4	Relation with other plans	14

1.5	Document version history	14

1.5.1	Edition 01	14

1.5.2	Edition 02	14

2.	References and terms	15

2.1	Referenced documents	15

2.2	Process basis	16

2.3	Standards and procedures	16

2.4	Terms, abbreviations and acronyms	18

2.4.1	Role abbreviations	18

2.4.2	Terms, abbreviations and acronyms	19

2.4.3	Abbreviations used in the project:	22

3.	Solution engineering and development process	23

3.1	Organization of solution engineering	23

3.1.1	Customer Organization	25

3.1.2	Solution core team	25

3.1.3	Solution team	26

3.1.4	External project roles	28

3.1.5	Configuration Control Board (CCB)	29

3.2	External stakeholder management	30

3.2.1	Communication networks and rules	31

3.3	System engineering supplies	32

3.4	Input data	32

3.5	Preconditions / Related solutions	32

3.6	Technical objectives	33

3.7	Detailed First Level WBS for Work Packages	33

3.8	Special need for training of system engineering team	34

3.9	Constraints / Risks	34

3.10	Work contained	34

3.11	Work not contained	35

3.12	Responsibility Assignment Matrix	35

3.13	Tools and Facilities	35

3.13.1	Management and Documentation Tools	35

3.13.2	Code Building Tools	37

4.	Project Context	38

4.1	Commercial Context	38

4.2	Contractual Context	38

4.3	Key Issues	38

4.4	Critical Success Factors	38

5.	Process Control	39

5.1	Control of Solution Development	39

5.1.1	Deviation	39

5.1.2	Metrics	39

5.2	Monitoring and Control of System Engineering Activities	42

5.2.1	Periodic Internal Reviews and Meetings	42

5.2.2	Milestone Reviews and Audits	43

5.2.3	Reporting	43

5.3	Critical Technologies	43

5.4	Risk and Opportunities Control	43

5.5	Corrective Action Process	43

5.6	Independent Evaluation and Verification	43

5.7	Estimate/Re-Estimate	43

5.8	Planning	43

5.9	Value Analysis and Design to Cost	43

5.10	Peer Reviews	44

6.	Development scenario and tailoring of the System Engineering Process	45

6.1	Tailoring for this solution	45

6.1.1	Orient the Solution	45

6.1.2	Design the Solution	45

6.1.3	Develop the Solution	45

6.1.4	Integrate and Verify the Solution	45

6.1.5	Validate the solution	45

6.1.6	Documentation Management	45

7.	System Engineering Support	47

7.1	Data and Configuration Management	47

7.2	Confidentiality	47

7.3	Export Control	47

7.4	Capitalization	47

7.5	Measurements and Analysis	47

7.6	Technical and Non-technical Requirements Management and Control	47

7.7	Validation of Requirements	48

7.8	Decision Analysis and Resolution	48

7.9	Subordinate Plans	48

7.10	Quality Assurance	48

7.11	Certification Support Activity	48

END OF DOCUMENT	48

List of Tables

Table 1: Solution Identification for BL CH22.20	8

Table 2: Change request over CR-Pauschale	9

Table 3: WBS managed as Solution	9

Table 4: WBS managed as Work Packages	9

Table 5: WBS managed as Work Packages covered by Maintenance	9

Table 6: Other component versions	9

Table 7: Key milestones	9

Table 8: Deliverables	9

Table 9 : Referenced Documents	9

Table 10 : Standards and Procedures	9

Table 11 : Role abbreviations	9

Table 12 : Terms, Abbreviation and Acronyms	9

Table 13 : Abbreviations used in the project	9

Table 14: Core team	9

Table 15: Team	9

Table 16: External project roles	9

Table 17: CCB	9

Table 18 : Stakeholder Requirements and Impacts	9

Table 19: Communication with Customer	9

Table 20: Preconditions	9

Table 21: Detailed WBS	9

Table 22: Management and Documentation Tools	9

Table 23: Code Building Tools	9

Table 24: Metrics	9

Table 25: Reviews and Meetings	9

Table of Figures

Figure 1: Product Breakdown Structure	9

Figure 2: OBS - BL CH22.20	9

Figure 3: Manage Project (PRJ)	9

Figure 4: Develop and Qualify the Solution (DDQS)	9

# SCOPE

The combined PSEMP, Project Management Plan (PMP) and System Engineering Management Plan (SEMP) describes the organisation, work packages, milestones and application of the Management System Release 2025-03.

## Identification

### General

| Project-ID: | 100025934 |
| --- | --- |
| Project category | A0 |
| Solution: | ATRENIB04 EL-CH BL 22.20 |
| Identification: | ELEKTRA Product Version PV CH 2.42.0 / BL CH22.20 |
| Contract: | - Offer-ID: CH/2024072/04 (PO 7009037 am 27.08.2024) - ELCH:FL:FEA:0181: - ELCH:FL:FEA:0182: - PCR PELSBB-5160 - PCR PESLBB-5159 - Offer-ID: CH/20250120/01 (wurde über CR-Pauschale 2025 gegengerechnet) - ELCH:FL:FEA:0183 - Offer-ID: CH/20241203/01 - PCR PELSBB-5158 - Offer-ID: CH/20241311/03 - ELCH:FL:FEA:0184 - Offer-ID: CH/20241015/01 (PO 7009183 am 12.12.2024) - PCR PELSBB-5156 - ELCH:FL:FEA:0183 (wurde nachträglich separat im Offer-ID: CH/20250120/01 angeboten) - ELCH:FL:FEA:0180 - ELCH:FL:FEA:0185 |
| Customer: | Hitachi Rail GTS Schweiz AG |
| End User: | SBB, BLS, SOB |
| SIL: | SIL4 |

Table 1: Solution Identification for BL CH22.20

| Project-ID: | ATRENIA01 |
| --- | --- |
| Project category | A0 |
| Solution: | ATRENIA01-E1 |
| Identification: | Change Request (CR) Pauschale |
| Contract: | n.a |
| Customer: | Hitachi Rail GTS Schweiz AG |
| End User: | SBB |

Table 2: Change request over CR-Pauschale

### WBS managed as Solution

| In Scope | WBS | Identification | SEM | SIL | Initial Product Version | Target Version | Target date |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | ATRENIB04-E0 | ELEKTRA Schweiz | L. Munoz | SIL4 | PV CH 2.41.0; BL CH 22.10 | PV CH 2.42.0; BL CH 22.20 | see FQR section 1.3.1 |

Table 3: WBS managed as Solution

The initial and target version of this solution and their work packages for this engineering project are listed in 1.1.3. The scope of these engineering projects is defined in the following documents:

- Scope of Change (SoC) BL CH22.20 [7]

### WBS managed as Work Packages

A detailed view on all WBS elements is listed in section 3.7.

|  | Solution Element: | ATRENIB04-E0 |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| In Scope | WBS | Ident. | WPM | Initial Version | Target Version | Target date |
|  | ATRENIB04-E0.WP3.DEV.3.1 | ELEKTRA Product Development Management | L. Munoz | BL CH 22.10 | BL CH 22.20 | Milestone TQR2 |
|  | ATRENIB04-E0.WP3.DEV.3.2.1 | ELEKTRA Development | G. Zöhrer | BL CH 22.10 | BL CH 22.20 | Milestone TRR1 |
|  | ATRENIB04- E0.WP3.DEV.3.2.1 | OREST | J. Cutig | 8.45 | 8.47 | Milestone TRR1 |
|  | ATRENIB04- E0.WP3.DEV.3.2.2 | ELEKTRA IVV | L. Munoz (interim) | BL CH 22.10 | BL CH 22.20 | Milestone TQR1 |
|  | ATRENIB04- E0.WP3.DEV.3.2.2 | Tools & Simulation | M. Edelbauer | - | - | Milestone TRR1 |

Table 4: WBS managed as Work Packages

|  | Solution Element: | ATRENIA01-E1 |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| In Scope | WBS | Ident. | WPM | Initial Version | Target Version | Target date |
|  | ATRENIA01-E1.SV1.VA | ELEKTRA Schweiz | L. Munoz | BL CH 22.10 | BL CH 22.20 | Milestone TQR2 |

Table 5: WBS managed as Work Packages covered by Maintenance

### Other component versions this engineering solution is based on

| Component | Version |
| --- | --- |
| Generic Productversion | PV GEN 2.19.10 |
| Webride2 | WR 2.1 |
| AZA, AzLM | AZA 7.6.13, 7.0, 6.1.11, 7.9 |
| RBC | 3.7 |
| TAS Platform | 2.4.2 |
| HW Interfaces | Included |
| Computing Hardware | MEN-D6/10 |

Table 6: Other component versions

## System overview

This solution provides a safe and highly reliable solution to control the railway operation. The objective of this solution is to upgrade the existing functionality of product ELEKTRA SBB and data preparation tool OREST with the scope as defined as follows:

- Scope of Change (SoC) [7] contains features, change requests and defect corrections which are planned to be released.

The initial and target versions of this solution and their work packages for this engineering project are listed in Table 3 to Table 5.

Level 1

Level 2

Level 3

Figure 1: Product Breakdown Structure

## Key points

### Milestones for Solution

| Milestone | Target Date | Type | Comment |
| --- | --- | --- | --- |
| Kick Off Meeting (KOM) | 01.10.2024 | Payment | Approved |
| Solution Orientation Review (SOR) | 01.10.2024 | Payment | Approved |
| Launch Review (LR) | 01.10.2024 | Internal | Approved |
| Solution Requirement Review (SRR) | 04.11.2024 | Payment | Approved |
| Solution Functional Review (SFR) | 04.11.2024 | Payment | Approved |
| Preliminary Design Review (PDR) | 12.02.2025 | Payment | Approved |
| Critical Design Review (CDR) | 12.02.2025 | Payment | Approved |
| Test Readiness Review (TRR1) | 19.05.2025 | Payment |  |
| Technical Qualification Review (TQR1) | 01.10.2025 | Payment | *all tests completed, ready for verification and validation |
| Test Readiness Review (TRR2) | 15.10.2025 | Internal | *verification completed |
| Technical Qualification Review 2 (TQR2) | 01.12.2025 | Payment | *validation completed, safety cases reviewed |
| Final Qualification Review (FQR) | 20.02.2026 | Payment | *Assessment from "Arsenal Race" available |
| Acceptance Review (AR) | 01.06.2026 | Payment | *Approval from "BAV" available |
| Closure Review (CR) | 01.06.2026 | Internal |  |

Table 7: Key milestones

### Deliverables

For Solution Element final date see Table 7. Additionally, deliverables in scope of this engineering project are listed below:

| Deliverable | Target Date | Comment |
| --- | --- | --- |
| Laboratory version for Hitachi Rail GTS Schweiz AG | 08/2025 | verification already started, but not finished |
| Data preparation tool OREST Version 8.47 | TQR2 |  |

Table 8: Deliverables

## Relation with other plans

See Documentation Plan/PVR [2].

## Document version history

### Edition 01

Initial edition.

### Edition 02

PSEMP Update after SoC update due to addon scope and PV GEN 2.19.10. See also CMR  3BU_15000_3640_BCAPA Ed 01

# References and terms

## Referenced documents

If not explicitly stated, the relevant version of a document is referenced in the Documentation Plan/PVR [2].

| Nr./Title | Reference | Version |
| --- | --- | --- |
| - Feature List Elektra Schweiz | 3BU 15000 4331 FLAPC | 37 |
| - Documentation Plan/PVR | Sharepoint project site, chapter 1.3.7 3BU 15000 3636 ADAPA (release planned with FQR) | Latest |
| - Risk Report | Sharepoint project site, chapter 1.3.5 | Latest |
| - Engineering Dashboard | Sharepoint project site, chapter 2.1 | Latest |
| - Quality Management Plan (QMP) | 3BU 15000 5244 QMAPA | 07 |
| - Safety Plan, ELEKTRA 2.x | 3BU 15000 0602 DUAPA | 06 |
| - Scope of Change (SoC) | 3BU 15000 3636 QEAPC | 02 |
| - Design Validation approval (Dva) | n/a; see tailoring chapter 6.1.1 |  |
| - Tool Classification EN50128 | 3BU 15000 5135 AAAPA | 27 |
| - Configuration Management Plan, ELEKTRA | 3BU 15000 3338 QMAPA | 11 |
| - List of SW-Baseline Label ELEKTRA Schweiz | 3BU 15000 3333 QEAPC | 34 |

Table 9 : Referenced Documents

## Process basis

The project is set up with the Management System Release 2025-03 as process basis. Changes in this process basis (e.g. adaptation to a new service release of Management System) have to be analysed, especially regarding the impact on already existing work products, documented and approved.

## Standards and procedures

| Nr./Title | Publishing Date/ Reference | Version/ Revision |
| --- | --- | --- |
| - IRIS Certification rules:2020 based on ISO/TS 22163:2017 | 2017, 2020 |  |
| - EN 50121-4:2016 Railway applications Electromagnetic compatibility Part 4: Emission and immunity of the signalling and telecommunications apparatus | 2016 |  |
| - EN 50126:2017 Railway applications. The specification and demonstration of reliability, availability, maintainability and safety (RAMS) Part 1: Generic RAMS Process Part 2: Systems Approach to Safety | 2017 |  |
| - EN 50128:2011 +A1:2020 +A2:2020 Railway applications Software for Railway Control and Protection Systems | 2011, 2020 |  |
| - EN 50129:2018 +AC:2019 Railway applications Safety related electronic systems for signalling | 2018 |  |
| - ISO 9001:2015 | 2015 |  |
| - Management System Process Manage Risks and Opportunities | Chapter 8.6 87200984-00-PRJ-GRP-EN (0001-0050019330) | 2025-03 |
| - Management System Process DDQ-SW – Design develop and qualify the Software solution | 87202125-00-DDQ-GRP-EN (0001-0050019355) | 2025-03 |
| - Management System Process CFG – Manage Configuration | 87202424-00-CFG-GRP-EN (0001-0050019454) | 2025-03 |
| - Management System Process Control Export | Chapter 1 87201392-00-LEG-GRP-EN (0001-0050019456) | 2025-03 |
| - Management System Process Guarantee quality and manage continuous improvement | Chapter 1.3 / 3 87200214-00-QCI-GRP-EN (0001-0050019226) | 2025-03 |
| - Protection of Group Information | 87201725-GOV-GRP-EN | 2025-03 |
| - Project Life Cycle | 83530275-DDQ-AUT-EN | 2025-03 |
| - Document Management Rules | 83530061-DOC-AUT-EN | 2025-03 |
| - Milestone Template Solutions | 83530019-DDQ-AUT-EN | 2025-03 |
| - Document List and Review Matrix for engineering projects | 83530224-DOC-AUT-EN | 2025-03 |

Table 10 : Standards and Procedures

## Terms, abbreviations and acronyms

### Role abbreviations

| ARC | Architect |
| --- | --- |
| CM | Configuration Manager |
| DM | Document Manager |
| DPM | Data Preparation Manager |
| HoD | Head of Discipline |
| IVVQM | Integration, Verification, Validation and Qualification Manager |
| PDA | Project Design Authority |
| PLM | Product Line Manager |
| PM | Project Manager |
| QAM | Quality Assurance Manager |
| RAM-AM | RAM Assurance Manager |
| RM | Requirements Manager |
| SAM | Safety Assurance Manager |
| SEM | System Engineering Manager |
| SM | Senior Management |
| TM | Test Manager |
| VAL | Validator |
| VER | Verifier |
| WPM | Work Package Manager |

Table 11 : Role abbreviations

### Terms, abbreviations and acronyms

| BCWS | Budgeted Cost of Work Scheduled |
| --- | --- |
| CBB | Contract Budget Baseline |
| CCB | Configuration Control Board |
| CDR | Critical Design Review |
| CHARM | CHAnge and Request Management |
| DDQS | Design, Develop and Qualify the Solution |
| EDM | ELEKTRA Delivery Model |
| EL1 | ELEKTRA Generation 1 |
| EL2 | ELEKTRA Generation 2 |
| ESM | Electronic Storage Media |
| EV | Earned Value |
| FQR | Final Qualification Review |
| GTS | Ground Transportation Systems |
| HW | Hardware |
| IVV | Integration, Verification and Validation |
| KOM | Kick-off Meeting |
| M | Mandatory |
| N/A | Not applicable |
| O | Optional |
| PCM | Primavera Core Model |
| PCR | Problem Report or Change Request |
| PDR | Preliminary Design Review |
| PMP | Project Management Plan |
| PV | Product Version |
| QMP | Quality Management Plan |
| RAM | Reliability, Availability and Maintainability |
| RAMS | Reliability, Availability, Maintainability and Safety |
| SDD | Software Design Description |
| SE | Solution Element |
| SEMP | System/Solution Engineering Management Plan |
| SFR | Solution Functional Review |
| SIL | Safety Integrity Level |
| SOR | Solution Orientation Review |
| SRR | Solution Requirement Review |
| SSS | System Segment Specification |
| SubIT | Subsystem Integration Test |
| SW | Software |
| TCS | Test Case Specification |
| TQR | Technical Qualification Review |
| TRL | Technology Readiness Level |
| TRR | Test Readiness Review |
| WBS | Work Breakdown Structure |
| WP | Work Package |
| WPD | Work Package Description |
| WUI | Wartung und Instandsetzung (German) |

Table 12 : Terms, Abbreviation and Acronyms

### Abbreviations used in the project:

| CCA | Central Control Channel A |
| --- | --- |
| CCB | Central Control Channel B |
| FZF | Folgezugfahrstrasse |
| GZF | Gegenzugfahrstrasse |
| NAZ | Notauflösung Zugfahrstrasse |
| OREST | Data Preparation Tool |
| RCA | Remote Control Channel A |
| RCB | Remote Control Channel B |
| Rf | Rangierfahrstrasse |
| Stw | Stellwerk |
| Subit | Subsystem Integrationstest |
| Zf | Zugfahrstrasse |

Table 13 : Abbreviations used in the project

# Solution engineering and development process

The Solution will be conducted according to Management System Release 2025-03 (see also chapter 2.2). As the Management System is continuously improving, it has to be mentioned, that in the devolution of the Solution, for newly created documents within this project, the respective valid templates have to be used according to the up-to-date Management System version. For maintenance and extension of existing documents the previously used template may remain.

## Organization of solution engineering

The description of the roles mentioned below can be found on the Management System.

The project OBS (Organizational Breakdown Structure) is shown in the diagram below. Please note that this does not reflect reporting to line management but only grouping of people for project-specific functions.

Jürg WULLSCHLEGER / Hitachi - CH (PLM) - Operative Project

Leyton MUNOZ (PM/SEM)

Gerald ARTNER (PDA)

Walter FUSS (PLM)

Christian JANNESCHITZ (QAM)

Klaus RADDA (SAM)

Natalia KARMATSKA (RM)

Jeremy CUTIG (CM)

Mohamed ALARSAN (Proj Office)

Wolfgang LUEF (VAL)

External

Gerhard ZÖHRER (ARC)

Leyton Munoz (interim) (IVVQM/WPM)

Jeremy 
CUTIG (OREST/WPM)

Robert KISS
(DPM)

Horst WALENTA (VER)

Raul HOSSA RAMBO (CM SEC)

Robert MITTERMAYR (SEC/WPM)

Figure 2: OBS - BL CH22.20

### Customer Organization

| Role | Resource | Deputy Resource |
| --- | --- | --- |
| Product Management (Hitachi Rail GTS Schweiz AG) | Juerg WULLSCHLEGER | Patric GSCHWEND |
| Head of System Design (Hitachi Rail GTS Schweiz AG) | Patric GSCHWEND |  |

### Solution core team

| Role | Resource | Deputy Resource |
| --- | --- | --- |
| PLM | W. Fuß | K. Schnabl M. Dum |
| PDA | G. Artner | n.a. |
| SEM | L. Munoz | M. Gollinger |
| IVVQM ELEKTRA | L. Munoz (interim) | A. Olgun |
| VER | H. Walenta | G. Eber |
| SAM | K. Radda | R. Büger |
| QAM | C. Janneschitz | D. Mahmudi |
| VAL | W. Luef | K. Fuchs |
| RM | N. Karmatska | G. Eber I. Miler |

Table 14: Core team

### Solution team

| Role | Resource | Deputy Resource |
| --- | --- | --- |
| ARC | G. Zoehrer | G. Artner |
| CM | J. Cutig | U. Larkin |
| DM | *) see below | n/a |
| DPM | R. Kiss | E. Müller |
| RAM-AM | F. Moser | B. Pavlovic |
| WPM(s) | J. Cutig A. Olgun R. Mittermayr | SEM |
| HSE Officer | n/a | n/a |
| Software Engineer ELEKTRA and SEC | G. Zoehrer F. Krammer G. Schild L. Santner T. Fuchs R. Mittermayr W. Arthold A. Kretscher | n/a |
| Tester | M. Böhm L. Seifritz A. Olgun D.-M. Preoteasa (RO) | n/a |
| Tester (SUBIT) | D. Preoteasa | n/a |
| Solution Team OREST | S. Krasny J. Cutig M. Pasztor D. Molnar L. Pocs E. Abd Almajeed Shebli Elshebli T. Neiger J. Saunders S. Szili Kis R. Ungerböck N. Yaneva M. B. Nemeth G. Simon | n/a |

Table 15: Team

*) The role DM is not executed by a single person. The major DM activities are spread to other roles:

- new document number can be obtained from the SEM

- Document Index is made by CM or SEM

- Formal check at release of a document is made by QAM

- Other DM activities are made by the author of the document

### External project roles

| Role | Resource | Deputy Resource |
| --- | --- | --- |
| Safety Assessor | D. von ARX (SBB) B. Pemmer (Arsenal RACE) | n.a. |

Table 16: External project roles

### Configuration Control Board (CCB)

| Role | Resource | Comment | Mandatory/Optional |
| --- | --- | --- | --- |
| PLM | see Table 14 | budget, schedule, scope | M |
| SEM | see Table 14 |  | M |
| PDA | see Table 14 |  | M |
| SAM | see Table 14 |  | M |
| RAM-AM | see Table 14 |  | M |
| IVVM | see Table 14 |  | M |
| VAL | see Table 14 |  | M |
| QAM | see Table 14 |  | M |
| Head of Route Control Projects | K. Ndue | budget, schedule, resources | M |
| Head of CAE Data Toolset | S. Krasny | configuration management, requirement management | O |
| Head of Project Engineering | G. Schmidmayr | for priority conflicts regarding resources especially from other departments | O |
| Head of Architecture, Technology and Innovation | H. Kantz | in case of resource conflicts | O |

Table 17: CCB

Other project team members are invited to the CCB as needed.

## External stakeholder management

The following table below show the organizations comprising the external stakeholders. [Table 18] shows the stakeholder’s expectations and how they are impacted by the project.

| Stakeholder | Requirements they expect from the project | Impacted by the project |
| --- | --- | --- |
| Hitachi Rail GTS Schweiz AG | - High quality deliverable(s). - Software that corresponds to customer requirements. This means they expect consultation in case of use-case and requirement issues. - Software with good value for money. - Delivery according to schedule. | Financial – Should make a reasonable profit from the project. Should however ensure that the railway operator in Switzerland is satisfied with the value they get. Strategic – Should keep the customer happy. Having the railway operator in Switzerland as customer has prestige value and helps win contracts in other markets. |
| railway operator in Switzerland | - High quality deliverable(s) – very high safety & availability, high performance. - Should correspond to their requirements. - Competitive. | Reputation – Should be seen to provide good rail service (both by rail users and Swiss transport ministry). High quality project deliverables help this. Financial – Should provide value for money to their rail users and transport ministry. Strategic – standardized interlocking interface between different suppliers and standardized interface to external elements should result in less maintenance effort and the customer is more flexible within different suppliers. |

Table 18 : Stakeholder Requirements and Impacts

### Communication networks and rules

| Communication with Customer |  |  |  |  |
| --- | --- | --- | --- | --- |
| Meeting | Responsible | Attendees | Frequency | Objectives |
| CRPR | Head of Project Engineering | PM, PDA, if concerned: PLM, Safety, HW Engineering | Bi-monthly | Present status of this baseline. |
| Offline ADD-Review, only concerning data preparation | ARC | Additional to internal mandatory review participants from Hitachi Rail GTS Schweiz: Armin KOHLER Patrick SONDEREGGER Juerg WULLSCHLEGER | Ad-hoc | Inform about planned design concerning data preparation issues. |
| Assessment – External Authority Review |  |  |  | Assessment of the project will be done by Arsenal Race |
| Offlinereview SRS | PDA | Juerg WULLSCHLEGER (Hitachi Rail GTS Schweiz) | Ad-hoc |  |
| P/CR discussion | PDA | Attendees from Hitachi Rail GTS Schweiz: Juerg WULLSCHLEGER Patric GSCHWEND Peter GOERBERT | Monthly, or on demand | Regular discussion of issues from ongoing BL development after TQR1 |

Table 19: Communication with Customer

## System engineering supplies

Not applicable.

## Input data

See Table 6: Other component versions.

## Preconditions / Related solutions

| Deliverable | Completion Date | Provider |
| --- | --- | --- |
| n.a. |  |  |

Table 20: Preconditions

## Technical objectives

See Scope of Change Scope of Change (SoC) [7].

## Detailed First Level WBS for Work Packages

Only the first level of the WBS is listed here.

| WBS element ID | WBS element name | WBS el. manager | Comments |
| --- | --- | --- | --- |
| ATRENIB04- E0.WP3.KMS | Key Milestones | SEM | Management System DDQS. |
| ATRENIB04- E0.WP3.DEV.3.1 | Systems Development Management | SEM | Contains Level of effort tasks (accompany the project) like efforts for meetings, QAM, RM, IVVQM, CM, VAL, SEM, VER, SAM, RAM-AM, DataPrep, Expert support. |
| ATRENIB04- E0.WP3.DEV.3.2 | Baseline Engineering Activities BL CH 22.20 | SEM | Contains the tasks for Design, Development, OREST, Tooling and Simulation, Integration and Verification (e.g. regression tests) for the whole BL CH 22.20. |
| ATRENIB04- E0.WP3.DEV.3.3 | Überlagerte GFM (PELSBB-5160) | SEM | Feature specific activities. See PCM planning. |
| ATRENIB04- E0.WP3.DEV.3.4 | Weitere Bits an OPTI (AF) (ELCH:FL:FEA:0182, ELCH:FL:FEA:0184) | SEM | Feature specific activities. See PCM planning. |
| ATRENIB04- E0.WP3.DEV.3.5 | Anstoss von Sig. durch OPTI (ELCH:FL:FEA:0181) | SEM | Feature specific activities. See PCM planning. |
| ATRENIB04- E0.WP3.DEV.3.6 | Adressierung AzLM (PELSBB-5159) | SEM | Feature specific activities. See PCM planning. |
| ATRENIB04- E0.WP3.DEV.3.7 | Erweiterung Schnittstelle ELEKTRA-OPTI um Zugnummern-meldungen (ELCH:FL:FEA:0185) | SEM | Feature specific activities. See PCM planning. |
| ATRENIB04- E0.WP3.DEV.3.8 | Erhöhung der Anzahl der Barrierenübergänge auf max. 40 (PELSBB-5156) | SEM | Feature specific activities. See PCM planning. |
| ATRENIB04- E0.WP3.DEV.3.9 | ausgelagerter EC über TCD-Verbindung (ELCH:FL:FEA:0180) | SEM | Feature specific activities. See PCM planning. |
| ATRENIB04- E0.WP3.GC | CCB Test in Romania | SEM | Cost Collector for CCB Subit Test |

Table 21: Detailed WBS

## Special need for training of system engineering team

In case of new team members or assignments of current team members to new roles, the qualification and mandatory trainings plan will be elaborated with the Head of Discipline. This especially applies for

- ELEKTRA Developer	
responsible trainer on the job: G. Zoehrer

- ELEKTRA Tester/Testmanager	
responsible trainer on the job: A. Olgun, M. Böhm

- ELEKTRA System Engineering Management	
responsible trainer on the job: M. Gollinger, G. Artner, K. Ndue

- Team Members	
new Cenelec EN 50129/50126, Safety principles of ELEKTRA:  responsible trainer: C. Suender

## Constraints / Risks

Constraints which are not already considered in the Risk Report [3] are listed here.

- Preconditions to other projects and solutions (see 3.5)

## Work contained

- Engineering of the scope mentioned in chapter 1.2 according to the applying parts of the relevant standards listed in chapter 2.3.

- Integration, verification, validation and safety certification of the entire solution.

- Audit information about all changes in the baseline (Baseline Audit), a list of all discovered P/CR's during the project and their status, and documentation of all activity including verification for the baseline. This is handed over to Hitachi Rail GTS Schweiz AG.

- Guidelines / instructions for data preparation (Projektierungshinweise) and maintenance documents (WUI) for handover to Hitachi Rail GTS Schweiz AG.

- Technical and Operational Assessment by external assessors (Arsenal Race and SBB)

- Delivery of the baseline documentation, including the Safety Cases.

- Delivery of the items listed in chapter 1.3.2.

- Fixes for selected field defects according to the Scope of Change (see [7])

- Enabling Systems (see List of SW-Baseline Label ELEKTRA Schweiz [11] which will be updated regularly with each new Labor Baseline)

## Work not contained

While the work contained is already stated in chapter 3.10, the following topics are explicitly mentioned as not part of this solution in order to sharpen the responsibility:

- Any additional changes to underlying software or functionality in ELEKTRA software and field P/CR's fixes that are not mentioned in chapter 3.10.

- Coordination and agreements with non-Hitachi Rail GTS Austria GmbH-internal customers.

- Data preparation of non-testing railway stations.

- End User documentation like „Projektierungshandbuch“.

- Field Installation

- Coordination and execution of Factory Acceptance Tests (Customer labor-/integration-tests).

- Industrialisation of HW components.

- Any HW, product or solution development not mentioned in chapter 1.1.2.

- Translation of documents from previous baselines into English.

- Integrationtest with real neighbour systems (e.g. RBC, ILTIS, ...)

## Responsibility Assignment Matrix

The responsibilities of the roles at a Milestone Review can be seen in Milestone Template Solutions [S15].

## Tools and Facilities

The following subsections provide a rough overview of the project tool setup. For version information and tool classification see document Tool Classification EN50128 [9].

### Management and Documentation Tools

| Tool Category | Tool | Note |
| --- | --- | --- |
| Project Management | Primavera PCM |  |
| Task Management | iTask |  |
| Requirements Management | DOORS/RMF |  |
| Management Traceability | DOORS/RMF |  |
| Configuration Management | ClearCase | used by ELEKTRA development |
|  | Git | used by OREST and SEC development |
| Change Management | CHARM |  |
|  | JIRA | Jira is used in addition to CHARM |
| Documentation Management | ClearCase |  |
|  | DWF |  |
|  | Team Online |  |
|  | Sharepoint |  |
| Documentation Generation | DOORS/RMF |  |
|  | MS Office |  |
| Build environment ELEKTRA | ClearCase |  |
|  | ClearMake |  |
| Build environment OREST | Git |  |
|  | ANT and Maven |  |
|  | Sonar |  |
|  | Jenkins |  |
| Build environment SEC | Git |  |
|  | Maven |  |
|  | SonarQube |  |
|  | Bitbucket |  |
|  | Jenkins |  |
| IVV Management | DOORS, Excel (other Tools) |  |

Table 22: Management and Documentation Tools

### Code Building Tools

See also Tool Classification EN50128 [9] and List of SW-Baseline Label ELEKTRA Schweiz [11].

| Tool Category | Tool | Version/Label | Note |
| --- | --- | --- | --- |
| Compiler | CHILL | 2.3.12 |  |
|  | GNU C/C++ | 7.3.0 |  |
|  | JAVA | 1.8.0 212-b01 |  |
|  | PAMELA | 3.0.6 |  |
| IVV | GCOV | 7.3.0 |  |
|  | EPS | 05.28 |  |
|  | Audit Tools | BLAUDIT_05.10 EL_CONF_04.06 |  |

Table 23: Code Building Tools

# Project Context

This is an engineering project and not a customer project. The operative project is managed by Hitachi Rail GTS Schweiz AG, which manages direct contact with the customer which is the railway operator in Switzerland. This engineering project covers only a part of the requirements of the customer and has following specific characteristics:

- Customer use-cases and requirements are mostly discussed with Hitachi Rail GTS Schweiz AG and with the railway operator in Switzerland.

- Hitachi Rail GTS Schweiz AG is responsible for coordination between Hitachi Rail GTS Austria GmbH components and other components from other organisations that make up the entire customer configuration. Other organisations include: Hitachi Rail GTS Deutschland GmbH for RBC and for AzLM, Siemens for ILTIS and Sevitec for WebRide.

- Hitachi Rail GTS Schweiz AG is responsible for test and commissioning of the customer stations.

- Hitachi Rail GTS Schweiz AG is responsible for configuration (data preparation) of the stations.

- Hitachi Rail GTS Austria GmbH is responsible for the delivery of a safety certified baseline.

- Once operational, Hitachi Rail GTS Schweiz AG is responsible for the 1st and 2nd line support for the project deliverables.

## Commercial Context

There are no special commercial considerations in the project compared to projects that have been realized for the “internal” customer Hitachi Rail GTS Schweiz AG and their target customer, the railway operator in Switzerland.

## Contractual Context

This is similar to previous ELEKTRA CH projects.

## Key Issues

No specific key issues available.

## Critical Success Factors

The critical success factors for this project are:

- Success in keeping within the defined project constraints of:

- Scope

- Budget

- Quality & Safety

- Schedule

- Perceived and measured development & test efficiency going forward in the future, as compared to the development in the parallel branches. Performance and reliability that is at least as good as the previously delivered products in the parallel branches.

# Process Control

## Control of Solution Development

The solution elements and assigned responsibilities are listed in Table 3.

### Deviation

The development of a Solution has to be planned and executed according to the DDQS Processes of Management System. No deviation to the description in Project Life Cycle [S13].

### Metrics

The used metrics for control of the engineering process are identified in the Engineering Dashboard [4].

The tailoring for this dashboard is listed below:

|  | Sheet | Tailoring |
| --- | --- | --- |
|  | Actions & Decisions monitoring | Used - no deviation. |
|  | Agile Iteration Burndown | Not used. |
|  | Agile Velocity & Burndown | Not used. |
|  | Code Quality | Not used. |
|  | Code Reuse | Not used. |
|  | Defect management | Not used. |
|  | Documentation | Not used. |
|  | Finance | Used. See Note 1 below. |
|  | Interface testing progress | Not used. |
|  | IVV Test Writing | Not used. |
|  | Master planning | Used - no deviation. |
|  | Milestones | Used - no deviation. |
|  | OBS | Used - no deviation. |
|  | PCR | Used. See Note 2 below. |
|  | Progress Matrix | Used - no deviation. |
|  | Quality | Used. Data provided by QAM. |
|  | Release content progress | Optional. Not only features are tracked, but also legacy PCRs which are part of the scope as defined in section 0. |
|  | Requirement Analysis | Used. See Note 3 below. |
|  | Requirement Flowdown | Not used. |
|  | Sizing params & critical performance | Not used. |
|  | Technical Risks | Used - no deviation. |
|  | Validate & qualify test progress | Not used. |
|  | Verification testing progress | Used. See Note 4 below. |
|  | WBS | Used - no deviation. |
|  | Workload | Used - no deviation. |
|  | Note 1: Guideline: - “BCWS Planned Spend” is the monthly planned costs of work. This value can be determined from PEP or PCM. It is the defined/updated at the time the CBB is defined or updated. - “Forecast” is the spending forecast from the last month with actuals to the end of the project (before this period it has to be empty). - “EV” is not used. |  |
|  | Note 2: Guideline: This metric deals with PCRs found in the phase “Integrate and Verify the Solution”. Hence no baseline can be given ahead. The “Raised Forecast” may be predicted after a few months of this phase from past data. |  |
|  | Note 3: Guideline: Only the table "requirements chart data" is filled out, where the - "Total number of Req.": is the sum of all approved requirements at the time of the reporting. The reporting is done every month - "Baseline": a new baseline is created, when a new release of the SSS is done and a new release label is generated in DOORS - "Analysis forecast": specifies the sum of current and new requirements. - Either a value in "Baseline" or in the "Analyses forecast" is filled out except in the current month, where both fields are filled out. Additionally to be filled out are: - "Analyzed Req.": sum of all requirements, which are analyzed and not changed - "Req. to be clarified": sum of requirements, which are currently not approved, new or changed, may not be the sum of the below attributes - "Obsolete Req": sum of requirements, which will be set to descoped - "Modified Req": sum of changed requirements - "New Req": sum of new requirements Requirements characterization can be generated via DOORS, via the menu "TRSS-AT" -> "Simple Functions" -> "KPI" -> "Input for Req. analysis tab". |  |
|  | Note 4: Guideline: Field “Req. conformity (%)” may be used as a percentage of tested and verified items of the scope defined in Scope of Change (SoC) [7]. |  |

Table 24: Metrics

## Monitoring and Control of System Engineering Activities

### Periodic Internal Reviews and Meetings

| Meeting | Responsible | Attendees | Frequency | Objectives |
| --- | --- | --- | --- | --- |
| Periodically Core Team Meeting | SEM | Solution core team, ARC, WPM(s) Only on demand: CM and RM | (Bi-)weekly | Project status and action points. |
| Risk and Opportunity Review | SEM | SEM, PLM, PDA, IVVQM, SAM, QAM, VAL, VER, ARC | on-demand / quarterly |  |
| Resource Review | SEM | SEM, HoD Route Control Projects | monthly | Check utilisation and additional needs of solution team. |
| PCR Decision Meeting | IVVQM | SEM, IVVQM, ARC, Designer, SAM, VAL | On demand (when a new LabBL is available, beginning with TRR1) | Standup-Meeting |
| Cost Tracking | Project controller | SEM, HoD Route Control Projects, Project Controller | monthly | Report of costs and progress to Financial Control Director. |
| Periodically Performance Project Review (PPPR) | SEM | SEM, HoD Route Control Projects, HoD Project Engineering, HoD Engineering, QAM | monthly | Report of costs and progress, KPI dashboard, required decisions from SM to HoD Project Engineering, HoD Engineering |

Table 25: Reviews and Meetings

### Milestone Reviews and Audits

Milestone reviews are done according Milestone Template Solutions [S15]. Audits will be conducted according to the Quality Management Plan (QMP) [5].

### Reporting

Reporting is done via the Engineering Dashboard [4] and Progress Matrix.

## Critical Technologies

N/A

## Risk and Opportunities Control

The Risk and Opportunities Control in this Solution will follow the Management System Process Manage Risks and Opportunities [S7] and is monitored in the Risk Report [3].

## Corrective Action Process

Information about the Corrective Action Process can be found in the Quality Management Plan (QMP) [5].

## Independent Evaluation and Verification

Independent evaluation and verification will be done by

- the verifier and domain experts upon instruction of the verifier (VER);

- the validator (VAL);

- the safety manager (SAM).

## Estimate/Re-Estimate

The initial estimation is either an input for the phase “Orientation the Solution” or is done or verified during this phase. Re-estimation of remaining work is done during the progress of working packages typically on a monthly period. The method used for estimation is mainly “Expert estimations” based on past experience, educated assumptions and risk considerations.

## Planning

Planning is done in the tool PCM and can be found there with the identification listed in Table 1.

## Value Analysis and Design to Cost

Value Analysis and Design to Cost is performed using the Engineering Dashboard [4].

## Peer Reviews

The Peer Reviews in this Solution will follow the Document Management Rules [S14]. An overview of mandatory Documents and Reviewer has to be done according to Document List and Review Matrix for engineering projects [S16].

# Development scenario and tailoring of the System Engineering Process

This development process follows the initialization by Manage Product Policy as described in Project Life Cycle [S13].

Figure 3: Manage Project (PRJ)

Figure 4: Develop and Qualify the Solution (DDQS)

## Tailoring for this solution

### Orient the Solution

DVa does not apply to this project.	
No further deviation to the description in Project Life Cycle [S13].

### Design the Solution

No deviation to the description in Project Life Cycle [S13].

### Develop the Solution

No deviation to the description in Project Life Cycle [S13].

### Integrate and Verify the Solution

No deviation to the description in Project Life Cycle [S13].

### Validate the solution

No deviation to the description in Project Life Cycle [S13].

### Documentation Management

The naming convention for the name “Firstname Lastname” of the author, verified by, approver of a document can also be “F. Lastname”.

No other deviation to the description in Document Management Rules [S14].

# System Engineering Support

## Data and Configuration Management

Data and Configuration Management is carried out according to Management System Process CFG – Manage Configuration [S9], Document Management Rules [S14] and the specific Configuration Management plans Configuration Management Plan, ELEKTRA [10].

## Confidentiality

The rules as listed in Protection of Group Information [S12] apply.

## Export Control

Export Control is carried out according to Management System Process Control Export  [S10].

## Capitalization

Capitalization is handled in the context of the related Manage Product Policy process.

## Measurements and Analysis

See section 4.

## Technical and Non-technical Requirements Management and Control

For Requirement Management the tool DOORS is used. The Requirements Manager ensures that requirements are

- uniquely identified

- unambiguous, testable and consistent

- traced from origin through all systems

- have all changes managed

The requirements manager manages changes throughout the life of the project. If requirements change, the impact will be reflected in the project plans, work products, and activities. Any inconsistencies between these customer- and/or system requirements and project plans, work products, and activities will be identified and resolved.

## Validation of Requirements

The validation is done in accordance with the Validation Qualification plans as listed in Documentation Plan/PVR [2].

## Decision Analysis and Resolution

Decision analysis and resolutions are part of design and review processes. The results are documented in design documents, review reports and in this document.

## Subordinate Plans

There are no subordinate plans.

## Quality Assurance

The Quality Assurance in this Solution will follow Management System Process Guarantee quality and manage continuous improvement  [S11]. Additional information can be found in the Quality Management plan as listed in Documentation Plan/PVR [2].

## Certification Support Activity

See Safety Management plans as listed in Documentation Plan/PVR [2].

# END OF DOCUMENT

From Project management point of view, this project distinguishes between following types of Milestones:

- Internal: non contractual Milestones (affects only internal Stakeholder)

- External: contractual & non-payment Milestones (affects internal and external Stakeholder)

- Payment: contractual & payment Milestones (affects internal, external Stakeholder and has a financial impact)

Until TQR2 (hand over to the assessor) the combined Docu Plan/PVR will be handled within Sharepoint. With the TQR2 the first edition will be released within DWF.

Verification and validation management activities of IVVQM are delegated to the VER / VAL.