PROJECT AND SYSTEM ENGINEERING MANAGEMENT PLAN

PV GEN 2.20.10

ELEKTRA Product Line Engineering

ELEKTRA

Generic System

| APPROVAL |  |  |
| --- | --- | --- |
|  | Name and Role/Job Title | Esignature |
| Written by | Robert Strauß SEM and PM |  |
| Verified by | Christian Janneschitz QAM |  |
| Approved by | Krist Ndue Ho EJR |  |

| LOG OF CHANGES |  |  |  |
| --- | --- | --- | --- |
| Revision | Date | Author | Change Description |
| 01 | 15.04.2026 | Robert Strauß | Initial edition for milestone SOR |

Contents

1.	SCOPE	8

1.1	Identification	8

1.1.1	General	8

1.1.2	WBS managed as Solution	8

1.1.3	WBS managed as Work Packages	8

1.1.4	Other component versions this engineering solution is based on	9

1.2	System overview	10

1.3	Key points	12

1.3.1	Milestones for Solution	12

1.3.2	Deliverables	13

1.4	Relation with other plans	14

1.5	Baselines of Software Configuration Items and Documentation Labels	14

1.6	Document version history	15

1.6.1	Edition 01	15

1.7	Open points / Issues	15

2.	References and terms	16

2.1	Referenced documents	16

2.2	Process basis	17

2.3	Standards and procedures	17

2.4	Terms, abbreviations and acronyms	22

2.4.1	Terms, Abbreviations and Acronyms used in the project	23

2.4.2	Role abbreviations	24

3.	Solution engineering and development process	26

3.1	Organization of solution engineering	26

3.1.1	Solution core team	26

3.1.2	Solution team	27

3.1.3	External project roles	29

3.1.4	Configuration Control Board (CCB)	30

3.2	System engineering supplies	30

3.3	Input data	30

3.4	Preconditions / Related solutions	30

3.5	Technical objectives	31

3.6	Detailed First Level WBS for Work Packages	31

3.7	Special need for training of system engineering team	32

3.8	Constraints / Risks	33

3.9	Work Contained	33

3.10	Work not contained	33

3.11	Responsibility Assignment Matrix	33

3.12	Tools and Facilities	34

3.12.1	Management and Documentation Tools	34

3.12.2	Code Building Tools	35

4.	Process Control	36

4.1	Control of Solution Development	36

4.1.1	Deviation	36

4.1.2	Metrics	36

4.2	Monitoring and Control of System Engineering Activities	36

4.2.1	Periodic Internal Reviews and Meetings	36

4.2.2	Milestone Reviews and Audits	37

4.2.3	Reporting	37

4.3	Critical Technologies	37

4.4	Risk and Opportunities Control	37

4.5	Corrective Action Process	37

4.6	Independent Evaluation and Verification	37

4.7	Estimate/Re-Estimate	37

4.8	Planning	38

4.9	Value Analysis and Design to Cost	38

4.10	Peer Reviews	38

5.	Development scenario and tailoring of the System Engineering Process	39

5.1	Tailoring for this solution (DDQS phases)	39

5.1.1	Orient the Solution	39

5.1.2	Design the Solution	39

5.1.3	Develop the Solution	39

5.1.4	Integrate and Verify the Solution	39

5.1.5	Validate the solution	40

5.2	Tailoring for Manage Project phases	40

5.2.1	Manage Project milestones	40

5.3	Tailoring of Documentation Management	40

5.4	Tailoring of role assignments	40

5.4.1	Role of IVVQM	40

5.4.2	Role of Verifier (VER) according CENELEC EN 50716 and EN 50129	41

5.4.3	Role of DM	41

6.	System Engineering Support	42

6.1	Data and Configuration Management	42

6.2	Confidentiality	42

6.3	Export Control	42

6.4	Capitalization	42

6.5	Measurements and Analysis	42

6.6	Technical and Non-technical Requirements Management and Control	42

6.7	Validation of Requirements	42

6.8	Decision Analysis and Resolution	42

6.9	Subordinate Plans	42

6.10	Quality Assurance	43

6.11	Certification Support Activity	43

6.12	Stakeholder Management	43

APPENDIX A	Criteria for the Selection of Techniques and Measures	44

List of Tables

Table 1: Solution Identification	8

Table 2: WBS managed as Solution	8

Table 3: WBS managed as Work Packages	8

Table 4: Other component versions	9

Table 5: Milestones	12

Table 6: Deliverables	14

Table 7: Referenced Documents	16

Table 8: Standards and Procedures	17

Table 9 : Terms, Abbreviations and Acronyms	23

Table 10 : Role abbreviations	24

Table 11: Core team	26

Table 12: GenSys Team	27

Table 13: EEC Team	28

Table 14: External project roles	29

Table 15: Configuration Control Board	30

Table 16: Preconditions	30

Table 17: Detailed WBS	31

Table 18: Management and Documentation Tools	34

Table 19: Code Building Tools	35

Table 20: Reviews and Meetings	36

List of Figures

Figure 1: Product Breakdown Structure GenSys	11

Figure 2: Product Breakdown Structure WP SEC SW	12

Figure 3: Product Line Engineering Process	39

Figure 4: Manage Project (PRJ)	39

Figure 5: Develop and Qualify the Solution (DDQS)	39

# SCOPE

The combined PSEMP, Project Management Plan (PMP) and System Engineering Management Plan (SEMP) describes the organisation, work packages, milestones and application of the GTS Management System Release 2026-03 within this solution.

This solution delivers ELEKTRA 2 Generic System product version PV GEN 2.20.10 which realizes improvements and changes (see chapter 1.2) which can be used as generic base for the products ELEKTRA OBB, CH, INT and SCWS.

## Identification

### General

Table 1: Solution Identification

| Cost collector / Project ID: | 100027731, GenSys 2.20.10 |
| --- | --- |
| Solution: | ATRENDB51 |
| Identification: | PV GEN 2.20.10 |
| SIL: | 4 |
| Security Level: | SL-C 2 |
| Maturity Level: | ML 3 |

### WBS managed as Solution

Table 2: WBS managed as Solution

| In Scope | WBS | Identification | SEM | SIL | Initial Product Version | Target Version | Target date |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | ATRENDB51-E0 | Lock Trac 6131 (ELEKTRA) SYSTEM | Robert Strauß | SIL4 | PV GEN 2.19.11 | PV GEN 2.20.10 | see FQR section 1.3.1 |

### WBS managed as Work Packages

A detailed view on all WBS elements is listed in section 3.6. If a WBS below is not in scope of this Solution element, the initial version (and unchanged target version) is stated anyway.

Table 3: WBS managed as Work Packages

|  | Solution Element: | ATRENDB51-E0 |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| In Scope | WBS | Ident. | WPM | Initial Version | Target Version | Target date |
|  | ATRENDB51-E0.WP3.2.[WP-ID] | ELEKTRA Generic | Robert Strauß | PV GEN 2.19.11 | PV GEN 2.20.10 | TQR2 |
|  | ATRENDB51-E0.WP3.2.EEC | SEC SW | Benjamin Koenig | SEC SW GEN 2.2.4 SEC SW OBB 2.1.2 | SEC SW GEN 2.2.5 SEC SW OBB 2.2.0 | TRR1 |

### Other component versions this engineering solution is based on

This product version is based on the latest ELEKTRA Generic System release PV GEN 2.19.11.

The SW components of PV GEN 2.19.11 are listed in the document Version Delivery Description, Komponenten des generischen Systems PV GEN 2.19.x [7]. The HW components of PV GEN 2.19.11 are visible in the document Version Delivery Description, ELEKTRA Hardware [8].

Table 4: Other component versions

| Component | Version |
| --- | --- |
| n/a |  |

## System overview

This solution provides a safe and highly reliable generic system for the ELEKTRA 2 interlocking systems. The objective of this solution is to upgrade the existing functionality of product ELEKTRA generic system with the scope as defined as follows:

- Scope of Change (SoC) with Test Plan, PV GEN 2.20.10 [6] contains change requests and defect corrections which are planned to be released.

Note: TAS PLF deliverable OCS-SBJ 3.6.1 is budgeted by this solution.

Remark: Regarding development and release of workpackage “EEC”:

The development of the SEC SW components (SEC SW GEN 2.2.5 and SEC SW OBB 2.2.0) must be started before the start of the project ELEKTRA BL OBB_29.50 (06/2026) in order to achieve the final baseline delivery E02/2028. The SEC SW components (SEC SW GEN 2.2.5 and SEC SW OBB 2.2.0) for ELEKTRA OBB will therefore be planned (budgeted and tracked) by this solution before the milestone TRR1 of workpackage “EEC”. Then the workpackage “EEC” will be handed over to project ELEKTRA BL OBB_29.50 to complete there the remaining phases and final delivery. In terms of content (documents (SoC, TP,…), development process, milestones), the workpackage “EEC” is being handled within the project ELEKTRA BL OBB_29.50. 	
No SEC HW development is planned in context of this solution.

- The scope of workpackage “EEC” is defined in the Workpackage Description EEC [11].

Remark: Regarding component “RJC SAHARA 2.3.0”:

The component “RJC SAHARA 2.3.0” will be developed by project “RJC 2025 1” and managed within workpackage “EEC” because the same people are working together, see Change Management Report RJC 2025 1 [12].

Note: Workpackage “EEC” with component “RJC SAHARA 2.3.0” is NOT part of product ELEKTRA Generic System.

The initial and target versions of this solution is listed in Table 2, and their work packages for this engineering project are listed in Table 3.

The Product Breakdown Structure for ELEKTRA generic system can be found below Figure 1.

Level 1

Level 2

Level 3

ELEKTRA PV GEN 2.20.10

Tools update

SCWS

ELEKTRA BL OBB 29.50

ELEKTRA BL SBB 23.00

ELEKTRA BL INT 25.00

TAS Platform Core 2.6.1

CAR 5.3.0

OCS-SBJ 3.6.1

J4S 3.6.1

Figure 1: Product Breakdown Structure GenSys

The Product Breakdown Structure for workpackage SEC SW (see remark below Table 3) can be found below Figure 2.

Level 1

Level 2

Level 3

ELEKTRA BL OBB 29.50

SEC SW OBB 2.2.0

SEC SW GEN 2.2.5

TAS Platform Core 2.6.1

RJC SAHARA 2.3.0

J4S 3.6.1

Figure 2: Product Breakdown Structure WP SEC SW

## Key points

### Milestones for Solution

Table 5: Milestones

| Milestone | Target Date | Comments |
| --- | --- | --- |
| Business Plan Decision Review (BP DR) | Defined on level MPP | Together with project ELOBB BL29.50 |
| Kick Off Meeting (KOM) | See tailoring chapter 5.2.1 |  |
| Solution Orientation Review (SOR) | 23.04.2026 |  |
| Launch Review (LR) | 29.05.2026 See tailoring chapter 5.2.1 |  |
| Development Launch Decision Review (DL DR) | Defined on level MPP | Together with project ELOBB BL29.50 |
| Solution Requirements Review (SRR) | 31.07.2026 |  |
| Solution Functional Review (SFR) | 30.10.2026 |  |
| Preliminary Design Review (PDR) | 18.12.2026 |  |
| Critical Design Review (CDR) | 18.12.2026 |  |
| Test Readiness Review (TRR1) | 30.06.2027 |  |
| Technical Qualification Review (TQR1) | 29.10.2027 | Test GenSys 2.20.10 ready (Stability, Module Tests,… Ready with PLF 2.6.1, OCS-SBJ 3.6.1, J4S 3.6.1). Date depends also on finalization of ELOBB BL29.50 application tests. |
| Test Readiness Review (TRR2) | 29.10.2027 |  |
| Technical Qualification Review 2 (TQR2) | 03.12.2027 | Depends also on application tests. |
| Acceptance Review (AR) | See tailoring chapter 5.2.1 |  |
| Final Qualification Review (FQR) | 29.02.2028 | Depends also on application assessment. |
| Deployment Decision Review (DP DR) | Defined on level MPP | Together with project ELOBB BL29.50 |
| Closure Review (CR) | See tailoring chapter 5.2.1 |  |

### Deliverables

Deliverables in scope of this engineering project are listed below:

Table 6: Deliverables

| Deliverable Generic System | Target Date | Comment |
| --- | --- | --- |
| CAR 5.3.0.x developer version | 03/2026 |  |
| GenSys 2.20.10 developer version on TAS PLF 2.6.0 | 07/2026 | Ready for pre-stability tests and pre-integration tests |
| GenSys 2.20.10 developer version on TAS PLF 2.6.1 (final version) with OCS-SBJ 3.6.1 TRR1 developer version | 05/2027 | Ready for application pre-integration tests |
| GenSys 2.20.10 feature complete on TAS PLF 2.6.1 | TRR1 | Ready for final stability test and application integration tests |

| Deliverable workpackage EEC |  |  |
| --- | --- | --- |
| SEC GEN/OBB developer version (ECMUX+OEC on TAS PLF 2.6.0) | E05/2026 | Ready for pre-integration tests |
| SEC SW GEN 2.2.5 and SEC SW OBB 2.2.0 feature complete | TRR1 | Ready for application integration tests |

| Deliverable project RJC 2025 1 |  |  |
| --- | --- | --- |
| RJC SAHARA 2.3.0 (TRR1 with RC1) | B12/2026 |  |
| RJC SAHARA 2.3.0 (TQR1) | B06/2027 |  |

## Relation with other plans

The PSEMP describes the application of the GTS Management System Solutions Engineering Processes (DDQS) to the design, development and deployment of the Solution ATRENDB51.

This document will be updated as the Solution effort evolves.

A general overview of the Solution and Project documents hierarchy is shown in the Documentation Plan PV GEN 2.20.10 [1].

## Baselines of Software Configuration Items and Documentation Labels

The labelling is based on the definitions of the Configuration Management Plan and as defined in the Documentation Plan PV GEN 2.20.10. The following labels have to be used:

- PV_EL_GEN_2.20.10 for all related documents of generic system in DWF.

- CAR_5.3.0 for all related documents of component CAR in DWF.

- <<generic component>_yy.zz_nn> for the software

The respective delivery is defined as the label without suffix “_nn” where yy.zz describe the intended target version in the field /for customer.

## Document version history

### Edition 01

Initial edition.

## Open points / Issues

None.

# References and terms

## Referenced documents

If not explicitly stated, the relevant version of a document is referenced in the Documentation Plan PV GEN 2.20.10 [1].

Table 7: Referenced Documents

| Nr./Title | Reference | Version |
| --- | --- | --- |
| - Documentation Plan PV GEN 2.20.10 | 3BU_15000_5337_ADAPA | 01 |
|  | SP-ID: MUQAPWKYFAJS-1008298600-135 | Working version |
| - Risk Report PV GEN 2.20.10 | SP-ID: MUQAPWKYFAJS-1008298600-130 | Latest |
| - Risk Report EEC | SP-ID: MUQAPWKYFAJS-1008298600-131 | Latest |
| - Engineering Dashboard PV GEN 2.20.10 | SP-ID: MUQAPWKYFAJS-1008298600-137 | Latest |
| - Quality Management Plan (QMP) ELEKTRA | 3BU_15000_5244_QMAPA | 08 |
| - Scope of Change (SoC) with Test Plan, PV GEN 2.20.10 | 3BU_15000_5337_QEAPA | 01 |
| - Version Delivery Description, Komponenten des generischen Systems PV GEN 2.19.x | 3BU_15000_5279_QEAPA | 08 |
| - Version Delivery Description, ELEKTRA Hardware | 3BU_15000_5225_ELAPA | 41 |
| - Software Development Tool Classification EN50128 | 3BU_15000_5135_AAAPA | 28 |
| - Configuration Management Plan | 3BU_15000_3338_QMAPA | 11 |
| - Workpackage Description EEC | 3BU_15000_2452_DPAPA | 01 |
|  | Confluence WPD EEC | Working version |
| - Change Management Report RJC 2025 1 | 3BU_01500_1501_DFAPA | 02 |

## Process basis

The project is set up with the GTS Management System Release 2026-03 as process basis. Changes in this process basis (e.g. adaptation to a new service release of GTS Management System) have to be analyzed, especially regarding the impact on already existing work products, and have to be documented and approved.

## Standards and procedures

Table 8: Standards and Procedures

| Nr./Title | Publishing Date/ Reference | Version/ Revision |
| --- | --- | --- |
| - ISO 22163:2023 Railway applications – Railway quality management system – ISO 9001:2015 and particular requirements for application in the rail sector | 2023 | n/a |
| - EN 50716:2023 (supersedes EN 50128) Railway Applications – Requirements for software development | 2023 | n/a |
| - EN 50129:2018 + AC:2019 Railway applications Safety related electronic systems for signalling | 2018, 2019 | n/a |
| - ISO 9001:2015 Quality management system - Requirements | 2015 | n/a |
| - EN 50126:2017 Railway applications. The specification and demonstration of reliability, availability, maintainability and safety (RAMS) Part 1: Generic RAMS Process Part 2: Systems Approach to Safety | 2017 | n/a |
| - EN 50121-4:2016 Railway applications Electromagnetic compatibility Part 4: Emission and immunity of the signalling and telecommunications apparatus | 2016 | n/a |
| - EN 50159:2010 + A1:2020 Railway applications – Communication, signalling and processing systems – Safety-related communication in transmission systems | 2010, 2020 | n/a |
| - Management System Process Manage Risks and Opportunities | Part of 87200984-00-PRJ-GRP-EN chapter 8.6 | n/a |
| - Design, Develop and Qualify the Solution | 87202127-00-DDQ-GRP-EN | n/a |
| - Management System Process DDQ-SW - Design, develop and qualify the Software solution | 87202125-00-DDQ-GRP-EN | n/a |
| - Management System Process DDQ-HW - Design, develop and qualify the Hardware solution | 87202126-00-DDQ-GRP-EN | n/a |
| - Management System Process CFG - Manage Configuration | 87202424-00-CFG-GRP-EN | n/a |
| - Management System Process Control Export | Part of 87201392-00-LEG-GRP-EN | n/a |
| - Management System Process Guarantee quality and manage continuous improvement | 87200214-00-QCI-GRP-EN | n/a |
| - Information Classification Standard | 90000485-ESS-GRP-EN (CYB-STD-009) | 2.8 |
| - Project Life Cycle | 83530275-DDQ-AUT-EN | 005 |
| - Document Management Rules | 83530061-DOC-AUT-EN | 014 |
| - Milestone Template Solutions | 83530019-DDQ-AUT-EN | 013 |
| - Document List and Review Matrix for engineering projects | 83530224-DOC-AUT-EN | 012 |
| - ELEKTRA 2.x System, Glossary: Definitions, Acronyms and Abbreviations | 3BU_15000_0081_DCAPA | 06 |
| - Hitachi Rail Austria - Glossary | 3BU_15000_8008_WDAPQ latest update: http://trss-at.at.gts/glossword | 04 |
| - EN 61000-4-3:2006 Electromagnetic compatibility (EMC) – Part 4-3: Testing and measurement techniques – Radiated, radio-frequency, electromagnetic field immunity test | 2006 | n/a |
| - EN 61000-4-4:2012: Electromagnetic compatibility (EMC) – Part 4-4: Testing and measurement techniques – Electrical fast transient/burst immunity test | 2012 | n/a |
| - EN 61000-4-5:2014, Electromagnetic compatibility (EMC) – Part 4.-5: Testing and measurement techniques – Surge immunity test | 2014 | n/a |
| - EN 61000-4-6:2014: Electromagnetic compatibility (EMC) – Part 4-6 Testing and measurement techniques – Immunity to conducted disturbances, induced by radio-frequency fields | 2014 | n/a |
| - EN 61000-4-11:2004 + A1:2017 Elektromagnetische Verträglichkeit (EMV) – Teil 4-11: Prüf- und Messverfahren – Prüfung der Störfestigkeit gegen Spannungseinbrüche, Kurzzeitunterbrechungen und Spannungsschwankungen | 2017 | n/a |
| - EN 61000-6-4:2007 +A1:2011: Elektromagnetische Verträglichkeit (EMV) – Teil 6-4: Fachgrundnormen – Störaussendung für Industriebereiche | 2007/2011 | n/a |
| - EN 61000-4-2:2009, Electromagnetic compatibility (EMC) – Part 4.-2: Testing and measurement techniques – Electrostatic discharge immunity test | 2009 | n/a |
| - EN 50122-1:2011/A2:2016 Railway application – Fixed installations – Electrical safety, earthing and the return circuit – Part 1: Protective provisions against electric shock | 2011/2016 | n/a |
| - EN 60529:1991 +A1:2001 + A2:2013 Schutzarten durch Gehäuse (IP-Code) | 1991/2001/2013 | n/a |
| - EN 55016-2-1:2014: Specification for radio disturbance and immunity measuring apparatus and methods – Part 2-1: Methods of measurement of disturbances and immunity – Conducted disturbance measurements (CISPR 16-2-1:2014) | 2014 | n/a |
| - CISPR 22:2008 Information technology equipment – Radio disturbance characteristics – Limits and methods of measurement | 2008 | n/a |
| - EN 50124-1:2017 Railway applications – Insulation coordination | 2017 | n/a |
| - EN 50121-4:2016, Railway applications – Electromagnetic compatibility – Part 4: Emission and immunity of signaling and telecommunications apparatus | 2016 | n/a |
| - EN 50124-1:2017 Railway applications – Insulation coordination – Part 1: Basic requirements – Clearances and creepage distances for all electrical and electronic equipment | 2017 | n/a |
| - EN 50125-3:2003 +Corrigendum Mai 2010: Bahnanwendungen; Umweltbedingungen für Betriebsmittel, Teil 3: Umweltbedingungen für Signal- u. Telekommunikationseinrichtungen | 2003 | n/a |
| - EN 60068-1:1994: Umweltprüfungen; Teil 1: Allgemeines und Leitfaden | 1994 | n/a |
| - EN 60068-2-1:2007: Umgebungseinflüsse; Teil 2-1: Prüfverfahren – Prüfung A: Kälte | 2007 | n/a |
| - EN 60068-2-2: 2007: Umgebungseinflüsse; Teil 2-2: Prüfverfahren – Prüfung B: Trockene Wärme | 2007 | n/a |
| - EN 60068-2-27: 2009: Umgebungseinflüsse – Teil 2-27: Prüfverfahren – Prüfung Ea und Leitfaden: Schocken | 2009 | n/a |
| - EN 60068-2-5:2011: Environmental testing. Part 2-5: Tests. Test Sa: Simulated solar radiation at ground level | 2011 | n/a |
| - EN 60068-2-30:2005: Umgebungseinflüsse; Teil 2-30: Prüfverfahren – Prüfung Db: Feuchte Wärme, zyklisch (12 + 12 Stunden) | 2005 | n/a |
| - EN 60068-2-29:93.04: Basic environmental testing procedures; part 2: tests; test Eb and guidance: bump | 1993 | n/a |
| - EN 60068-2-31:2008: Environmental testing – Part 2-31: Tests – Test Ec: Rough handling shocks, primarily for equipment-type specimens | 2008 | n/a |
| - EN 60068-2-64:2008: Umgebungseinflüsse – Teil 2-64: Prüfverfahren – Prüfung Fh: Schwingen, Breitbandrauschen (digital geregelt) und Leitfaden | 2008 | n/a |
| - OVE EN IEC 60721-3-1:2019 Klassifizierung von Umgebungsbedingungen – Teil 3-1: Klassen von Einflussgrößen und deren Grenzwerte – Lagerung | 2019 | n/a |
| - OVE EN IEC 60721-3-2:2019-01-01 Language: DE Klassifizierung von Umgebungsbedingungen – Teil 3-2: Klassen von Einflussgrößen und deren Grenzwerte – Transport und Handhabung | 2019 | n/a |
| - CISPR 16-1-1:2010, Specification for radio disturbance and immunity measuring apparatus and methods – Part 1-1: Radio disturbance and immunity measuring apparatus – Measuring apparatus | 2010 | n/a |
| - CISPR 16-1-2:2003, Specification for radio disturbance and immunity measuring apparatus and methods – Part 1-2: Radio disturbance and immunity measuring apparatus – Ancillary equipment – Conducted disturbances | 2003 | n/a |
| - CISPR 16-1-4:2007, Specification for radio disturbance and immunity measuring apparatus and methods – Part 1-4: – Radio disturbance and immunity measuring apparatus – Radiated disturbances | 2007 | n/a |
| - CISPR 16-2-1:2008, Specification for radio disturbance and immunity measuring apparatus and methods – Part 2-1: Methods of measurement of disturbances and immunity – Conducted disturbance measurements | 2008 | n/a |
| - CISPR 16-2-3:2006, Specification for radio disturbance and immunity measuring apparatus and methods – Part 2-3: Methods of measurement of disturbances and immunity – Radiated disturbance measurements | 2006 | n/a |
| - EN 61000-6-2:2005 Electromagnetic compatibility (EMC) – Part 6-2: Generic standards – Immunity for industrial environments | 2005 | n/a |
| - IEC 62443-4-1:2018 Security for industrial automation and control systems – Part 4-1: Secure product development life-cycle requirements | 2018 | n/a |
| - IEC 62443-4-2:2019 Security for industrial automation and control systems – Part 4-2: Technical security requirements for IACS components | 2019 | n/a |
| - MLS Security Engineering Instruction 83559080-DDQ-DEU-EN-002 | 83559080-DDQ-DEU-EN | 002 |

## Terms, abbreviations and acronyms

For Terms and abbreviations see [S20] and [S21]. Missing terms/abbreviations are added in the following tables.

### Terms, Abbreviations and Acronyms used in the project

Table 9 : Terms, Abbreviations and Acronyms

| App | Applicable |
| --- | --- |
| BCWS | Budgeted Cost of Work Scheduled |
| CBB | Contract Budget Baseline |
| CCB | Configuration Control Board |
| CDR | Critical Design Review |
| DDQS | Design, Develop and Qualify the Solution |
| EL1 | ELEKTRA Generation 1 |
| EL2 | ELEKTRA Generation 2 |
| ESM | Electronic Storage Media |
| EV | Earned Value |
| FQR | Final Qualification Review |
| HW | Hardware |
| IVV | Integration, Verification and Validation |
| JPS | Juridical Protocol Service |
| KOM | Kick of Meeting |
| M | Mandatory |
| MDS | Monitoring and Data collection System |
| N/A | Not applicable |
| O | Optional |
| PCM | Primavera Core Model |
| PCR | Problem Change Request |
| PDR | Preliminary Design Review |
| PEP | Personnel Efforts Planning |
| PMP | Project Management Plan |
| QMP | Quality Management Plan |
| RAMS | Reliability, Availability, Maintainability and Safety |
| SE | Solution Element |
| SEMP | System Engineering Management Plan |
| SFR | Solution Functional Review |
| SIL | Safety Integrity Level |
| SOR | Solution Orientation Review |
| SP-ID | Sharepoint Identifier (document identifier within Sharepoint) |
| SRR | Solution Requirement Review |
| SubIT | Subsystem Integration Test |
| SW | Software |
| TQR | Technical Qualification Review |
| TRR | Test Readiness Review |
| WBS | Work Breakdown Structure |
| WP | Work Package |
| WPD | Work Package Description |

### Role abbreviations

Table 10 : Role abbreviations

| ARC | Architect |
| --- | --- |
| CM | Configuration Manager |
| DM | Document Manager |
| DPM | Data Preparation Manager |
| HoD | Head of Discipline |
| IVQM | Integration, Verification and Qualification Manager |
| PDA | Project Design Authority |
| PLM | Product Line Manager |
| PM | Project Manager |
| PSM | Project Security Manager |
| QAM | Quality Assurance Manager |
| RAM-AM | Reliability, Availability, Maintainability Assurance Manager |
| SAM | Safety Assurance Manager |
| RM | Requirements Manager |
| SecAM | Security Assurance Manager |
| SEM | System Engineering Manager |
| SM | Senior Management |
| TM | Test Manager |
| VAL | Validator |
| VER | Verifier |
| WPM | Work Package Manager |

# Solution engineering and development process

The Solution will be conducted according to GTS Management System (see also 2.2). As the GTS Management System is continuously improving, it has to be mentioned, that in the evolution of the Solution, for newly created documents within this project, the respective valid templates have to be used according to the up-to-date Management System. For maintenance and extension of existing documents the previously used template may remain.

## Organization of solution engineering

The description of the roles mentioned below can be found on the GTS Management System Portal.

### Solution core team

Table 11: Core team

| Role | Resource | Deputy Resource |
| --- | --- | --- |
| PLM | Mario Dum / MP | Karl Schnabl / MP |
| PM / SEM | Robert Strauß / EJR | Benjamin König / EPR |
| PDA | Alexander Paul / ESD | Attila Nemeth / EJR Erwin Glaser / EPR (support) |
| IVQM/TM | Szilard Bako / EJR (OG) | Robert Strauß / EJR |
| VER | Horst Walenta / EJT See **) below table | Elaheh Rahmani / EJT |
| SAM | Roman Büger / RS | Christoph Sünder / RS |
| QAM | Christian Janneschitz / QA | Fabian Rotter / QA |
| VAL | Kurt Fuchs / RV | Igor Grgic / RV |
| PSM | Tomas Fischer / EDI | Sandra Cako |

**) The verification according CENELEC of all documents is performed throw reviews by the roles defined in the Document List and Review Matrix for engineering projects [S19]. The role VER is not executed by a single person. The VER activities are distributed to following roles:

- Process Verification: is made by QAM

- Final document Verification: is made by VER

- Software/Code Verification: is made by domain expert

- Deliverables Verification: is made by IVM

- Enabling systems Verification: is made by CM

- Lifecycle phases Verification: is made by VER

- Collection of Verification results in Verification-report: is made by VER

### Solution team

Table 12: GenSys Team

| Role | Resource | Deputy Resource |
| --- | --- | --- |
| ARC | Thomas Reitmayr / EPR | Matthias Westermeier / EPR |
| RM | Michael Schneider / EJT | Igor Miler / EJT Natalia Karmatska / EJT |
| CM | Una Larkin / EJT | Martin Socha / EJT (support) |
| DM | see *) below table | n/a |
| RAM-AM | Florian Moser / RR | Borivoje Pavlovic / RR |
| SecAM | Jean-Marie Lauranson / EDI | n/a |
| WPM(s) | Benjamin König / EPR | SEM |
| Software Engineer ELEKTRA | Wolfgang Arthold / EPR Zoltan Bek / EPR Matthias Westermeier / EPR Mihai Paslariu (ROM) Georg Schild / EJR Tobias Fuchs / EJR Herbert Mair / EJR Lukas Santner / EJR Karl Padourek (Consultant) Peter Kovacs / EJR (OG) Tamas Ruzsovits / EJR (OG) Rene Prikler / EJR (OG) | n/a |
| Security Engineer ELEKTRA | Klaus Botschen / EPR | n/a |
| Integration Engineer | Matthias Westermeier / EPR | n/a |
| Tester (Stability test) | Valentin Voicu / ROM | Georgian-Adelin Cioraneanu / ROM Catalin Bondrea / ROM (support) |
| Tester ELEKTRA (AzLM interface) | Istvan Hegyi / EJR (OG) | n/a |
| Tester Security feature | Catalin Bondrea / ROM | n/a |
| Tester (MT for FBI/BUSEXE/Generic functions) | Dan-Mihai Preoteasa / ROM (FBI/BUSEXE-MT) Catalin Bondrea / ROM | n/a |

*) The role DM is not executed by a single person. The major DM activities are spread to other roles:

- new ANV: can be obtained by SEM

- Document Index: is made by CM or SEM

- Formal check at release of a document: is made by QAM

- Other DM activities: are made by author of the document

Table 13: EEC Team

| Role | Resource | Deputy Resource |
| --- | --- | --- |
| WPM | Benjamin König / EPR | Rambo Raul / EPR SEM |
| PDA | Reinhard Holzmann / EPR | n/a |
| ARC | Reinhard Holzmann / EPR | n/a |
| IVM (from BL OBB_29.50) | Marko Gvozdic / EPR | n/a |
| SAM | Roman Büger / RS | n/a |
| VAL | Wolfgang Luef / RV | n/a |
| PSM | Tomas Fischer / EDI | n/a |
| SAM + VER (RJC SAHARA) | Denis Dema / RS | n/a |
| QAM (RJC SAHARA) | Christian Janneschitz / QA | n/a |
| VAL (RJC SAHARA) | Gerhard Schmid / RS | n/a |
| PSM (RJC SAHARA) | Jean-Marie Lauranson / EDI | n/a |
| Scrum Master | Rambo Raul / EPR | n/a |
| Software Engineer EEC | Klaus Aichner / EPR Robert Mittermayr / EPR Dushko Zashev / EPR Frigyes Pratser / EPR Andrei Iancu / ROM Asja Korlevic / EPR Christiana-Marie Popescu / ROM Alexandru Telehoi / ROM | n/a |
| Security Engineer EEC | Balazs Mezoedi / EPR | n/a |
| Security Tester EEC | Mihai Malaianu / ROM | n/a |
| SubIT Tester EEC | Lukas Kritzl / EPR | n/a |

### External project roles

Table 14: External project roles

| Role | Resource | Deputy Resource |
| --- | --- | --- |
| Safety Assessor | B. Pemmer (Arsenal RACE) | n/a |
| Tools & Workbenches | Werner Schütz / EDT Manfred Edelbauer / EJR | n/a |

### Configuration Control Board (CCB)

Table 15: Configuration Control Board

| Role | Resource | Comment | M/O |
| --- | --- | --- | --- |
| PLM | see Table 11 | Budget, schedule, scope | M |
| PM | see Table 11 |  | M |
| PDA | see Table 11 |  | M |
| SEM | see Table 11 |  | M |
| WPM | see Table 12 |  | O |
| SAM | see Table 11 |  | M |
| IVQM/TM | see Table 11 |  | M |
| VAL | see Table 11 |  | M |
| QAM | see Table 11 |  | M |
| PSM | see Table 11 |  | O |
| RAM-AM | see Table 12 |  | O |
| Head of IxL Development | Krist Ndue | Budget, schedule, resources EJR | M |
| Head of Local Product Development | Gerhard Schmidmayr | for priority conflicts regarding resources department EJ | O |

Other project team members are invited to the CCB as needed.

## System engineering supplies

Not applicable in this project.

## Input data

See Table 4.

## Preconditions / Related solutions

Table 16: Preconditions

| Deliverable | Completion Date | Provider |
| --- | --- | --- |
| TAS PLF 2.6.0 TQR1 (Core Deliverable 2.6.0.8) | 14.01.2026 | TAS PLF Core 2.6.0 |
| TAS PLF 2.6.1 TQR1 | cw2708 (E02/2027) | TAS PLF Core 2.6.1 |
| J4S release x84 32-bit with GraalVM supporting Core 2.6.0 based on J4S 3.1.0 | cw2610 (B03/2026) | TAS PLF J4S 3.6.0 |
| J4S 3.6.1 TRR1 developer release | cw2713 (B03/2027) | TAS PLF J4S 3.6.1 |
| J4S 3.6.1 TQR1 | cw2719 (M05/2027) | TAS PLF J4S 3.6.1 |
| OCS SBJ 3.6.1 developer release (with SAHARA support) | cw2616 (M04/2026) | TAS PLF OCS SBJ 3.6.1 |
| OCS SBJ 3.6.1 TRR1 developer release | cw2714 (B-M04/2027) | TAS PLF OCS SBJ 3.6.1 |
| OCS SBJ 3.6.1 TQR1 | cw2724 (M06/2027) | TAS PLF OCS SBJ 3.6.1 |
| New MEN-D10 version (RAM, BIOS, TPM FW) FQR | cw2645 (B-M11/2026) | TAS PLF |
| New MEN-D10 version delivery for lab usage | EQ1/2027 |  |

## Technical objectives

The major technical objective of this ELEKTRA 2 system product version PV GEN 2.20.10 is to migrate to TAS PLF 2.6.0/1, realize fix for y2038 problem, achieve SL-2 and to be Cyber Resilience Act (CRA) compliant, which can be used as generic base for the ELEKTRA OBB, SBB, INT and SCWS applications.

For detailed scope see Scope of Change (SoC) with Test Plan, PV GEN 2.20.10 [6].

## Detailed First Level WBS for Work Packages

Table 17: Detailed WBS

| WBS element ID | WBS element name | WBS el. manager | Comments |
| --- | --- | --- | --- |
| ATRENDB51-E0.GC | General Costs | SEM | Cost collector. |
| ATRENDB51-E0.KMS | Key Milestones | SEM | GTS Management System DDQS |
| ATRENDB51-E0PM | Management and Support | SEM | Contains Level of effort tasks (accompany the project) like efforts for meetings, QAM, RM, IVQM, CM, VAL, SEM, VER, RAM-AM, SAM, Expert support. |
| ATRENDB51-E0.WP3.2.SL2 | Cyber Security for SL-C 2 | see Table 3 | Contains tasks for Cyber Security for SL-C 2 (PSM, development, integration, verification) |
| ATRENDB51-E0.WP3.2.PLF26M | Work package: TAS PLF 2.6.x Migration | see Table 3 | Contains tasks for TAS PLF migration (development, integration, verification). |
| ATRENDB51-E0.WP3.2.OCSSBJ | Work package: TAS PLF OCS-SBJ 3.6.1 | SEM | Cost collector: for TAS PLF deliverable OCS-SBJ 3.6.1 |
| ATRENDB51-E0.WP3.2.IFAZLM | Work package: AzLM Interface with OCS-SBJ | see Table 3 | Contains tasks for AzLM Interface with OCS-SBJ (development, integration, verification). |
| ATRENDB51-E0.WP3.2.IFRBC | Work package: RBC Interface (CH) with OCS-SBJ | see Table 3 | Cost collector: Contains tasks for RBC Interface (CH) with OCS-SBJ (development, integration). This workpackage will be transferred to project BL SBB_23.00 as it starts or closed by TRR1. |
| ATRENDB51-E0.WP3.2.NSAFC | Work package: New safety concept 2 Channel on one HW | see Table 3 | Contains tasks for New safety concept 2 Channel on one HW (SAM). |
| ATRENDB51-E0.WP3.2.LPCR | Work package: Legacy PCRs | see Table 3 | Contains tasks for legacy PCRs (development, integration, verification). |
| ATRENDB51-E0.WP3.2.EEC | Work package: EEC PLF 2.6.x Migration (SEC, ECMUX, RJC) | see Table 3 | Contains tasks for EEC PLF 2.6.x Migration (SEC, ECMUX, RJC) (development, integration, verification, SAM, VAL, QAM, PSM, WPM). This work package will be handed over to project BL OBB_29.50 before milestone TRR1 (closed by TRR1). |

## Special need for training of system engineering team

All engineering project roles shall attend following training:

- Cybersecurity Foundations for Engineers

Architects, developers and testers shall also attend following training:

- Cybersecurity Secure design, development and testing

Additionally, training on job is planned for Security Engineers and Security Testers.

Training on the job is planned in 2026 for

- Rene Prikler and Tamas Ruzsovits (new ELEKTRA generic system developers) by Wolfgang Arthold (experienced ELEKTRA generic system developer);

- Valentin Voicu and Adelin Cioraneanu (new stability-test testers) by Catalin Bondrea (experienced stability-test tester);

- Alexander Paul with support by Erwin Glaser in the role PDA.

## Constraints / Risks

Constraints which are not already considered in the Risk Report PV GEN 2.20.10 [2] and Risk Report EEC [3] are listed here.

- None.

## Work Contained

Engineering of the scope mentioned in section 1.2 according to the applying parts of the relevant standards listed in section 2.3.

Delivery of the baseline documentation, including the Safety Cases and Security Case.

Delivery of the items listed in section 1.3.2.

## Work not contained

While the work contained is already stated in section 3.9, the following topics are explicitly mentioned as not part of this solution in order to sharpen the responsibility:

- Assessment Certification for the solution. Details have to be documented in Chapter 5.1.5 Validate the solution

Coordination and agreements with non- Hitachi Rail Austria GmbH-internal customers.

Data preparation of non-testing railway stations.

Installation

Coordination and execution of Factory Acceptance Tests (Customer labor-/integration-tests).

Coordination and execution of System integration tests.

Coordination of Application Development system/integration-tests.

No integration or test of mixed HW versions D6/D10.

Industrialisation of HW components.

Any HW, product or solution development not mentioned in section 1.1.2 or 1.1.3.

Any other kind of customer- / user-documentation as described in section 3.9. The following examples are all in responsibility of PDA of application and customer project:

  - Update of the user document “Wartung und Instandsetzung ESTW Stellwerks-Rechner "

Translation of documents from previous baselines into English.

Training of new and external (Romanian, Hungarian) employees.

Documents (SoC, TP,…), development process, milestones) of workpackage “EEC” is not contained, this is being handled within the project ELEKTRA BL OBB_29.50.

Everything for workpackage “EEC” from milestone TRR1 onwards is not contained.

## Responsibility Assignment Matrix

The responsibilities of the roles at a Milestone Review can be seen in Milestone Template Solutions [S18].

## Tools and Facilities

The following subsections provide a rough overview of the project tool setup. For version information and tool classification see document

| - Version Delivery Description, ELEKTRA Hardware | 3BU_15000_5225_ELAPA | 41 |
| --- | --- | --- |
| - Software Development Tool Classification EN50128 | 3BU_15000_5135_AAAPA | 28 |

[8].

### Management and Documentation Tools

Table 18: Management and Documentation Tools

| Tool Category | Tool | Note |
| --- | --- | --- |
| Project Management | Primavera PCM |  |
| Task Management | iTask |  |
| Requirements Management | DOORS/RMF |  |
| Management Traceability | DOORS/RMF |  |
| Configuration Management | ClearCase Git |  |
| Change Management | Jira/CHARM |  |
| Documentation Management | ClearCase DWF Sharepoint Confluence |  |
| Documentation Generation | DOORS RMF Java Doc MS Office |  |
| Model Driven Engineering | n/a |  |
| Build environment ELEKTRA | ClearCase ClearMake |  |
| Build environment EBO2 | n/a |  |
| Build environment OREST | n/a |  |
| Build environment SEC | Git Maven Bitbucket Jenkins |  |
| IVV Management | DOORS, Excel (other Tools) |  |
| Security Management | OpenVAS OpenSCAP NMAP CVEval | Vulnerability Assessment Scanner Security Content Authentication Protocol |

### Code Building Tools

Table 19: Code Building Tools

| Tool Category | Tool | Version | Note |
| --- | --- | --- | --- |
| Compiler | CHILL | 2.3.13 |  |
|  | TAS PLF GCC | 13.3.0 |  |
|  | JAVA | 1.8 |  |
|  | PAMELA | 3.07 |  |
| IVV | GCOV | See comment | Version provided with GNUCHILL compiler (GCC) |
|  | EPS | 05.31 |  |
|  | COTO | n/a |  |
|  | Audit Tools | 05.20 |  |

# Process Control

## Control of Solution Development

The solution elements and assigned responsibilities are listed in Table 2.

### Deviation

The development of a Solution has to be planned and executed according to the DDQS Processes of GTS Management System No deviation to the description in Project Life Cycle [S16].

### Metrics

The used metrics for control of the engineering process are identified in the Engineering Dashboard PV GEN 2.20.10 [4].

The template for the engineering dashboard can be found on SharePoint Side Engineering Operation see following link: Engineering Dashboard - AT

## Monitoring and Control of System Engineering Activities

### Periodic Internal Reviews and Meetings

Table 20: Reviews and Meetings

| Meeting | Responsible | Attendees | Frequency | Objectives |
| --- | --- | --- | --- | --- |
| periodically Core Team Meeting | SEM | Solution core team, ARC, WPM(s) Only on demand: CM and RM | Bi-weekly | Project status and action points. |
| Risk and opportunity review | SEM | SEM, PLM, PDA, IVVQM, PSM, SAM, RAM-AM | Quarterly or on demand |  |
| Resource review | SEM | SEM, HoD Route Control, HoD Route Control Projects | on demand | Check utilisation and additional needs of solution team. |
| Cost tracking | Project controller | SEM, HoD Route Control, HoD Route Control Projects, Project Controller | monthly | Report of costs and progress to Financial Control Director. |
| Periodically Performance Project Review (PPPR) | SEM | SEM, HoD Route Control, HoD Route Control Projects, HoD Project Engineering, HoD Engineering Only on demand: SEM OBB BL 29.50, SEM SBB BL 22.30, SEM ELINT 25.00, SEM SCWS | monthly | Report of costs and progress, KPI dashboard, required decisions from SM to HoD Project Engineering, HoD Engineering |

### Milestone Reviews and Audits

Milestone reviews are done according Milestone Template Solutions [S18]. Quality Audits will be conducted through the QAM – see Quality Management Plan (QMP) ELEKTRA [5].

### Reporting

Reporting is done via the Engineering Dashboard PV GEN 2.20.10 [4].

## Critical Technologies

N/A.

## Risk and Opportunities Control

The Risk and Opportunities Control in this Solution will follow the Management System Process Manage Risks and Opportunities [S8] and is monitored in the Risk Report PV GEN 2.20.10 [2].

## Corrective Action Process

Information about the Corrective Action Process can be found in the Quality Management Plan (QMP) ELEKTRA [5].

## Independent Evaluation and Verification

Independent evaluation and verification will be done by

- the verifier and domain experts upon instruction of the verifier (VER);

- the validator (VAL);

- the safety manager (SAM);

- the security assurance manager (SecAM).

## Estimate/Re-Estimate

The initial estimation is either an input for the phase “Orientation the Solution” or is done or verified during this phase. Re-estimation of remaining work is done during the progress of working packages typically on a monthly period. The method used for estimation is mainly “Expert estimations” based on past experience, educated assumptions and risk considerations.

## Planning

Planning is done in the tool PCM and can be found there with the identification listed in Table 1.

## Value Analysis and Design to Cost

Will be done in the Engineering Dashboard PV GEN 2.20.10 [4].

## Peer Reviews

The Peer Reviews in this Solution will follow the Document Management Rules [S17]. An overview of mandatory Documents and Reviewer has to be done according to Document List and Review Matrix for engineering projects [S19].

# Development scenario and tailoring of the System Engineering Process

This development process follows the initialisation by Manage Product Policy as described in Project Life Cycle [S16].

Figure 3: Product Line Engineering Process

The project will be conducted following the GTS Management System processes Manage Project (PRJ) and Design, Develop and Qualify the Solution (DDQS) and their interfaces according to Project Life Cycle [S16].

Figure 4: Manage Project (PRJ)

Figure 5: Develop and Qualify the Solution (DDQS)

## Tailoring for this solution (DDQS phases)

### Orient the Solution

No deviation to the description in Project Life Cycle [S16].

### Design the Solution

No deviation to the description in Project Life Cycle [S16].

### Develop the Solution

Preliminary Design Review (PDR) and Critical Design Review (CDR) will be conducted together and relatively late in the development phase. The main activity of the project is integration and test of the new PLF version(s). This Solution requires a stable PLF version (TQR1 quality – see Table 16: Preconditions) to conduct PDR and CDR, therefore date is relatively late in the development phase.

No further deviation to the description in Project Life Cycle [S16].

### Integrate and Verify the Solution

The verification of this Solution (PV GEN 2.20.10) is split up into two steps:

- Integration and Pre-Tests of the ELEKTRA Generic System with TAS PLF 2.6.0 (2.6.0.8): Module tests, generic Subsystem Tests and complete Stability Tests.

- With the final TAS PLF 2.6.1 all (remaining) defined tests will be executed: Module Tests, generic Subsystem Test, complete Stability Test.

For finalization of ELEKTRA Generic System Verification Phase also ELEKTRA Application Integration Tests are required to get the full verification of the ELEKTRA Generic System.

No further deviation to the description in Project Life Cycle [S16].

### Validate the solution

The Assessment Certification according to CENELEC is needed for this product version. No other deviation to the description in Project Life Cycle [S16].

Notice: Assessment will be financed and coordinated by the Safety department.

## Tailoring for Manage Project phases

### Manage Project milestones

The tailoring of the Product Line Engineering (PLE) is used as described in Project Life Cycle [S16]. The Manage Project milestones are replaced by the Manage Product Policy milestones.

- Kick Off replaced by Business Plan Decision Review.

- Launch Review replaced by Development Launch Decision Review, in case the scope of change has no deviation between Development Launch Decision Review and Launch Review.

- Acceptance Review and Closure Review replaced by Deployment Decision Review.

## Tailoring of Documentation Management

The tailoring of the Product Line Engineering (PLE) is used as described in Project Life Cycle [S16].

- The PMP and SEMP is combined in one document PSEMP.

The naming convention for the name “Firstname Lastname” of the author, verified by, approver of a document can also be “F. Lastname”.

No other deviation to the description in Document Management Rules [S17].

## Tailoring of role assignments

### Role of IVVQM

The role IVVQM is not executed by a single person. The major IVVQM activities are distributed to other roles:

- Integration: is made by IVM

- Verification: is made by IVM

- Validation: is made by VAL

- Qualification: is made by VAL (in case of HW development)

### Role of Verifier (VER) according CENELEC EN 50716 and EN 50129

The verification according CENELEC of all documents is performed throw reviews by the roles defined in the Document List and Review Matrix for engineering projects [S19]. The role VER is not executed by a single person. The VER activities are distributed to other roles:

- Process Verification: is made by QAM

- Final document Verification: is made by VER

- Software/Code Verification: is made by domain expert

- Deliverables Verification: is made by IVM

- Enabling systems Verification: is made by CM

- Lifecycle phases Verification: is made by VER

- Collection of Verification results in Verification-report: is made by VER

### Role of DM

The role DM is not executed by a single person. The major DM activities are distributed to other roles:

- new ANV: can be obtained by SEM

- Document Index: is made by CM or SEM

- Formal check at release of a document: is made by QAM

- Other DM activities: are made by author of the document

# System Engineering Support

## Data and Configuration Management

Data and Configuration Management is carried out according to Management System Process CFG - Manage Configuration [S12], Document Management Rules [S17] and the specific Configuration Management plans Configuration Management Plan [10].

## Confidentiality

The rules as listed in Information Classification Standard [S15] apply.

## Export Control

Export Control is carried out according to Management System Process Control Export  [S13].

## Capitalization

Capitalization is handled in the context of the related Manage Product Policy process.

## Measurements and Analysis

See section 4.

## Technical and Non-technical Requirements Management and Control

For Requirement Management the tool DOORS is used. The Requirements Manager ensures that requirements are

uniquely identified

unambiguous, testable and consistent

traced from origin through all systems

have all changes managed

The Requirements Manager manages changes throughout the life of the project. If requirements change, the impact will be reflected in the project plans, work products, and activities. Any inconsistencies between these customer- and/or system requirements and project plans, work products, and activities will be identified and resolved.

## Validation of Requirements

The validation is done in accordance with the Validation Qualification plans as listed in Documentation Plan PV GEN 2.20.10 [1].

## Decision Analysis and Resolution

Decision analysis and resolutions are part of design and review processes. The results are documented in design documents, review reports and in this document.

## Subordinate Plans

There are no subordinate plans.

## Quality Assurance

The Quality Assurance in this Solution will follow Management System Process Guarantee quality and manage continuous improvement [S14]. Additional information can be found in the Quality Management plans as listed in Documentation Plan PV GEN 2.20.10 [1].

## Certification Support Activity

See Safety Management plans as listed in Documentation Plan PV GEN 2.20.10 [1].

## Stakeholder Management

The external Safety Assessor is coordinated by the Safety department.

- Criteria for the Selection of Techniques and Measures

The clauses of this document are associated within this annex to the clause tables (see A.2, Table A.1 to Table A.11) to illustrate the means of achieving conformance. There exist lower level tables as well, the detailed tables (see A.3, Table A.12 to Table A.21), which expand upon certain entries in the clause tables. The detailed tables only apply if the measure or technique was selected within the clause table (e.g., Table A.13 only applies if dynamic testing was selected when applying Table A.6, Table A.6 or Table A.7). There also exists an informative Annex D which is referred to from these tables.

Some techniques or measures appear in more than one table in this annex because they are applicable to more than one lifecycle phase. The recommendation for the usage of the techniques or measures may be different for different lifecycle phases.

With each technique or measure in the tables there is a requirement for each software integrity level. In this version of the document, the requirements for software integrity levels 1 and 2 are the same for each technique. Similarly, each technique has the same requirements at software integrity levels 3 and 4. These requirements can be:

- ‘M’
This symbol means that the use of a technique is mandatory.

- ‘HR’
This symbol means that the technique or measure is Highly Recommended for this safety integrity level. If this technique or measure is not used then the rationale for using alternative techniques shall be detailed in the Software Quality Assurance Plan or in another document referenced by the Software Quality Assurance Plan.

- ‘R’
This symbol means that the technique or measure is Recommended for this safety integrity level. This is a lower level of recommendation than an ‘HR’ and such techniques can be combined to form part of a package.

- ‘--’
This symbol means that the technique or measure has no recommendation for or against being used.

- ‘NR’
This symbol means that the technique or measure is positively Not Recommended for this safety integrity level. If this technique or measure is used then the rationale behind using it shall be detailed in the Software Quality Assurance Plan or in another document referenced by the Software Quality Assurance Plan.

The combination of techniques or measures are to be stated in the Software Quality Assurance Plan or in another document referenced by the Software Quality Assurance Plan with one or more techniques or measures being selected unless the notes attached to the table makes other recommendations. The combination shall conform to approved techniques and measures for all lifecycle phases. If such techniques or combinations of techniques, including all respective mandatory techniques, are used then the Assessor shall accept them as valid and shall only be concerned that the rationale for selecting the techniques and measures is sound and can be justified, then the Assessor may find this acceptable.

Table A.1 Lifecycle Issues and Documentation (5.3) from EN 50716

| DOCUMENTATION | App | SIL 4 | References of Doc Type |
| --- | --- | --- | --- |
| Planning |  |  |  |
| 1. Software Quality Assurance Plan | Yes | HR | QMP |
| 2. Software Planning Verification Report | Yes | HR | Review Reports of the SW planning documents |
| 3. Software Configuration Management Plan | Yes | HR | CMP |
| 4. Software Verification Plan | Yes | HR | IVP |
| 5. Software Validation Plan | Yes | HR | VQP |
| Software requirements |  |  |  |
| 6. Software Requirements Specification | Yes | HR | SSS |
| 7. Overall Software Test Specification | Yes | HR | Test Plan |
| 8. Software Requirements Verification Report | Yes | HR | VoR and review reports of SSS documents |
| Architecture and design |  |  |  |
| 9. Software Architecture Specification | Yes | HR | SSDD |
| 10. Software Design Specification | Yes | HR | SSDD |
| 11. Software Interface Specifications | Yes | HR | SSDD |
| 12. Software Integration Test Specification | Yes | HR | TCS |
| 13. Software/Hardware Integration Test Specification | Yes | HR | TCS |
| 14. Software Architecture and Design Verification Report | Yes | HR | Verification Report |
| Component Design |  |  |  |
| 15. Software Component Design Specification | Yes | HR | SDD |
| 16. Software Component Test Specification | Yes | HR | SSCTR |
| 17. Software Component Design Verification Report | Yes | HR | Verification Report and review reports of design documents |
| Component Implementation and Testing |  |  |  |
| 18. Software Source Code and supporting documentation | Yes | HR | ClearCase, GIT |
| 19. Software Component Test Report | Yes | HR | SSCTR |
| 20. Software Source Code Verification Report | Yes | HR | SSCTR |
| Integration |  |  |  |
| 21. Software Integration Test Report | Yes | HR | Integration Test Report |
| 22. Software/Hardware Integration Test Report | Yes | HR | Integration Test Report |
| 23. Software Integration Verification Report | Yes | HR | Verification Report and review reports of test reports |
| Overall Software Testing / Final Validation |  |  |  |
| 24. Overall Software Test Report | Yes | HR | ∑ Test Reports |
| 25. Software Validation Report | Yes | HR | Validation Report |
| 26. Tools Validation Report | Yes | HR | Tools classification report, handling of TACs in Verification Report |
| 27. Release Note | Yes | HR | VDD |
| Systems configured by application data |  |  |  |
| 28. Application Requirements Specification | No | HR | Not applicable since this is a generic application development. The customization of the application data for a specific application is not part of this development. |
| 29. Application Preparation Plan | No | HR |  |
| 30. Application Test Specification | No | HR |  |
| 31. Application Architecture and Design | No | HR |  |
| 32. Application Preparation Verification Report | No | HR |  |
| 33. Application Test Report | No | HR |  |
| 34. Source Code of Application Data | No | HR |  |
| 35. Application Data Verification Report | No | HR |  |
| 36. Application Integration Test Specification | No | HR |  |
| 37. Application Integration Test Report | No | HR |  |
| 38. Application Release Note | No | HR |  |
| Software deployment |  |  |  |
| 39. Software Deployment Manual | Yes | HR | VDD |
| 40. Deployment Records | Yes | HR | VDD |
| 41. Deployment Verification Report | Yes | HR | Verification Report and review Report of VDD |
| Software maintenance |  |  |  |
| 42. Software Maintenance Plan | Yes | HR | CMP, SoC |
| 43. Software Change Records | Yes | HR | CHARM, DOORS |
| 44. Software Maintenance Records | Yes | HR | CHARM |
| 45. Software Maintenance Verification Report | Yes | HR | PCR Evaluation Report |
| Software assessment |  |  |  |
| 46. Software Assessment Plan | No | HR | Not applicable, External assessment is outside of PV development; therefore, no evidence can be given. |
| 47. Software Assessment Report | Yes | HR | External assessment report if product version will be assessed |
| For basic integrity, the content of the software verification plan can be limited to 6.2.4.9 a), b), c), d), f). For basic integrity the software Interface specification is only highly recommended for the boundary of the overall software (see also 7.3.4.18). |  |  |  |

Table A.2 Software Requirements Specification (7.2) from EN 50716

| TECHNIQUE/MEASURE | App | SIL 4 | Remark |
| --- | --- | --- | --- |
| 1. Modelling | No | HR | Method is not applied. See requirement 2) at the bottom of this table. For this product “structured methodology” is chosen as applied technique. |
| 2. Structured methodology | Yes | HR | Based on requirements tool DOORS |
| 3. Decision Tables | No | HR | Method is not applied. See requirement 2) at the bottom of this table. For this product “structured methodology” is chosen as applied technique. |
| Requirements: 1) The Software Requirements Specification shall include a description of the problem in natural language and any necessary formal or semiformal notation. 2) The table reflects additional requirements for defining the specification clearly and precisely. One or more of these techniques shall be selected to satisfy the Software Integrity Level being used. |  |  |  |

Table A.10 – Software maintenance (9.2) from EN 50716

| TECHNIQUE/MEASURE | App | SIL 4 | Remark |
| --- | --- | --- | --- |
| 1. Impact Analysis | Yes | M | CHARM |
| 2. Data Recording and Analysis | Yes | M | CHARM |

Table E.2 Safety Requirements Specification (from EN 50129)

| TECHNIQUE/MEASURE | App | SIL 4 | References of Doc Type |
| --- | --- | --- | --- |
| 1. Graphical description, e.g. block diagrams | Yes | HR | SSS |
| 2. Structured Specification | Yes | HR | SSS |
| 3. Formal or semiformal specification | No | HR |  |
| 4. Computer aided specification tools | No | R |  |

END OF DOCUMENT

only available in this role till resumption of project DSTW. Deputy will take over this role.

only available in this role till resumption of project DSTW.

only available in this role till resumption of project DSTW.

only available in this role till resumption of project DSTW. Security tasks must be finalized for this project.