SEMP

System Engineering Management Plan

Solution Element

Digital Field Elements

| APPROVAL |  |  |
| --- | --- | --- |
|  | Name and Role/Job Title | Esignature |
| Written by | Bernhard Mandl / SEM DFE |  |
| Verified by | Fabian Rotter / QAM |  |
| Approved by | Erich Stemmer / SEM DIL |  |

| LOG OF CHANGES |  |  |  |
| --- | --- | --- | --- |
| Revision | Date | Author | Change Description |
| 01 | 2025-05-09 | Bernhard Mandl | First Edition |
| 02 | 2025-09-30 | Bernhard Mandl | See chapter 1.5.2 |

Contents

1.	Scope	9

1.1	Identification	10

1.2	System Overview	10

1.3	Key Point	15

1.3.1	Milestones	15

1.3.2	Deliverables	16

1.4	Relation with other Plans	16

1.5	Document Version History	17

1.5.1	Edition 01	17

1.5.2	Edition 02	18

1.6	Open Points	18

2.	References and terms	19

2.1	Referenced Documents	19

2.2	Standards and Procedures	21

2.3	Terms, Abbreviations and Acronyms	23

2.3.1	Role Abbreviations	23

2.3.2	Terms, Abbreviations and Acronyms	23

2.3.3	Abbreviations used in the project:	24

3.	Solution engineering and development process	26

3.1	Organization of Solution Development and Engineering	26

3.1.1	Solution Core Team	26

3.1.2	Solution Team	27

3.1.3	External Project Roles	27

3.1.4	Configuration Control Board	27

3.1.5	Tailoring of role assignments	28

3.2	System Engineering Supplies	29

3.3	Input Data	30

3.4	Preconditions	30

3.5	Related Solutions	31

3.6	Technical Objectives	31

3.7	WBS/OBS and Engineering Work Packages	31

3.8	Training of System Engineering Team	34

3.9	Constraints	35

3.10	Work Contained Phase 1	35

3.10.1	WP3.DEV.3.2.3.1 - IFC ZG62 (HW + SW)	35

3.10.2	WP3.DEV.3.2.3.2 - FES S DCA	35

3.10.3	WP3.DEV.3.2.3.3 - FES M DCA	36

3.10.4	WP3.DEV.3.2.3.4 - FES M AzLM	36

3.10.5	WP3.DEV.3.2.3.5 - FES S IFC LCSI	37

3.11	Work not contained in Phase 1	38

3.12	Work contained in later Phases	38

3.12.1	Phase 2	38

3.12.2	Phase 3	39

3.13	Responsibility Assignment Matrix	39

3.13.1	Types of Involvement	39

3.13.2	Involvements	40

3.13.3	Explanation	40

3.14	Development Approach	40

3.15	Tools and Facilities	41

3.15.1	Project Management	41

3.15.2	Task Management	41

3.15.3	Requirements Management	41

3.15.4	Management Traceability	42

3.15.5	Configuration Management	42

3.15.6	Change Management	42

3.15.7	Documentation Management	43

3.15.8	Documentation Generation	43

3.15.9	Model Driven Engineering	43

3.15.10	Code Building	44

3.15.11	Hardware Engineering Environment	47

3.15.12	IVV Management	47

4.	Process Control	49

4.1	Control of Solution Development	49

4.1.1	Deviation	49

4.1.2	Metrics	49

4.2	Monitoring and Control of System Engineering Activities	49

4.2.1	Periodic Internal Reviews and Meetings	49

4.2.2	Milestone Reviews and Audits	50

4.2.3	Reporting	51

4.3	Critical Technologies	51

4.4	Risk and Opportunities Control	51

4.5	Corrective Action Process	52

4.6	Independent Evaluation and Verification	52

4.7	Estimate/Re-Estimate	52

4.8	Planning	52

4.9	Value Analysis and Design to Cost	52

4.10	Peer Reviews	52

5.	Development Scenario and Tailoring of the System Engineering Process	53

5.1	Orient the Solution	53

5.1.1	Overview	53

5.1.2	Input/Start	53

5.1.3	Activities and Deviations	53

5.1.4	Output	54

5.2	Design the Solution	54

5.2.1	Overview	54

5.2.2	Input/Start	55

5.2.3	Activities and Deviations	55

5.2.4	Output	55

5.3	Develop the Solution	56

5.3.1	Overview	56

5.3.2	Input/Start	56

5.3.3	Activities and Deviations	56

5.3.4	Output	57

5.4	Integrate and Verify the Solution	57

5.4.1	Overview	58

5.4.2	Input/Start	58

5.4.3	Activities and Deviations	58

5.4.4	Output	60

5.5	Validate the solution	60

5.5.1	Overview	60

5.5.2	Input/Start	60

5.5.3	Activities and Deviations	60

5.5.4	Output	62

6.	System Engineering Support	63

6.1	Data and Configuration Management	63

6.2	Confidentiality	63

6.3	Export Control	63

6.4	Capitalization	63

6.5	Measurements and Analysis	63

6.6	Technical and Non-Technical Requirements Management and Control	63

6.7	Validation of Requirements	63

6.8	Decision Analysis and Resolution	63

6.9	Subordinate Plans	64

6.10	Quality Assurance	64

7.	Approach and Criteria used for Tailoring of the System Engineering Process	65

8.	Certification Support Activity	66

9.	Notes	67

Appendix A :	Criteria for the Selection of Techniques and Measures	68

END OF DOCUMENT	73

List of Tables

Table 1 	Solution Identification	10

Table 2 	Security / Maturity Level	10

Table 3	  Milestones Phase 1	15

Table 4	 Deliverables Phase 1	16

Table 5	 Subordinate Planning Documents	17

Table 6	 Referenced Documents	19

Table 7 	Standards and Procedures	21

Table 8 	Role Abbreviations	23

Table 9 	Terms, Abbreviation and Acronyms	23

Table 10 	Abbreviations used in the project	24

Table 11	Core Team Solution Element DFE	26

Table 12	Team	27

Table 13	External Project Roles	27

Table 14	CCB	27

Table 15	Suppliers Input Data	30

Table 16	Preconditions for Phase 1	30

Table 17	Related Solutions	31

Table 18	Technical Objectives	31

Table 19	WBS DFE	33

Table 20	Detailed OBS Solution Team	34

Table 21	Involvements table	40

Table 22	Project Management	41

Table 23	Task Management	41

Table 24	Requirements Management	41

Table 25	Management Traceability	42

Table 26	Configuration Management	42

Table 27	Change Management	42

Table 28	Documentation Management	43

Table 29	Documentation Generation	43

Table 30	Model Driven Engineering	43

Table 31	Hitachi Control - Continuous Build	44

Table 32	Build	44

Table 33	Eclipse Development	44

Table 34	Programming Languages/Compiler	45

Table 35	Elektra Tools	45

Table 36	ETCS Tools	46

Table 37	Legacy Tools	46

Table 38	Internal Used Products	46

Table 39	Development Platform	47

Table 40	HW Engineering Environment	47

Table 41	IVV Management	47

Table 42	Metrics	49

Table 43	Reviews and Meetings	49

Table 44	Milestone Reviews	51

Table 45	Orient the Solution, Activities and Deviations	53

Table 46	Design the Solution, Activities and Deviations	55

Table 47	Develop the Solution, Activities and Deviations	56

Table 48	I&V the Solution, Activities and Deviations	58

Table 49	Validate the Solution, Activities and Deviations	61

List of Figures

Figure 1	Scope Split	9

Figure 2	Solution Overview	9

Figure 3	System Architecture and Solutions	9

Figure 4 	EULYNX System Architecture Baseline 4 Release 4	9

Figure 5	WBS DSTW ÖBB Entwicklung	9

Figure 6	OBS DFE Core Team	9

Figure 7	FES M DCA Schematic	9

Figure 8	FES M AzLM Schematic	9

Figure 9	Orient the Solution	9

Figure 10	Design the Solution	9

Figure 11	Develop the Solution	9

Figure 12	Integrate & Verify the Solution	9

Figure 13	Validate the Solution	9

# Scope

The System Engineering Management Plan (SEMP) describes the Solution Work Plan and Engineering Process as it is to be applied.

It includes a description of the DDQS processes planned to

- Define the system requirements,

- Define the preferred system configuration,

- Satisfy the requirements,

- Provide the planning and control of the technical project tasks,

- Provide management of a totally integrated effort of product engineering including test, logistic, production engineering and to meet cost, schedule and product quality objectives.

## Identification

Table 1 	Solution Identification

| Project: | DSTW ÖBB Entwicklung |
| --- | --- |
| Solution: | 100025795 / ATRELDE91 |
| Solution / System: | Generic Application Digital Interlocking OBB 1.0.0 (GA DIL OBB 1.0.0) |
| Solution Element: | Digital Field Elements (DFE) Phase 1 |
| Identification: | DFE 1.0.0 IFC 1.0.0 |
| Contract: | Digitales Stellwerk DSTW – Rahmenvereinbarung |
| Customer: | ÖBB |
| End User: | ÖBB |
| SI-Level | SIL 4 |

In the following table (Table 2) SL-T is the target security level as required by the customer, SL-C is the capability security level of a particular component.

Table 2 	Security / Maturity Level

| Security Level | SL-T 3, SL-C 3 |
| --- | --- |
| Maturity Level | ML 3 |

## System Overview

For an overview about customer expectation see:

[CRS]  „OBB_RA-DSTW-D1_Leistungsbeschreibung“

The detailed tasks are listed in the document, but in summary it should be noted:

- Development of the new ELEKTRA interlocking generation based on the ÖBB specifications for the digital interlocking solution and new field elements

- Possibly up to 435 interlockings (IxL) virtualized on site of two to three centralized computing centers (incl. geo-redundancy)

- reduction of facilities/buildings needs for the interlocking core and maintenance needs for the field elements by use of virtualization and object controllers,

- address the European standardization efforts of railway operators, known as the “EULYNX initiative”,

- cyber security on base of the IEC 62443, TS50701 and EULYNX BL 4, tackling the upcoming NIS2 directive and changed cyber threat situation

- Enabling roll-out projects

- Setting up a service infrastructure

- Overall integration of the interlocking solution into the ÖBB infrastructure

Figure 1	Scope Split

For more information about used products see [PBS]. The PBS distinguishes between:

- Make  Developed within Hitachi Austria

- Team  Developed within Hitachi Rail Ltd.

- Buy  Developed by 3rd party

Therefore, the categorization between externally provided components and custom developed components from third-party suppliers according to the IEC 62443-4-1 .

For clarification on Figure 1 the Lightpoints will be integrated and delivered with the rollout, however a new development is NOT included in the project scope.

The project Generic Application Digital Interlocking OBB 1.0.0 (GA DIL OBB 1.0.0) is divided into three Solution Elements (see Figure 2).

Figure 2	Solution Overview

Figure 3	System Architecture and Solutions

This document describes the Solution Element Digital Field Elements in detail. This involves the implementation of EULYNX-compliant hardware, whereby the field elements:

- Subsystem - Point

- Subsystem - Light Signal

- Subsystem - Generic I/O  general purpose IO, used for IO based elements that are not specified in EULYNX (e.g. key locks)

- Subsystem - Train Detection System

- Subsystem - External Level Crossing System

are integrated with the digital interlocking core unit (EULYNX component EIL – Electronic Interlocking) via the Interface SCI and controlled via Object Controllers located in Field Element Stations.

Figure 4 	EULYNX System Architecture Baseline 4 Release 4

Additionally, Interface Converters (e.g. ZG62, Sbl60, Figure 3) to connect neighbor blocks are implemented in own cabinets, including hardware and software development. These converters are logically not part of the Digital Field Elements, but are nevertheless handled and developed in the Solution Element Digital Field Elements.

The development will be split in three Phases (see Chapter 3.10). In Phase 1, following Field Element Stations are developed:

- FES S (Small) DCA

- FES M (Medium) DCA

- FES M (Medium) AzLM

- IFC ZG62

- Support external supplier (Mission Embedded ME) for LCSI development

For more details regarding the different stations, see Chapter 3.7. Additionally, support for LCSI Gateway (delivered by external company Mission Embedded) starts in Phase 1 due to long timeline, even though the development and integration in a field element station is part of phase 2.

## Key Point

### Milestones

Since the delivery items are the stations, the milestones were divided according to the individual stations.

Table 3		 Milestones Phase 1

| Milestone | Target Date |
| --- | --- |
| Solution Orientation Review (SOR-1) | 4.4.2025 |
| Solution Orientation Review (SOR-2) | T0 + 1 month |
| Solution Requirement Review (SRR-1) | 30.09.2025 |
| Solution Requirement Review (SRR-2) | MS E03 + 3 months |
| Solution Functional Review (SFR-1) | 26.01.2026 |
| Solution Functional Review (SFR-2) | MS E036 + 5 months |
| Preliminary Design Review (PDR) | 11.09.2026 |
| Critical Design Review (CDR) | 26.01.2027 |
| Test Readiness Review (TRR1) FES M AzLM | 01.02.2027 |
| Technical Qualification Review (TQR1) FES M AzLM | 08.10.2027 |
| Test Readiness Review (TRR1) FES M DCA | 11.05.2027 |
| Technical Qualification Review (TQR1) FES M DCA | 10.01.2028 |
| Test Readiness Review (TRR1) FES S DCA | 15.07.2027 |
| Technical Qualification Review (TQR1) FES S DCA | 17.01.2028 |
| Test Readiness Review (TRR1) IFC ZG62 HW | 15.07.2027 |
| Test Readiness Review (TRR1) IFC ZG62 SW | 14.05.2027 |
| Technical Qualification Review (TQR1) IFC ZG62 HW + SW | 07.02.2028 |
| Technical Qualification Review (TQR2) | 15.03.2028 |
| Final Qualification Review (FQR) | 15.05.2028 |

All dates are under the assumption of a contract signature by end of 2025 (=T0). The milestones are related to the content of Phase 1 as included in the offer submitted to ÖBB in September 2025 (see Work contained in Chapter 3.10).

### Deliverables

Table 4		Deliverables Phase 1

| Deliverable | Completion Date | Customer |
| --- | --- | --- |
| Developed and qualified FES M AzLM (AzLM version 7.10 with EULYNX BL4R4) DFE 1.0.0 | 08.10.2027 | Generic Application Digital Interlocking OBB 1.0.0 (GA DIL OBB 1.0.0) |
| Developed and qualified FES M DCA3.x (with EULYNX BL4R4) DFE 1.0.0 | 10.01.2028 | Generic Application Digital Interlocking OBB 1.0.0 (GA DIL OBB 1.0.0) |
| Developed and qualified FES S DCA3.x (with EULYNX BL4R4) DFE 1.0.0 | 17.01.2028 | Generic Application Digital Interlocking OBB 1.0.0 (GA DIL OBB 1.0.0) |
| Developed and qualified IFC ZG62 within a shelf (HW + SW) IFC 1.0.0 | 07.02.2028 | Generic Application Digital Interlocking OBB 1.0.0 (GA DIL OBB 1.0.0) |
| Prototype of LCSI Gateway DFE 1.0.0 | 01.10.2027 | Generic Application Digital Interlocking OBB 1.0.0 (GA DIL OBB 1.0.0) |

## Relation with other Plans

The SEMP describes the application of the Management System Solutions Engineering Processes (DDQS) to the design, development and deployment of the Solution Digital Field Elements.

This document will be updated as the Solution effort evolves.

A general overview of the Solution Element documents hierarchy and the baseline associated with each level of specification is shown in Configuration Management Plan.

Table 5		Subordinate Planning Documents

| Title | Description | Ref. |
| --- | --- | --- |
| Project Management Plan | Focuses on the Management System including organization, policies and plans that are carried out by Thales Austria in relation to the Project. | [PMP] |
| Configuration Management Plan | Provides details of the formal Configuration Management process. | [CMP_GEN], [CMP_HW] |
| Quality Management Plan | Describes requirements for all quality assurance measures and quality assurance activities to be carried out in the solution as contribution to the fulfilment of the project goals. | [QMP] |
| RAM Plan | Provides details of the tasks and activities about Reliability, Availability and Maintainability of the Solution. One Plan for Generic Application and one plan for Solution Element DFE. | [RAMP_DFE] |
| Safety Plan | Provides details of the tasks and activities of Solution safety management and Solution safety engineering required to identify, evaluate and eliminate or control hazards throughout the life cycle. Reference to Generic Safety Plan and Project Specific Plan | [SP] |
| Integration and Verification Plan | Is the general overview how it is planned to manage and test the Generic Application with the three Solution Elements. The generic IVP and a project specific plan following the ÖBB requirements is provided | [IVP] |
| Validation and Qualification Plan | Is the general overview how it is planned to manage and validate the Generic Application with the three Solution Elements. The generic VQP and a project specific plan following the ÖBB requirements is provided | [VQP] |
| Security Management Plan | Is the general overview how it is planned to address the security aspects in the Generic Application with the three Solution Elements. The generic SecMP and a project specific plan following the ÖBB requirements is provided | [SecMP] |
| Industrialization and Purchasing Plan DFE – Phase 1 | Is the general overview how it is planned to industrialize and purchase relevant parts and components for the Solution Element Digital Field Elements for Phase 1 | [IPP] |
| Test Plan | Is the overview of the planned test activities of the Digital Field Elements in Phase 1 | [Test Plan] |

## Document Version History

### Edition 01

First Release

### Edition 02

Document updates in regards to DFE related changes according to the 4th Edition of the offer placed to ÖBB at 12th of September 2025. These changes in regards to DFE are:

- X25 to X25oRaSTA Converter cancelled

- Converter Zustimmung cancelled

- EPD Box excluded

- Retrofit cancelled

Additionally, milestones, WBS/OBS and the according work package descriptions have been updated.

## Open Points

IFC ZG62:

- Check whether the security requirements are met with TAS Platform 2.5.2, as it is actually currently running on the Compute Board SCA. Since the self-developed SEC/SEA implementation is running on the Computing Board, an update of the TAS Platform is possible if necessary.

# References and terms

## Referenced Documents

Table 6		Referenced Documents

|  | Nr. /Title | Reference | Version |
| --- | --- | --- | --- |
| [CMP_GEN] | Configuration Management Plan – Generic | 3BU 15000 3338 QMAPA | 11RL |
| [CMP_HW] | Configuration Management Plan – Hardware Generic | 3BU 15000 8006 QMAPA | 02RL |
| [CRS] | DSTW Streckenausrüstung OBB - Teil D Leistungsbeschreibung und Lastenhefte | 3BU 17300 0004 DSAPC | 04RL |
| [CRS_Light Signals] | DSTW Streckenausrüstung OBB - Teil E Mitgeltende Dokumente [715] LH Signalgeber DSTW V1.0 | 3BU 17300 0005 DSAPC | 04RL |
| [DoP] | Documentation Plan / PVR Solution Element – DFE Phase 1 | 3BU 62800 0000 ADAPA | 01PD03 |
| [DVa] | Design Validation approval (DVa) | OeBB_Bid_DVa.docx extended with updates and details from “Digitales Stellwerk - Technische Konzepte” 3BU 17300 0010 DSAPC | 12 04RL |
| [EngDB] | Engineering Dashboard (sharepoint) | 100025795_ATRELDE91_DSTW-ÖBB-Entwicklung_DFE_202503.xlsm | Latest |
| [IMP] | Integrated Master Schedule | Eng_Master_Schedule in SharePoint | Latest |
| [IPP] | Industrialization and Purchasing Plan - DFE Phase 1 | 3BU 62800 0050 MCAPA | 01PD02 |
| [IVP] | Project Specific Integration and Verification Plan (IVP) | 3BU 17300 1206 DUAPC | 01RL |
| [MS-Report] | Milestone Report Solution | 3BU 62800 0002 ADAPA | Latest |
| [OBB_RA-DSTW] | OBB_RA-DSTW-D1_Leistungsbeschreibung | 3BU 17300 0004 DSAPC | 04RL |
| [PBS] | Product Breakdown Structure | 3BU 17300 1215 DPAPA | 02RL |
| [PMP] | Project Management Plan | 3BU 17300 1000 DPAPC | 01PD02 |
| [QMP] | Quality Management Plan ELEKTRA | 3BU 17300 1202 QMAPC | at SOR-2 |
| [RAMP_DFE] | RAM Plan DFE | 3BU 62800 0018 DUAPA | 02RL |
| [RiskReport] | Risk Report | 100025795_ATRELDE91-E0_DSTW_ÖBB_Entwicklung_Risk_List_20250930_ED02.xlsx | 02RL |
| [RMP] | Requirements Management Plan (RMP) Generic Application Digital Interlocking OBB | 3BU 17300 1207 DUAPA | 01RL |
| [SaCo] | Sicherheitskonzept, ELEKTRA Safety Concept - Two Diverse SW Channels on a Redundant Platform Safety Concept Elektra 4 Communication Safety concept DIL | 3BU 15000 0622 DUAPC 3BU 15000 6957 DUAPA 3BU 15000 6956 DUAPA 3BU 17300 1212 DUAPC | 04RL 01PD02 01PD05 at SRR |
| [SecMP] | Project Specific Security Management Plan (SecMP) | 3BU 17300 1213 DPAPA | 01PD02 |
| [SEMP_DIL] | System Engineering Management Plan Generic Application – Digital Interlocking OBB | 3BU 17300 1200 DPAPA | 02PD01 |
| [SEMP_IPSS] | System Engineering Management Plan Solution Element IPSS | 3BU 17300 2001 DPAPA | 01PD02 |
| [SEMP_VIL] | System Engineering Management Plan Solution Element Virtual Interlocking | 3BU 15000 6955 DPAPA | 01PD01 |
| [SP] | Safety Plan DSTW | 3BU 17300 1204 DUAPA | 01RL |
| [Test Plan] | Test Plan - DFE Phase 1 | 3BU 62800 0100 QTAPA | 01RL |
| [ToolClass] | Hitachi Austria Tool Classification EN50129 | 3BU 15000 5135 190EN | Latest |
| [ToolClassSW] | Software Development, Tool Classification, EN 50128 | 3BU 15000 5135 AAAPA | Latest |
| [VQP] | Project Specific Validation and Qualification Plan (VQP) | 3BU 17300 1205 DUAPA | 01RL |
| [WBS/OBS] | WBS/OBS Solution Element Digital Field Elements | 3BU 62800 0013 BCAPA | 02RL |
| [Estimation Sheet_DSTW_HW] | Estimation Sheet DSTW Hardware | 3BU 00603 0149 BEAPA | 06RL |
| [Estimation Sheet_DSTW_NIC_SW] | Estimation Sheet DSTW Software / NIC | 3BU 00603 0214 BEAPA | 02RL |

## Standards and Procedures

Table 7 	Standards and Procedures

| Nr./Title | Publishing Date/ Reference | Version/ Revision |
| --- | --- | --- |
| - IRIS Certification rules:2020 based on ISO/TS 22163:2017 | 2017 | n/a |
| - EN 50716:2023 – Railway application – Requirements for software development | 2023 | n/a |
| - EN 50129:2018 + AC:2019 Railway applications – Communication, signalling and processing systems – Safety related electronic systems for signalling | 2018/2019 | n/a |
| - ISO 9001 | 2015 | n/a |
| - EN 50126-1:2017 – Railway Applications – The Specification and Demonstration of Reliability, Availability, Maintainability and Safety (RAMS) – Part 1: Generic RAMS Process | 2017 | n/a |
| - EN 50126-2:2017 – Railway Applications – The Specification and Demonstration of Reliability, Availability, Maintainability and Safety (RAMS) – Part 2: Systems Approach to Safety | 2017 | n/a |
| - Management System Process Manage Risks and Opportunities | Part of 87200984-00-PRJ-GRP-EN (Chapter 8.6) | 2025-01 |
| - Management System Process Manage Project | 87200984-00-PRJ-GRP-EN | 2025-01 |
| - Minimum Requirements for the configuration management implementation | Part of 87100077-CFG-GRP | 007 |
| - Management System Process 6.1 DDQS-SW - Design develop and qualify the Software solution | Part of 87202125-00-DDQ-GRP-EN | 2025-01 |
| - Management System Process 6.1 DDQS-HW - Design develop and qualify the Hardware solution | Part of 87202126-00-DDQ-GRP-EN | 2025-01 |
| - Management System Process Validate the Solution | Part of 87202127-00-DDQ-GRP-EN | 2025-01 |
| - Management System Process Integrate and Verify the Solution | Part of 87202127-00-DDQ-GRP-EN | 2025-01 |
| - Management System Process Orient the Solution | Part of 87202127-00-DDQ-GRP-EN | 2025-01 |
| - Management System Process Design the Solution | Part of 87202127-00-DDQ-GRP-EN | 2025-01 |
| - Management System Process Develop the Solution | Part of 87202127-00-DDQ-GRP-EN | 2025-01 |
| - Management System Process 9.7 CFG - Manage Configuration | 87202424-00-CFG-GRP-EN | 2025-01 |
| - Management System Process 9.3 Control Export | 87299999-00-EXP-GRP-EN | 2025-01 |
| - Management System Guarantee quality and manage continuous improvement | 87200214-00-QCI-GRP-EN | 2025-01 |
| - Protection of Group Information | 87201725-GOV-GRP-EN | 005 |
| - Personal Data Protection Policy | 87212828-GOV-GRP-EN | 001 |
| - Project Life Cycle | 83530275-DDQ-AUT-EN | 005 |
| - Document Management Rules | 83530061-DOC-AUT-EN | 013 |
| - Milestone Template Solutions | 83530019-DDQ-AUT-EN | 012 |
| - Document List and Review Matrix for engineering projects | 83530224-DOC-AUT-EN | 010 |
| - HSE Instruction | 83530048-HSE-AUT-DE | 020 |
| - Agile Definition SMP | 83530312-DDQ-AUT-EN | 002 |
| - ISA/IEC 62443-3-3 Industrial communication networks - Network and system security, Part 3-3: System security requirements and security levels, Edition 1, 09 2013 | 2013 | 01 |
| - ISA/IEC 62443-4-1 - Security for industrial automation and control systems, Part 4-1: Secure product development lifecycle requirements, Edition 1, 01 2018 | 2018 | 01 |
| - ISA/IEC 62443-4-2 - Security for industrial automation and control systems, Part 4-2: Technical security requirements for IACS components, Edition 1, 04 2019 | 2019 | 01 |
| - EN 50159:2010, + A1:2020 Railway applications – Communication, signalling and processing systems – Safety-related communication in closed transmission systems | 2020 | n/a |
| - CLC/TS 50701:2023 – Technical Specification: Railway Applications – Cybersecurity | 2023 | 2023-10 |
| - MLS Security Engineering Instruction | 83559080-DDQ-DEU-EN | 002 |

## Terms, Abbreviations and Acronyms

### Role Abbreviations

Table 8 	Role Abbreviations

| APM | Acquisition Project Manager |
| --- | --- |
| ARC | Architect |
| ATS | Acquisition Technical Support |
| CHARM | Change and Request Management |
| CM | Configuration Manager |
| DM | Document Manager |
| DPM | Data Preparation Manager |
| HwEM | Hardware Engineering Manager |
| IM | Industrial Manager |
| IVM | Integration and Verification Manager |
| IVVQM | Integration, Verification, Validation and Qualification Manager |
| PDA | Project Design Authority |
| PLM | Product Line Manager |
| PM | Project Manager |
| PPTM | Production Process and Technology Manager |
| PSM | Project Security Manager |
| QAM | Quality Assurance Manager |
| RAM-AM | Reliability, Availability, Maintainability Assurance Manager |
| RM | Requirements Manager |
| SAM | Safety Assurance Manager |
| SecAM | Security Assurance Manager |
| SEM | System Engineering Manager |
| SpE | Specialty Engineer |
| SVEM | Service Engineering Manager |
| SwEM | Software Engineering Manager |
| TM | Test Manager |
| VAL | Validator |
| VER | Verifier |
| WPM | Work Package Manager |

### Terms, Abbreviations and Acronyms

Table 9 	Terms, Abbreviation and Acronyms

| App | Applicable |
| --- | --- |
| CENELEC | European Committee for Electrotechnical Standardization |
| CCB | Configuration Control Board |
| CDR | Critical Design Review |
| CMP | Configuration Management Plan |
| DDQS | Design, Develop and Qualify the Solution |
| DWF | Document Web Frontend |
| ECM | Enterprise Content Management |
| FCA | Functional Configuration Audit |
| FQR | Final Qualification Review |
| ILS | Integrated Logistic Support |
| IVV | Integration, Verification and Validation |
| I&V | Integration and Verification |
| KOM | Kick of Meeting |
| LUT | Label Unit Tracking |
| M | Mandatory |
| NA | Not applicable |
| O | Optional |
| PCA | Physical Configuration Audit) |
| PCB | Printed Circuit Board |
| PCM | Primavera Core Model |
| PDR | Preliminary Design Review |
| PMP | Project Management Plan |
| QMP | Quality Management Plan |
| RAM | Reliability, Availability and Maintainability |
| RJC | Reuseable Java Components |
| SE | Solution Element |
| SEMP | System Engineering Management Plan |
| SFR | Solution Functional Review |
| SOR | Solution Orientation Review |
| SRR | Solution Requirement Review |
| SubIT | Subsystem Integration Test |
| SW | Software |
| T | Tailoring |
| TM | Test Manager |
| TQR | Technical Qualification Review |
| TRN | Thales Record Number |
| TRR | Test Readiness Review |
| VA | Validation |
| WBS | Work Breakdown Structure |
| WP | Work Package |
| WPM | Work Package Manager |

### Abbreviations used in the project:

Table 10 	Abbreviations used in the project

| AzLM | Multi Section Axel Counter (one type of TDS) |
| --- | --- |
| BI | Basic Integrity |
| CFI | Customer Furnished Item |
| DCA | Distributed Controller Architecture |
| DDSP | Daten Diagnose Service Plattform (CFI ÖBB) |
| DFE | Digital Field Elements |
| DGP | Diagnosis Processor (ELEKTRA) |
| DIL | Digital Interlocking = DSTW |
| DSTW | Digitales Stellwerk = DIL |
| DSTW-ZE | Digitales Stellwerk Zentraleinheit = EIL |
| ECMUX | Element Controller MultipleXer |
| EIL | Electronic Interlocking System according to EULYNX – equals to DSTW-ZE |
| EKSA | Eisenbahnkreuzungssicherungsanlage = LCSI (CFI ÖBB) |
| EULYNX | European Initiative to Linking Interlocking Systems |
| FES | Field Element Station |
| IEC | International Electrotechnical Commission |
| IFB | Interface Board |
| IFC | Interface Converter |
| GA DIL OBB | Generic Application Digital Interlocking ÖBB |
| IPS | Integrated Platform Services |
| IPSS | IPS Solution Element |
| LCSI | Level Crossing Safety Installation = EKSA |
| LX | EULYNX External Level Crossing |
| MDM | EULYNX, Maintenance and Data Management (CFI) |
| OBB | Oesterreichische Bundes Bahn (Austrian Railway Operator, ÖBB) |
| OC | Object Controller |
| OMC | Operation Management Center = BFZ (Betriebsführungszentrale) |
| RaSTA | Rail Safe Transport Application (safety protocol for railway signalling systems) |
| RBC | Radio Block Center (CFI ÖBB) |
| SCI | Standard Communication Interface (EULYNX interface for process data information) |
| SCWS | Signal Controlled Warning System |
| SDI | Standard Diagnostic Interface (EULYNX interface for diagnostics) |
| SiDiNet | SicherungsDienstNetzwerk (CFI ÖBB) |
| SMI | Standard Maintenance Interface (EULYNX interface for maintenance) |
| Solution | A consistent set of systems, equipment and services provided to the Customer to meet a specific requirement |
| Solution Element | A system, a sub-system, a product / equipment, or a service, a software component, a hardware component |
| SSI | Standard Security Interface (EULYNX interface for security) |
| SSP | Security Services Platform (CFI ÖBB) |
| TDS | Train detection system |
| VIL | Virtual Interlocking |
| VSTW | Virtuelles Stellwerk = VIL |

# Solution engineering and development process

The Solution will be conducted according to Hitachi Rail GTS Austria Management System. The Management System version valid at the start of the Solution is 2025-01.

As the Management System is continuously improving, it has to be mentioned, that in the devolution of the Solution, the respectively valid Templates have to be used according to the up-to-date version.

If Template changes are done, the document will only be adapted if they need to be revised anyway.

## Organization of Solution Development and Engineering

The description of the roles mentioned below can be found on the Management System Portal.

### Solution Core Team

Table 11	Core Team Solution Element DFE

| Role | Resource | Deputy Resource |
| --- | --- | --- |
| IVM | NN |  |
| PDA HW | A. Haunschmied | D. Baumgartner |
| PDA SW | R. Mittermayr | K. Aichner |
| PLM | R. Holzknecht | M. Dum |
| PSM HW | S. Peternel |  |
| PSM SW | T. Fischer |  |
| QAM | F. Rotter | A. Haslinger |
| RM | G. Eber | I. Miler |
| SAM HW | M. Pohl | C. Sünder |
| SAM SW | R. Büger | C. Sünder |
| SEM | B. Mandl | M. Goldenits |
| SEM Generic Application DIL | E. Stemmer | M. Gartner-Pohl |
| VAL HW | I. Grgic | M. Pohl |
| VAL SW | W. Luef |  |
| VER HW*) | H. Iqbal |  |
| VER SW*) | H. Walenta |  |
| WPM FES M AzLM | B. Mandl | M. Goldenits |
| WPM FES M DCA | B. Mandl | M. Goldenits |
| WPM FES S DCA | B. Mandl | M. Goldenits |
| WPM FES S IFC LCSI | B. Mandl | M. Goldenits |
| WPM ZG62 HW | B. Mandl | M. Goldenits |
| WPM ZG62 SW | K. Aichner | R. Rambo |

*) For more detailed description regarding the role of HW VER, see chapter 3.1.5.2.

### Solution Team

Table 12	Team

| Role | Resource | Deputy Resource |
| --- | --- | --- |
| ARC HW | E. Brenner | A. Haunschmied |
| ARC SW | K. Aichner | R. Mittermayr |
| DM | See chapter 3.1.5.3 | n/a |
| CM HW | D. Baumgartner |  |
| CM SW | K. Aichner |  |
| RAM-AM | F. Moser | M. Scheuer |
| SecAM | A. Willenberg |  |
| IM | R. Ratz |  |
| Test Manager HW | H. Schneider |  |
| Tester HW | See Table 20 |  |
| Tester SW | See Table 20 |  |

### External Project Roles

Table 13	External Project Roles

| Role | Resource | Deputy Resource |
| --- | --- | --- |
| Safety Assessor | Arsenal Race | n/a |
| Security Assessor* | tbd | tbd |
| Tester (EMC) | Bluetechnix Lab GmbH (EMC Vienna) | n/a |
| Tester (Shock, Vibration, Thermal) | RST LABS - Rail System Testing GmbH | n/a |
| Developer | Mission Embedded GmbH | n/a |

*) Nomination of Security Assessor still open

### Configuration Control Board

Table 14	CCB

| Role | Resource | Comment | M/O |
| --- | --- | --- | --- |
| PLM | See Table 11 |  | M |
| PM | See Table 11 |  | M |
| PSM | See Table 11 |  | M |
| SEM | See Table 11 |  | M |
| PDA | See Table 11 |  | M |
| SAM | See Table 11 |  | M |
| WPM | See Table 11 |  | M |
| QAM | See Table 11 |  | M |
| CM | See Table 11 |  | O |
| IVVQM | See Table 11 |  | O |
| IM | See Table 12 |  | O |
| VAL | See Table 11 |  | M |
| VER | See Table 11 |  | M |

Other project team members are invited to the CCB as needed.

### Tailoring of role assignments

#### Role of IVVQM

The role IVVQM is not executed by a single person. The major IVVQM activities are distributed to other roles:

- Integration: is made by IVM

- Verification: is made by IVM

- Validation: is made by VAL

- Qualification: is made by VAL (in case of HW development)

#### Role of Verifier (VER) according CENELEC EN 50716 and EN 50129

The verification according CENELEC of all documents is performed through reviews by the roles defined in the Document List and Review Matrix for engineering projects [S25]. The role VER is not executed by a single person. The VER activities are distributed to other roles:

- Process Verification: is made by QAM

- Final document Verification: is made by RM

- Software/Code Verification: is made by an Independent Designer

- HW (Design) Verification: is made by HW VER

- Deliverables Verification: is made by IVM

- Enabling systems Verification: is made by CM

- Lifecycle phases Verification: is made by VER

- Collection of Verification results in Verification-report: is made by VER

The Verifier according to EN 50129 is equivalent to the Tester of EN 50716. Therefore, the HW verification tasks are handled by a tester.

The HW Design Verification is done by a dedicated role HW VER who is not involved in design, test and validation activities. The HW VER performs the documentation verification based on the basic questionnaire and creates a verification report as summary of the tests performed as well as the open defects resulting from them.

#### Role of DM

The role DM is not executed by a single person. The major DM activities are distributed to other roles:

- new ANV: can be obtained by SEM

- Document Index: is made by CM or SEM

- Formal check at release of a document: is made by QAM

- Other DM activities: are made by author of the document

## System Engineering Supplies

For detailed description of used or purchased products, see [PBS].

The FES in phase 1 are available in 3 different versions + the outdoor elements:

- FES S DCA + FES M DCA  supporting up to 2 Object Controller (S) and 10 Object Controller (M)

  - Housekeeping SPS

  - Lighting/Access Control

  - DCA-P 3.1.0

    - Interface Control Unit Point - ICB-P HW 3.0

  - DCA-LS 3.1.0

    - Interface Control Unit Output – ICB-O2

    - Interface Control Unit Light Signal – ICB-LS

  - DCA-I/O 3.1.0

    - Interface Control Unit Input/Output High Power – ICB I/O HP

    - Interface Control Unit Input – ICB-I2

  - ICB Carrier Boards

    - Carrier 19 Inch for 4 ICB

    - Carrier 19 inch for 2 ICB (Left)

    - Carrier 19 inch for 2 ICB

- FES M AzLM  supporting TDS

  - Housekeeping SPS

  - Lighting/Access Control

  - Object Controller Module

    - AzLM v7.10

Outdoor Elements:

- Station Key Lock

- Line Key Lock

- Local Control Post

- iLED

- iAnzeiger

- AzLM Outdoor

Additionally, for phase 1, the IFC Cabinets include:

- IFC ZG62 1.0

  - Computing Board SCA

  - DCA 2.x IOC

  - Relay Group

For the LCSI-Gateway, in phase 1 only a prototype will be provided for first tests.

## Input Data

The following table shows all necessary input versions on which Solution Element DFE is based.

Table 15	Suppliers Input Data

| Item | Version | Provider |
| --- | --- | --- |
| AzLM | 7.10 | Hitachi Rail Germany |
| DCA for IFC DCA for DFE | 2.x 3.1.x | Hitachi Rail Spain (SW) + Germany (HW) |
| Computing Board SCA | 06 | Hitachi Rail Austria |
| TAS Platform for DCA 3.x TAS Platform for AzLM IFB for DCA 2.x TAS Platform for SCA | 2.6 2.6 Platform IFB 2.5.2 | Hitachi Rail Austria |
| J4S | 3.1.0 | Hitachi Rail Austria |
| RCJ Core RJC RaSTA | 1.1.0 2.0.0 | Hitachi Rail Austria |

## Preconditions

Table 16 lists all subsequent delivery versions on which the solution and development process/schedule depend.

Table 16	Preconditions for Phase 1

| Deliverable | Completion Date | Provider |
| --- | --- | --- |
| AzLM 7.10 (new subrack HW, not SW feature complete, but HW ready for qualification)* | 12/2026 (TRR-A Positive Assessment Report) | Hitachi Rail Germany |
| DCA 3.x Release 1 **) | 10/2026 | Hitachi Rail Spain |
| LCSI-Gateway 1st Prototype | 10/2027 | Mission Embedded |

*) SMI Feature – no download, SDI – partially filling of OPC-UA, EULYNX BL4.4 valid release (but not all data fields), new HW and subrack Prototype will be available for Integration tests

**) New ICB HW to be expected until End of 2027  need to match with TRR1 FES M DCA

## Related Solutions

Table 17	Related Solutions

| Project / Solution | Solution Element | Responsibility |
| --- | --- | --- |
| Project DSTW ÖBB Entwicklung | Generic Application Digital Interlocking (GA DIL OBB 1.0.0) | E. Stemmer (SEM) |
| Solution Element | Solution Element Virtual Interlocking (VIL OBB 1.0.0) | P. Bargiel (SEM) |
| Solution Element | Solution Element IPS Solution (IPSS OBB 1.0.0) | V. Vasilev (SEM) |

## Technical Objectives

Goal of the project Generic Application Digital Interlocking (GA DIL OBB 1.0.0) is to reduce buildings and hardware costs through virtualization of interlockings. Due to the high complexity of the project a 3-Phase approach for the development is defined (see [SEMP_DIL] chapter 3.9.1). This document is focusing on Phase 1.

The DFE Solution Element provides stations or cabinets that ensure EULYNX-compliant controlling and communication between the virtual interlockings and the field elements or legacy interlockings. The communication itself is done via so called Object Controllers (OC) located in the Field Element Stations. In Table 18 the dependencies between the subcomponents and the different stations is shown. For more information about used products see [PBS].

Table 18	Technical Objectives

| FES S+M DCA (DFE 1.0.0) | FES M AzLM (DFE 1.0.0) | IFC ZG62 (IFC 1.0.0) | LCSI-Gateway 1.0* |
| --- | --- | --- | --- |
| DCA 3.x Release 1 for Phase 1 (New ICB HW to be expected until End of 2027) TAS Platform 2.6.x | AzLM 7.10 (new subrack HW, not SW feature complete for Q-Test with fixed HW TAS Platform 2.6.x | Computing Board SCA TAS Platform 2.5.2**) | 1st Prototype |
|  |  | DCA 2.x IOC Platform IFB |  |
|  |  | J4S 3.1.0 |  |

*) In phase 2 the LCSI-Gateway will be integrated in a FES S

**) Check if required Security features included in TAS Platform 2.5.2 or if update necessary is open (see 1.6)

## WBS/OBS and Engineering Work Packages

The WBS for the Project DSTW ÖBB Entwicklung is shown in Figure 5 (see also [WBS/OBS]).

Figure 5	WBS DSTW ÖBB Entwicklung

Due to the high variance and complexity of the hardware, a WBS is selected to ensure compliance with the master plan. Therefore, it was advisable to structure the work packages in such a way that self-contained deliverables could be achieved.

The breakdown of the work packages shown is based on the FES size (number of object controllers) and the technology used for the object controllers or interface converters.

Station size S will be equipped exclusively with OCs consisting of DCA 3.x units. Station size M will be equipped with DCA 3.x units and AzLM units for the TDS.

The interface converter for ZG62 will be equipped with SCA and DCA 2.x for communication with neighboring interlockings.

This WBS enables independent qualification/approval of the respective deliverables and thus optimization of the schedule as needed.

Table 19 shows the Workpackages for the Solution Element DFE. For DFE see [WBS/OBS].

Table 19	WBS DFE

| WP ID | WP Name | WP Manager | WP Management Approach |
| --- | --- | --- | --- |
| WP3.DEV.3.2.3.1 | IFC ZG62 (HW + SW) | B. Mandl HW / K. Aichner SW | Managed as WP |
| WP3.DEV.3.2.3.2 | FES S DCA | B. Mandl | Managed as WP |
| WP3.DEV.3.2.3.3 | FES M DCA | B. Mandl | Managed as WP |
| WP3.DEV.3.2.3.4 | FES M AzLM | B. Mandl | Managed as WP |
| WP3.DEV.3.2.3.5 | FES S IFC LCSI | B. Mandl | Managed as WP |

Figure 6	OBS DFE Core Team

The Figure above shows the Top-Level OBS for the Solution Element DFE. For a more detailed view, see [WBS/OBS]. More detailed information about the work packages is also shown in Table 20.

Table 20	Detailed OBS Solution Team

|  | WP3 DEV.3.2.3.1 IFC ZG62 (HW + SW) | WP3 DEV.3.2.3.2 FES S DCA | WP3 DEV.3.2.3.3 FES M DCA | WP3 DEV.3.2.3.4 FES M AzLM | WP3 DEV.3.2.3.5 FES S IFC LCSI |
| --- | --- | --- | --- | --- | --- |
| WPM | B. Mandl HW K. Aichner SW | B. Mandl | B. Mandl | B. Mandl | B. Mandl |
| System Architect | E. Brenner HW K. Aichner SW | E. Brenner | E. Brenner | E. Brenner | E. Brenner |
| Designer 1 HW | A. Böhm | A. Böhm | A. Böhm | R. Hanel | J. Reuter |
| Designer 2 HW | J. Reuter | R. Altermann | R. Altermann | A. Haunschmied | A. Haunschmied |
| Designer 3 HW | L. Strehn | J. Reuter | J. Reuter | E. Hamp | L. Strehn |
| Designer 4 HW | A. Haunschmied | A. Haunschmied | A. Haunschmied |  | E. Hamp |
| Designer 5 HW | E. Hamp | E. Hamp | E. Hamp |  |  |
| Designer 6 HW |  | L. Strehn | L. Strehn |  |  |
| Testmanager HW | H. Schneider | H. Schneider | H. Schneider | H. Schneider | H. Schneider |
| Tester 1 HW | NN | NN | NN | NN | NN |
| Tester 2 HW | R. Hanel | R. Hanel | R. Hanel | J. Reuter |  |
| Tester 3 HW | R. Altermann | M. Schimkowitsch | M. Schimkowitsch | M. Schimkowitsch |  |
| Tester 4 HW | M. Schimkowitsch |  |  |  |  |
| Designer 1 SW | R. Mittermayer |  |  |  |  |
| Designer 2 SW | B. Mezödi |  |  |  |  |
| Tester SW | NN |  |  |  |  |

## Training of System Engineering Team

The majority of the engineers are employees with many years of experience in HW and/or SW development. Employees who have recently joined the team are subject to the Hitachi training program, which is coordinated with HR. Furthermore, there is mentoring specifically for the DSTW project from the experienced colleagues mentioned above. On top of that, the SEM is participating in trainings for IPMA certification. Any necessary training measures will be coordinated with the respective superiors.

## Constraints

Aside from preconditions representing deliverables from other projects which are listed in Table 16. This table lists all subsequent delivery versions on which the solution and development process/schedule depend. The following preconditions and assumptions constitute the foundation for this plan:

- Delivery dates for DCA, AzLM will hold

- No changes in HW after TRR1 for DCA and AzLM

- Components for network communication provided by customer

- IFC ZG62

  - Based on SEC 2.5 (DCA-2 HW) and OBB Pilot development

  - Based on SCA board, Plf 2.5.2 (or higher if necessary, see 1.6), J4S 3.1, RJC Core 1.1.0

  - Network connectivity provided by customer, no supervision necessary

Constraints which are not listed here can be found in the [RiskReport].

## Work Contained Phase 1

The complete DFE Development will be split in 3 Phases. This document and the Work Contained describes in detail phase 1.

### WP3.DEV.3.2.3.1 - IFC ZG62 (HW + SW)

- Development/Qualification IFC ZG62 HW + SW

  - Based on ÖBB-Pilot DCA 2.x

  - Development/Integration of Computing Board SCA, DCA 2.x IOC, Relay Group

  - X25 over RaSTA

- Industrialization of HW

- Labor Setup

### WP3.DEV.3.2.3.2 - FES S DCA

Development/Qualification of FES S (up to 2 OC) + M DCA (up to 10 OC)

- Development/Integration of the DCA 3.x (Object Controller Release 1 for EULYNX BL4R4 generic functionalities and OBB specific functionalities) version (HW)

- Development/Qualification of FES Modules

  - Module Network

  - Module Cable Distribution Frame

  - Module Power Supply

- Development/Qualification of

  - Housekeeping

  - Lighting / Access Control

  - Mechanics

  - Overvoltage & Lightning Protection

- Development/Qualification of additional Equipment:

  - Indusi Extender (for Subsystem Signal)

  - CAN-Extension for Distances > 100m (for Subsystem Signal)

- Development/Qualification of Subsystems

  - Point

  - Light Signal

  - Generic I/O (Station Key Lock, Line Key Lock, Local Control Post)

- Industrialization of HW

- Labor Setup

### WP3.DEV.3.2.3.3 - FES M DCA

Development/Qualification of FES M DCA (up to 10 OC)

- Development/Integration of the DCA 3.x (Object Controller Release 1 for EULYNX BL4R4 generic functionalities and OBB specific functionalities) version (HW)

- Development/Qualification of FES Modules

  - Module Network

  - Module Cable Distribution Frame

  - Module Power Supply

- Development/Qualification of

  - Housekeeping

  - Lighting / Access Control

  - Mechanics

  - Overvoltage & Lightning Protection

- Development/Qualification of additional Equipment:

  - Indusi Extender (for Subsystem Signal)

  - CAN-Extension for Distances > 100m (for Subsystem Signal)

- Development/Qualification of Subsystems

  - Point

  - Light Signal

  - Generic I/O (Station Key Lock, Line Key Lock, Local Control Post)

- Industrialization of HW

- Labor Setup

### WP3.DEV.3.2.3.4 - FES M AzLM

Development/Qualification FES M AzLM (TDS) v7.10.

- Development/Qualification of FES Modules

  - Module Network

  - Module Cable Distribution Frame

  - Module Power Supply

- Development/Qualification of

  - Housekeeping

  - Lighting / Access Control

  - Mechanics

  - Overvoltage & Lightning Protection

- Integration/Qualification of Subsystem AzLM (TDS) with EULYNX BL4R4 - target to be compliant with LFC10 / encryption

- Industrialization of HW

- Labor Setup

### WP3.DEV.3.2.3.5 - FES S IFC LCSI

- Development Support FES S IFC LCSI

  - Support Supplier in LCSI Gateway development (Mission Embedded)

  - Pre-Test of 1st Prototype

The next two figures show a schematic buildup of a FES M DCA and a FES M AzLM.

Figure 7	FES M DCA Schematic

Figure 8	FES M AzLM Schematic

## Work not contained in Phase 1

The following points are defined as Work not Contained:

- DCA Development

- AzLM Development

- Execution of Field tests on site

- Installation and put into operation at customer site

- Development/Integration iLED/iAnzeiger according to [CRS_Light Signals]

## Work contained in later Phases

### Phase 2

- Development/Qualification of FES L+XL with all included components (DCA 3.x Release 2, Including Data encryption with LFC20 Board due to CPU maximum load of 60% in operation, TAS Platform 2.6)

- Development/Qualification of FES L+XL with all included components (AzLM v7.11 Feature Complete, Cryptography, TAS Platform 2.6)

- Development/Qualification of IFC Sbl60A with all included components

- Development/Qualification of FES S IFC LCSI

  - Integration/Qualification of external developed LCSI-Gateway

- Full DDSP Integration (except self-test and SW activation)

- Extension of Laboratory Equipment

### Phase 3

- Development/Qualification of FES XXL

- New Functionalities, Corrections or Obsolescences

- Self-Test and System-Activation for OC

- Tunnel Cabinet

## Responsibility Assignment Matrix

The responsibilities of the roles at a Milestone Review can be seen in Milestone Template Solutions [S24].

The milestone review TQR2 confirms the successful completion of product validation and the readiness of all needed elements for customer acceptance and that the Solution is ready for Assessment according to CENELEC. The PDAs confirm with the approval to milestone TQR2 that the delivered solution meets their expectations.

The milestone review FQR confirms that the Design, Development and Qualification activities including Assessment according to CENELEC are complete and that the Solution is ready for production, deployment and transition to support.

### Types of Involvement

A	Approve

R	Responsible for organization (incl. contribution)

C	Contribute

AR	Attend on request

### Involvements

Table 21	Involvements table

| Stakeholder | SOR | SRR | SFR | PDR | CDR | TRR | TQR | FQR |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| PM | C | C | C | C | C | C | C | C |
| PDA | A | A | A | A | A | A | A | A |
| PSM | C | C | C | C | C | C | C | C |
| ARC | C | C | C | C | C | - | - | - |
| SEM | R | R | R | R | R | C | C | R |
| IVVQM | C | C | C | C | C | R | R | C |
| HwEM | C | C | C | C | C | C | C | C |
| SwEM | C | C | C | C | C | C | C | C |
| SpE | AR | AR | AR | AR | AR | AR | AR | AR |
| PPTM | C | C | C | C | C | C | C | C |
| SVEM | C | C | C | C | C | - | C | C |
| APM | C | - | - | - | C | - | C | AR |
| ATS | AR | AR | AR | AR | AR | AR | AR | AR |
| CM | C | C | C | C | C | C | C | C |
| QAM | C | C | C | C | C | C | C | C |
| RAM-AM | C | C | C | C | C | C | C | C |
| SAM | C | C | C | C | C | C | C | C |
| RM | C | C | C | C | C | C | C | C |
| VAL | C | C | C | C | C | C | C | C |
| VER | C | C | C | C | C | C | C | C |
| WPMs | C | C | C | C | C | C | C | C |

### Explanation

## Development Approach

The SW-Development Approach is shown in Agile Definition SMP [S27].

The development of a HW Solution has to be planned and executed according to the DDQS Processes of Management System.

## Tools and Facilities

In this chapter the needed tools for executing the Solution Element DFE will be identified. The tool version is only mentioned if the corresponding tool has a direct effect to the deliverable (see also [ToolClass] and [ToolClassSW]).

### Project Management

Table 22	Project Management

| Name | Version |  | Rationale | User max/Concurrent | Reference to validation report |
| --- | --- | --- | --- | --- | --- |
| PCM Project Planner / Primavera |  |  |  | 2/2 |  |
| Pertmaster Project Risk |  |  |  |  |  |
| Estimation Worksheet |  |  |  |  |  |
| OTL Timesheets |  |  |  | all |  |

### Task Management

Table 23	Task Management

| Name | Version |  | Rationale | User max/Concurrent | Reference to validation report |
| --- | --- | --- | --- | --- | --- |
| TIPI |  |  |  |  |  |
| Jira |  |  |  |  |  |
| Jira / SCRUM |  |  |  |  |  |
| Jira AT Task Management / iTask |  |  |  |  |  |

### Requirements Management

Table 24	Requirements Management

| Name | Version |  | Rationale | User max/Concurrent | Reference to validation report |
| --- | --- | --- | --- | --- | --- |
| Doors / RMF | 9.7 / 6.1 |  | DOORS/RMF as customer defined tool |  |  |
| Doors |  |  |  |  |  |
| Polarion |  |  |  |  |  |

### Management Traceability

Table 25	Management Traceability

| Name | Version |  | Rationale | User max/Concurrent | Reference to validation report |
| --- | --- | --- | --- | --- | --- |
| Reqtify |  |  |  |  |  |
| Doors |  |  | DOORS/RMF as customer defined tool |  |  |
| Polarion |  |  |  |  |  |

### Configuration Management

Table 26	Configuration Management

| Name | Version |  | Rationale | User max/Concurrent | Reference to validation report |
| --- | --- | --- | --- | --- | --- |
| ClearCase |  |  | Repository for DWF managed documents. Repository for data prepared for tests and field |  |  |
| ClearCase UCM |  |  |  |  |  |
| CVS |  |  | Legacy |  |  |
| GIT |  |  |  |  |  |
| HG |  |  | Client only |  |  |
| Subversion |  |  |  |  |  |
| Subversion UCM |  |  |  |  |  |
| Bitbucket |  |  |  |  |  |
| Nexus |  |  |  |  |  |
| Shared Palma |  |  |  |  |  |

### Change Management

Table 27	Change Management

| Name | Version |  | Rationale | User max/Concurrent | Reference to validation report |
| --- | --- | --- | --- | --- | --- |
| ClearQuest |  |  |  |  |  |
| ClearQuest CHARM |  |  |  |  |  |
| Gnats |  |  | Legacy |  |  |
| Jira |  |  |  |  |  |
| Jira CHARM |  |  |  |  |  |

### Documentation Management

Table 28	Documentation Management

| Name | Version |  | Rationale | User max/Concurrent | Reference to validation report |
| --- | --- | --- | --- | --- | --- |
| CMCS |  |  |  |  |  |
| Clear Case, DWF |  |  |  |  |  |
| Confluence |  |  |  |  |  |
| Live link (TOL), ECM |  |  |  |  |  |
| Modulo |  |  |  |  |  |
| Subversion |  |  |  |  |  |
| Share Point |  |  |  |  |  |

### Documentation Generation

Table 29	Documentation Generation

| Name | Version |  | Rationale | User max/Concurrent | Reference to validation report |
| --- | --- | --- | --- | --- | --- |
| Doxygen |  |  |  |  |  |
| Java Doc |  |  |  |  |  |
| Mozart |  |  |  |  |  |
| Soda |  |  |  |  |  |
| WEXP (Doors RMF) |  |  |  |  |  |
| Thales AT Word Exporter |  |  |  |  |  |
| MS Office |  |  |  |  |  |
| Polarion |  |  |  |  |  |

### Model Driven Engineering

Table 30	Model Driven Engineering

| Name | Version |  | Rationale | User max/Concurrent | Reference to validation report |
| --- | --- | --- | --- | --- | --- |
| Melody/Advance |  |  |  |  |  |
| Rhapsody / Orchestra Profile |  |  |  |  |  |
| Rhapsody |  |  |  |  |  |
| Topcased |  |  |  |  |  |
| Visual Paradigm |  |  |  |  |  |

### Code Building

#### Hitachi Control - Continuous Build

Table 31	Hitachi Control - Continuous Build

| Name | Version | App | Rationale | User max/Concurrent | Reference to validation report |
| --- | --- | --- | --- | --- | --- |
| Hudson + Subversion |  |  |  |  |  |
| Hudson + Clear Case |  |  |  |  |  |
| Maven | 3.6.2 |  |  |  |  |
| Sonarqube | 9.9 |  |  |  |  |
| Jenkins | 2 |  |  |  |  |

#### Hitachi AT Build

Table 32	Build

| Name | Version | App | Rationale | User max/Concurrent | Reference to validation report |
| --- | --- | --- | --- | --- | --- |
| Ant |  |  |  |  |  |
| Bash | 4.4.20 |  |  |  |  |
| Make | 4.1 |  |  |  |  |

#### Eclipse Development

Table 33	Eclipse Development

| Name | Version | App | Rationale | User max/Concurrent | Reference to validation report |
| --- | --- | --- | --- | --- | --- |
| Eclipse IDE |  |  |  |  |  |
| <Plugins> |  |  |  |  |  |

#### Programming Languages / Compiler

Table 34	Programming Languages/Compiler

| Name | Version | App | Rationale | User max/Concurrent | Reference to validation report |
| --- | --- | --- | --- | --- | --- |
| C | As delivered by TAS Platform 2.5.2 |  |  |  |  |
| C++ |  |  |  |  |  |
| C# |  |  |  |  |  |
| Certified GCC |  |  |  |  |  |
| GNU C/C++ |  |  |  |  |  |
| Drools |  |  |  |  |  |
| Java | 21 |  |  |  |  |
| Perl |  |  |  |  |  |
| PHP |  |  |  |  |  |
| PL/SQL |  |  |  |  |  |
| Python |  |  |  |  |  |
| GraalVM native-image | 22.3.1 |  |  |  |  |

#### Hitachi AT Elektra Tools

Table 35	Elektra Tools

| Name | Version | App | Rationale | User max/Concurrent | Reference to validation report |
| --- | --- | --- | --- | --- | --- |
| Audit Tools |  |  |  |  |  |
| CEL Tools |  |  |  |  |  |
| Configure Station |  |  |  |  |  |
| Data Difference Tool |  |  |  |  |  |
| DB Compare |  |  |  |  |  |
| DB Generator (DBG) |  |  |  |  |  |
| EditXMLFiles |  |  |  |  |  |
| Elektra Make files |  |  |  |  |  |
| GNU Chill compiler |  |  |  |  |  |
| Java4chill |  |  |  |  |  |
| PAMELA |  |  |  |  |  |
| VAX Interface |  |  |  |  |  |

#### Hitachi AT ETCS Tools

Table 36	ETCS Tools

| Name | Version | App | Rationale | User max/Concurrent | Reference to validation report |
| --- | --- | --- | --- | --- | --- |
| Audit Tools |  |  |  |  |  |
| Release Tools |  |  |  |  |  |
| Generated Configure. Spec. |  |  |  |  |  |

#### Hitachi AT Legacy Tools

Table 37	Legacy Tools

| Name | Version | App | Rationale | User max/Concurrent | Reference to validation report |
| --- | --- | --- | --- | --- | --- |
| VAX Tools |  |  |  |  |  |
| Aeos1, Aeos2 tools & techn. |  |  |  |  |  |
| Solaris tools |  |  |  |  |  |

#### Hitachi AT Internal Used Products

Table 38	Internal Used Products

| Name | Version | App | Rationale | User max/Concurrent | Reference to validation report |
| --- | --- | --- | --- | --- | --- |
| Data Prep. Tool AWS |  |  |  |  |  |
| Data Prep. Verif. Tool AWS |  |  |  |  |  |
| ELEPRO (Seibersdorf) |  |  |  |  |  |
| Orest | Developed for DSTW |  |  |  |  |
| TAS Platform | 2.5.x |  |  |  |  |

#### Development Platform

Table 39	Development Platform

| Name | Version | App | Rationale | User max/Concurrent | Reference to validation report |
| --- | --- | --- | --- | --- | --- |
| Linux/RedHat |  |  |  |  |  |
| Solaris |  |  |  |  |  |
| Linux/Ubuntu |  |  |  |  |  |
| Windows |  |  |  |  |  |

### Hardware Engineering Environment

Table 40	HW Engineering Environment

| Name | Version | App | Rationale | User max/Concurrent | Reference to validation report |
| --- | --- | --- | --- | --- | --- |
| ATDM | V 3.25 |  |  |  |  |
| Cadence | 22.1 S007 |  |  |  |  |
| SOLIDWORKS | Premium 2022 |  |  |  |  |
| TCIS | V4.7 |  |  |  |  |
| LTspice | V24 |  |  |  |  |
| EPLAN Electric P8 | 2024 Update 2 |  |  |  |  |

### IVV Management

Table 41	IVV Management

| Name | Version | App | Rationale | User max/Concurrent | Reference to validation report |
| --- | --- | --- | --- | --- | --- |
| DOORS |  |  |  |  |  |
| Coverity |  |  |  |  |  |
| Expect |  |  |  |  |  |
| GCOV |  |  |  |  |  |
| Mercury Win Runner |  |  |  |  |  |
| QF Test |  |  |  |  |  |
| Quick Test |  |  |  |  |  |
| Rational Test RT Mercury Loader |  |  |  |  |  |
| QAC |  |  |  |  |  |
| PurifyPlus |  |  |  |  |  |
| ICOV |  |  |  |  |  |
| EPS |  |  |  |  |  |
| Polarion |  |  |  |  |  |
| MS Excel |  |  |  |  |  |
| SOS (SCWS outside Area Simulator) |  |  |  |  |  |

# Process Control

## Control of Solution Development

The Solution Element DFE assigned responsibilities are listed in Table 11.

### Deviation

The development of a Solution has to be planned and executed according to the DDQS Processes of Management System. Deviation to the description in Project Life Cycle [S22] is described in section 5.

### Metrics

The used metrics for control of the engineering process are identified in the Engineering Dashboard [EngDB].

Table 42	Metrics

| ID | Name | App | Type |
| --- | --- | --- | --- |
| 1 | Schedule | M | Indicators |
| 1.1 | MTA | M | Metrics |
| 1.2 | Actual Milestones | O | Metrics |
| 2 | EAC vs CBB | M | Indicators |
| 2.1 | CBB-EAC Synthesis | O | Metrics |
| 2.2 | WP CBB-EAC | O | Metrics |
| 2.3 | Workload diagram | O | Metrics |
| 3 | Subcontractor | M | Indicators |
| 3.1 | Subcontractor Status | O | Info |

## Monitoring and Control of System Engineering Activities

### Periodic Internal Reviews and Meetings

Table 43	Reviews and Meetings

| INTERNAL REVIEWS & MEETINGS |  |  |  |  |
| --- | --- | --- | --- | --- |
| Meeting | Responsible | Attendees | Frequency | Objectives |
| Solution Core Team Meeting | SEM | Solution Core Team, ARC, WPM(s) Only on demand: CM, IM | Weekly | Solution Status and Action Points |
| Risk and opportunity review | SEM | SEM DIL, PLM, PDA, IVVQM, SAM, ARC, QAM, IM, SecAM | Quarterly or on demand | Reassess current risks and include new risks |
| Resource review | SEM | SEM DIL, HoD | Monthly | Check utilisation and additional needs of solution team |
| Change Control Board | SEM | See Table 14 | On demand |  |
| Daily Standup | WPM ZG62 SW |  | On demand | Internally handled by Agile SW Development |
| Weekly Sync Meetings | WPM ZG62 SW | WPM with Team members | Weekly | Status and Action Points |
| Sprint Planning Meeting | WPM ZG62 SW |  |  | Internally handled by Agile SW Development |
| Sprint Review and Sprint Retrospective | WPM ZG62 SW |  |  | Internally handled by Agile SW Development |
| Periodically Performance Project Review (PPPR) | SEM | PM, SEM, QAM | Monthly | Report of costs and progress, KPI dashboard, Progress Matrix, required decisions from SM to HoD Project engineering, HoD Engineering |

### Milestone Reviews and Audits

Milestone reviews are done according to Milestone Template Solutions [S24]. Quality Audits will be conducted through the QAM – see [QMP]. Safety Audits will be conducted through the SAM – see [SP].

Table 44	Milestone Reviews

| Review | Responsible | Attendees | Objectives |
| --- | --- | --- | --- |
| SOR | SEM | As defined in Milestone Template Solutions [S24] | Start of Design phase for Solution Approve preliminary solution architecture in particular with respect to make/team/buy |
| SRR | SEM | As defined in Milestone Template Solutions [S24] | Approve the solutions initial functional baseline |
| SFR | SEM | As defined in Milestone Template Solutions [S24] | Approve PBS and preliminary allocated baseline |
| PDR | SEM | As defined in Milestone Template Solutions [S24] | Approve allocated baseline and IVVQ strategy |
| CDR | SEM | As defined in Milestone Template Solutions [S24] | Approve the solution elements conformance to FBL and ABL and approve the completeness of the product baseline. |
| TRR1 | IVVQM | As defined in Milestone Template Solutions [S24] | Start solution integration and system testing with first work package released to System Test |
| TQR1/TRR2 | IVVQM | As defined in Milestone Template Solutions [S24] | Start solution validation |
| TQR2 | IVVQM | As defined in Milestone Template Solutions [S24] | The validation of the solution is finished. This milestone also includes the handover to external assessor. |
| FQR | SEM | As defined in Milestone Template Solutions [S24] | Approve functional and physical configuration audits as well as deviations and waivers. |

### Reporting

Reporting is done via the Engineering Dashboard [EngDB].

## Critical Technologies

Critical technologies are managed in the risk management [RiskReport].

## Risk and Opportunities Control

The Risk and Opportunities Control in this Solution will follow the Management System Process Manage Risks and Opportunities [S7] and is monitored in the [RiskReport].

## Corrective Action Process

Information about the Corrective Action Process can be found in the Quality Management Plan [QMP].

## Independent Evaluation and Verification

Independent evaluation and verification will be done by

- the verifier and domain experts upon instruction of the verifier (VER);

- the validator (VAL);

- the safety assurance manager (SAM).

## Estimate/Re-Estimate

The initial estimation is either an input for the phase “Orientation the Solution” or is done or verified during this phase. Re-estimation of remaining work is done during the progress of working packages typically on a monthly period. The method used for estimation is mainly “Expert estimations” based on past experience, educated assumptions and risk considerations. See also Estimation Sheets  [Estimation Sheet_DSTW_HW] and [Estimation Sheet_DSTW_NIC_SW].

## Planning

Planning is done in the tool PCM and can be found there with the identification listed in Table 1.

## Value Analysis and Design to Cost

Value Analysis and Design to Cost is done by the Engineering Dashboard [EngDB].

## Peer Reviews

The Peer Reviews in this Solution will follow the Minimum Requirements for the configuration management implementation [S9]. An overview of mandatory Documents and Reviewer has to be done according to Document List and Review Matrix for engineering projects [S25].

# Development Scenario and Tailoring of the System Engineering Process

## Orient the Solution

Figure 9	Orient the Solution

### Overview

Objective: Understand Customer Needs and define a development strategy

The Design of the Solution is carried out according to the Management System Process Orient the Solution [S14].

### Input/Start

The Start Review for this Solution is the KOM.

This SEMP Edition is based on the 4th Edition of the offer placed to ÖBB at 12th of September 2025 and the negotiations process is ongoing. KOM will take place after the contract has been signed. Current activities are based on the customer requirements [CRS]. SOR will be repeated after official KOM.

### Activities and Deviations

The activities, details and deviations are planned according to the Management System Process Orient the Solution [S14].

Table 45	Orient the Solution, Activities and Deviations

| Nr | Activity | Method* | Document |
| --- | --- | --- | --- |
| 1 | Understand customer expectations |  | SEMP, FL |
| 2 | Understand the impact of regulatory compliance including HSE |  |  |
| 3 | Estimate the viability of the solution |  |  |
| 4 | Update needs (Operational Concepts) |  | OCD |
| 5 | Define the Solution life cycle strategy |  |  |
| 6 | Prepare Validation and Qualification |  |  |
| 7 | Develop industrial and support strategy |  |  |

*Here are the methods listed used to conduct the activity. If there is a deviation, it will be shown in the cell and explained in the paragraph below.

Deviation:

No other deviation to the according to the Management System Process Orient the Solution [S14].

### Output

The End Review for this Phase is the SOR.

The SOR is the consolidation of all collected information of the project and the related solutions (see Table 17).

## Design the Solution

Figure 10	Design the Solution

### Overview

Objective: Formalise any outstanding requirement, agree and finalise the chosen architectural design, specifications and plans used to develop the Solution.

The Design of the Solution is carried out according to the Management System Process Design the Solution [S15].

### Input/Start

The Start Review for this Solution is the SOR.

Regarding the according Decision Review Report, see [MS-Report].

### Activities and Deviations

The activities, details and deviations are planned according to the Management System Process Design the Solution [S15].

Table 46	Design the Solution, Activities and Deviations

| Nr | Activity | Method* | Document |
| --- | --- | --- | --- |
| 1 | Formalise stakeholder requirements |  | SSS |
| 2 | Capture functions and capabilities |  |  |
| 3 | Develop validation, test scenarios, test descriptions and environment |  |  |
| 4 | Prepare for verification & qualification |  |  |
| 5 | Define & justify architecture with respect to the product policy |  |  |
| 6 | Develop logical and physical architecture |  |  |
| 7 | Prepare integration and verification |  |  |

Deviation:

No other deviation to the according to the Management System Process Design the Solution [S15].

### Output

The End Review for this Phase is the SFR.

Regarding related solutions, see Table 17.

## Develop the Solution

Figure 11	Develop the Solution

### Overview

Objective: refine the lower level of requirements down to a complete definition (Solution elements, HW and/or SW components) and to consolidate definition up to the solution level with agreement of all concerned levels. At the lowest level, the Develop step leads, after definition consolidation, to implement hardware and/or software components according to the Make/Buy strategy.

The Development of the Solution is carried out according to the Management System Process Develop the Solution [S16].

### Input/Start

The Start Review for this Solution is the SFR.

Regarding the according Decision Review Report, see [MS-Report].

### Activities and Deviations

The activities, details and deviations are planned according to the Management System Process Develop the Solution [S16].

Table 47	Develop the Solution, Activities and Deviations

| Nr | Activity | Method* | Document |
| --- | --- | --- | --- |
| 1 | Formalise [solution element] requirements associated to a [solution element] preliminary design taking into account technology process and reuse, |  | SSS, SSDD, VCRM |
| 2 | Specify [solution element] interfaces, |  | IDD |
| 3 | Perform a [Preliminary Design Review (PDR)] with relevant stakeholders, |  | Project Status Review Report Solution |
| 4 | Perform a component detail design, |  | HDD, SDD |
| 5 | Complete the [Design Definition File DDF)] and the [Design Justification File (DJF)] |  | DDF, DJF |
| 6 | Make or buy the software components |  |  |
| 7 | Make or buy the hardware components |  |  |
| 8 | Update validation plan and perform appropriate early validation tasks (simulation, modelling, prototyping, …) |  | IVVP, Design validation form (DVA) |

*Here are the methods listed used to conduct the activity. If there is a deviation, it will be shown in the cell and explained in the paragraph below.

Deviation:

No other deviation to the according to the Management System Process Develop the Solution [S16].

### Output

The End Review for this Phase is the TRR1.

Regarding related solutions, see Table 17.

## Integrate and Verify the Solution

Figure 12	Integrate & Verify the Solution

### Overview

The objective of the Integrate and Verify process step is to assemble the Solution Element in a logical and controlled manner and to evaluate the design, behaviour, interactions and performance, and confirm through provision of objectives evidences that the requirements against which it has been designed are fulfilled.

Integrate & Verify the Solution is carried out according to the Management System Process Integrate and Verify the Solution [S13].

### Input/Start

The Start Review for this Solution is the TRR1.

Regarding the according Decision Review Report, see [MS-Report].

### Activities and Deviations

The activities, details and deviations are planned according to the Management System Process Integrate and Verify the Solution [S13]. The verification tasks will be handled according to CENELEC [S2] EN 50716:2023 – Railway application – Requirements for software development.

Table 48	I&V the Solution, Activities and Deviations

| Nr | Activity | Method* | Document |
| --- | --- | --- | --- |
| 1 | Record and maintain the configuration of the elements constituting the component or system as received for any integration stage from production or supplier, and their interfaces |  |  |
| 2 | Check product supplier elements (from internal or external suppliers) against their configuration description |  |  |
| 3 | Maintain interface descriptions and update them after change approval |  |  |
| 4 | Assemble and test in accordance with the Integration Plan including the logical order of integration events |  |  |
| 5 | Begin to conduct tests when the minimum configuration is reached, for early identification of anomalies, features and risk reduction |  |  |
| 6 | Measure quantitative results once the maximum configuration is reached |  |  |
| 7 | Evaluate the solution design, behaviour, interactions and performance according to the integration plan |  |  |
| 8 | Record the identity of the resources used |  |  |
| 9 | Follow the verification procedure |  |  |
| 10 | Compile the results documents |  |  |
| 11 | Control the deviations |  |  |
| 12 | Record verification results |  |  |
| 13 | Communicate information on variances and anomalies to stakeholders |  |  |
| 14 | Plan and perform the various supplier Functional Configuration Audits and Physical Configuration Audits for components and/or systems |  |  |
| 15 | Ensure that the method for recording and managing defects found during testing is established and known, and that the mechanism is set-up and ready to use |  |  |
| 16 | Ensure that the product data packages of solution elements are accurate and detailed enough for release to production |  |  |
| 17 | Support the project management to obtain a declaration of technical qualification of solution elements |  |  |
| 18 | Provide data and services to develop enabling systems required to produce, support or dispose of the solution including any test facilities, training assets, documentation and courses or support systems or logistical processes |  |  |
| 19 | Revisit the solution qualification strategy |  |  |
| 20 | Develop the engineering parts of Qualification plan |  |  |

*Here are the methods listed used to conduct the activity. If there is a deviation, it will be shown in the cell and explained in the paragraph below.

Deviation:

No other deviation to the according to the Management System Process Integrate and Verify the Solution [S13].

### Output

The End Review for this Phase is the TQR1.

Regarding related solutions, see Table 17.

## Validate the solution

Figure 13	Validate the Solution

### Overview

The objective of the Validate process step of DDQS process is to confirm through the provision of objective evidence, that the agreed and contracted requirements have been met by the solution and, from industrial point of view, confirm that all IVV activities are completed and that the Product Data Package is ready for release to production and to support.

Validate the Solution is carried out according to the Management System Process Validate the Solution[S12].

### Input/Start

The Start Review for this Solution is the TQR1.

Regarding the according Decision Review Report, see [MS-Report].

### Activities and Deviations

Here, the activities and the methods for reaching the objectives are listed and deviations are pointed out:

The Assessment Certification according to CENELEC is needed for this solution.

The activities, details and deviations are planned according to the Management System Process Validate the Solution [S12].

Table 49	Validate the Solution, Activities and Deviations

| Nr | Activity | Method* | Document |
| --- | --- | --- | --- |
| 1 | Confirm with objective evidence that the requirement for specific use or application of the solution is satisfied as defined in the contract (or any other formal agreement) in order to support the certification (if required) |  |  |
| 2 | Confirm the production process is repeatable at the desired quality level and that the product conforms with the definition file |  |  |
| 3 | Qualify the manufacturing process with the initial production items (demonstration of the production to cost objective at required quality level) |  |  |
| 4 | Provide the evidence that the solution is reliable, maintainable, available and safe |  |  |
| 5 | Prepare the means and documentation for installation, deployment into service and support of the solution to ensure the smooth transition into service and into support |  |  |
| 6 | Provide data for the Functional Configuration Audit (FCA) and the Physical Configuration Audit (PCA) of the solution |  |  |
| 7 | Provide data for the Functional Configuration Audit (FCA) and the Physical Configuration Audit (PCA) of the Solution components |  |  |
| 8 | Develop and establish the safety cases |  |  |
| 9 | prepare and support the external assessment |  |  |

*Here are the methods listed used to conduct the activity. If there is a deviation, it will be shown in the cell and explained in the paragraph below.

Deviation:

No other deviation to the according to the Management System Process Validate the Solution [S12].

### Output

The End Review for this Phase is the FQR.

Regarding related solutions, see Table 17.

# System Engineering Support

## Data and Configuration Management

Data and Configuration Management is carried out according to Management System Process 9.7 CFG - Manage Configuration [S17], Document Management Rules [S23] and the Configuration Management Plans [CMP_GEN] & [CMP_HW].

## Confidentiality

The rules as listed in Protection of Group Information [S20] apply.

## Export Control

Export Control is carried out according to Management System Process 9.3 Control Export [S18].

## Capitalization

Capitalization is handled in the context of the related Manage Product Policy process.

## Measurements and Analysis

See section 4.

## Technical and Non-Technical Requirements Management and Control

For Requirement Management the tools DOORS and Polarion are used. The Requirements Manager ensures that requirements are

- uniquely identified

- unambiguous, testable and consistent

- traced from origin through all systems

- have all changes managed

The Requirements Manager manages changes throughout the life of the project. If requirements change, the impact will be reflected in the project plans, work products, and activities. Any inconsistencies between these customer- and/or system requirements and project plans, work products, and activities will be identified and resolved.

## Validation of Requirements

The validation is done in accordance with the Validation Qualification Plan ([VQP]).

## Decision Analysis and Resolution

Decision analysis and resolutions are part of design and review processes. The results are documented in design documents, review reports and in this document.

## Subordinate Plans

Planning documents are mentioned in Table 5 as well as in [DoP].

## Quality Assurance

The Quality Assurance in this Solution will follow Management System Guarantee quality and manage continuous improvement [S19]. Additional information can be found in the Quality Management plans as listed in [DoP].

# Approach and Criteria used for Tailoring of the System Engineering Process

The Tailoring Methods are described in Chapter 5 for the respective Phase.

# Certification Support Activity

See Safety Management Plans and Security Management Plans as listed in [DoP].

# Notes

None

- Criteria for the Selection of Techniques and Measures

With each technique or measure in the tables there is a requirement for each software safety integrity level (SIL). In the version 2023 of the EN 50716, the requirements for software safety integrity levels 1 and 2 are the same for each technique. Similarly, each technique has the same requirements at software safety integrity levels 3 and 4. These requirements can be

“App” this column selects with “Yes” for all relevant "documentation", “technique” or “measure” for the actual project or “No” if this row isn’t mandatory for the project.

'M' this symbol means that the use of a technique is mandatory,

'HR' this symbol means that the technique or measure is Highly Recommended for this safety integrity level. If this technique or measure is not used then the rationale for using alternative techniques shall be detailed in the Software Quality Assurance Plan or in another document referenced by the

Software Quality Assurance Plan

'R' this symbol means that the technique or measure is recommended for this safety integrity level. This is a lower level of recommendation than an 'HR' and such techniques can be combined to form part of a package,

'-' this symbol means that the technique or measure has no recommendation for or against being used,

'NR' this symbol means that the technique or measure is positively “Not Recommended” for this safety integrity level. If this technique or measure is used then the rationale behind using it shall be detailed in the Software Quality Assurance Plan or in another document referenced by the Software Quality Assurance Plan.

Table A. 1 	Lifecycle Issues and Documentation

| DOCUMENTATION | App | Basic Integrity | SIL 1 | SIL 2 | SIL 3 | SIL 4 | References of Doc Type |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Planning |  |  |  |  |  |  |  |
| 1. Software Quality Assurance Plan |  | HR | HR | HR | HR | HR | [QMP] |
| 2. Software Planning and Verification Report |  | R | HR | HR | HR | HR | VER REP |
| 3. Software Configuration Management Plan |  | HR | HR | HR | HR | HR | [CMP_GEN], [CMP_HW] |
| 4. Software Verification Plan |  | HR | HR | HR | HR | HR | [IVP] |
| 5. Software Validation Plan |  | HR | HR | HR | HR | HR | [VQP] |
| Software requirements |  |  |  |  |  |  |  |
| 6. Software Requirements Specification |  | HR | HR | HR | HR | HR | SSS |
| 7. Overall Software Test Specification |  | HR | HR | HR | HR | HR | TCS |
| 8. Software Requirements Verification Report |  | R | HR | HR | HR | HR | VER Rep |
| Architecture and design |  |  |  |  |  |  |  |
| 9. Software Architecture Specification |  | R | HR | HR | HR | HR | SSDD |
| 10. Software Design Specification |  | R | HR | HR | HR | HR | SSDD |
| 11. Software Interface Specifications |  | HR | HR | HR | HR | HR | IFS |
| 12. Software Integration Test Specification |  | R | HR | HR | HR | HR | TCS |
| 13. Software/Hardware Integration Test Specification |  | R | HR | HR | HR | HR | TCS |
| 14. Software Architecture and Design Verification Report |  | R | HR | HR | HR | HR | VER REP |
| Component Design |  |  |  |  |  |  |  |
| 15. Software Component Design Specification |  | - | HR | HR | HR | HR | SDD |
| 16. Software Component Test Specification |  | - | HR | HR | HR | HR | TCS |
| 17. Software Component Design Verification Report |  | - | HR | HR | HR | HR | VER REP |
| Component Implementation and Testing |  |  |  |  |  |  |  |
| 18. Software Source Code and supporting documentation |  | HR | HR | HR | HR | HR | Git |
| 19. Software Component Test Report |  | - | HR | HR | HR | HR | Test Report |
| 20. Software Source Code Verification Report |  | - | HR | HR | HR | HR | VER REP |
| Integration |  |  |  |  |  |  |  |
| 21. Software Integration Test Report |  | R | HR | HR | HR | HR | Test Report |
| 22. Software/Hardware Integration Test Report |  | R | HR | HR | HR | HR | Test Report |
| 23. Software Integration Verification Report |  | R | HR | HR | HR | HR | VER REP |
| Overall Software Testing / Final Validation |  |  |  |  |  |  |  |
| 24. Overall Software Test Report |  | HR | HR | HR | HR | HR | Test Report |
| 25. Software Validation Report |  | HR | HR | HR | HR | HR | VAL REP |
| 26. Tools Validation Report |  | - | HR | HR | HR | HR |  |
| 27. Release Note |  | HR | HR | HR | HR | HR | VDD |
| Systems configured by application data |  |  |  |  |  |  |  |
| 28. Application Requirements Specification |  | HR | HR | HR | HR | HR | N/A |
| 29. Application Preparation Plan |  | R | HR | HR | HR | HR | N/A |
| 30. Application Test Specification |  | HR | HR | HR | HR | HR | N/A |
| 31. Application Architecture and Design |  | R | HR | HR | HR | HR | N/A |
| 32. Application Preparation Verification Report |  | - | HR | HR | HR | HR | N/A |
| 33. Application Test Report |  | HR | HR | HR | HR | HR | N/A |
| 34. Source Code of Application Data |  | HR | HR | HR | HR | HR | N/A |
| 35. Application Data Verification Report |  | R | HR | HR | HR | HR | N/A |
| 36. Application Integration Test Specification |  | HR | HR | HR | HR | HR | N/A |
| 37. Application Integration Test Report |  | HR | HR | HR | HR | HR | N/A |
| 38. Application Release Note |  | HR | HR | HR | HR | HR | N/A |
| Software deployment |  |  |  |  |  |  |  |
| 39. Software Deployment Manual |  | R | HR | HR | HR | HR | N/A |
| 40. Deployment Records |  | R | HR | HR | HR | HR | N/A |
| 41. Deployment Verification Report |  | R | HR | HR | HR | HR | N/A |
| Software maintenance |  |  |  |  |  |  |  |
| 42. Software Maintenance Plan |  | R | HR | HR | HR | HR | N/A |
| 43. Software Change Records |  | HR | HR | HR | HR | HR | N/A |
| 44. Software Maintenance Records |  | R | HR | HR | HR | HR | N/A |
| 45. Software Maintenance Verification Report |  | R | HR | HR | HR | HR | N/A |
| Software assessment |  |  |  |  |  |  |  |
| 46. Software Assessment Plan |  | - | HR | HR | HR | HR | N/A |
| 47. Software Assessment Report |  | - | HR | HR | HR | HR | N/A |
| For Basic Integrity, the content of the software verification plan can be limited to 6.2.4.9 a), b), c), d), f). For Basic Integrity the software interface specification is only highly recommended for the boundary of the overall software (see also 7.3.4.18). |  |  |  |  |  |  |  |
| NOTE 1 According to 5.3.2.12 and 5.3.2.13, documents can be combined differently. NOTE 2 Documents 29, 30 and 31 being HR or R depends on the importance defined in the process and where the verification takes place, e.g. data can only be needed to be verified but tested in the system domain while more functional properties need both test and verification. In this case HR has been marked but can be optional R. NOTE 3 Software Architecture Specification and Software Design Specification for Basic Integrity is important to establish especially for long-term maintenance, selection can consider this (e.g. adding these information within Software Requirements specification). |  |  |  |  |  |  |  |

Table A. 2 	Software Requirements Specification

| TECHNIQUE/MEASURE | Ref | Basic Integrity | SIL 1 | SIL 2 | SIL 3 | SIL 4 |
| --- | --- | --- | --- | --- | --- | --- |
| 1. Modelling | Table A.17 | R | R | R | HR | HR |
| 2. Structured methodology | D.52 | R | R | R | HR | HR |
| 3. Decision Tables | D.13 | R | R | R | HR | HR |
| Requirements: 1) The Software Requirements Specification shall include a description of the problem in natural language and any necessary formal or semiformal notation. 2) The table reflects additional requirements for defining the specification clearly and precisely. One or more of these techniques shall be selected to satisfy the Software Integrity Level being used. |  |  |  |  |  |  |

Table A. 10	Software Maintenance

| TECHNIQUE/MEASURE | Ref | Basic Integrity | SIL 1 | SIL 2 | SIL 3 | SIL 4 |
| --- | --- | --- | --- | --- | --- | --- |
| 1. Impact Analysis | D.32 | R | HR | HR | M | M |
| 2. Data Recording and Analysis | D.12 | HR | HR | HR | M | M |

Techniques and measures according to EN 50129:2018 + AC:2019 Railway applications – Communication, signalling and processing systems – Safety related electronic systems for signalling:

Table E. 2	Safety Requirements Specification

| TECHNIQUE/MEASURE | SIL 1 | SIL 2 | SIL 3 | SIL 4 |  |
| --- | --- | --- | --- | --- | --- |
| 1. Graphical description, e.g. block diagrams | R | R | HR | HR |  |
| 2. Structured Specification | HR | HR | HR | HR | (a) |
| 3. Formal or Semiformal Specification | - | - | HR | HR | (b) |
| 4. Computer Aided Specification Tools | - | R | R | R | (c) |
| Approved combinations of techniques for SIL 3 and SIL 4 are: - 1 and 2, or - 2 and 3 (in case of semiformal specification), or - 3 (in case of formal specification).. |
| (a) In order to reduce complexity, it is recommended that a structured requirements specification is developed through a hierarchical structure of refined requirements. This technique structures the functional specification into partial requirements such that the simplest possible, visible relations exist between the latter. This analysis is successively refined until small clear requirements can be distinguished. The result is a hierarchical structure of requirements which provide a framework for the specification of the complete black-box functional and safety requirements. This method emphasizes the interfaces of the requirements and is particularly effective for avoiding interface specification errors. (b) Formal or semi-formal specification provides a means of developing a description of a system based on a structured notation during the specification phase. Formal specifications are based on mathematical models of the system function and/or structure. Formal specification generally includes a verification process based on mathematical analyses to ensure the consistency of the resultant specification model. Semi-formal specification is recommended to express parts of a specification unambiguously and consistently, so that some mistakes, omissions and wrong behaviour can be detected. For semi-formal specification, in some cases the description can be analysed by machine or animated to display various aspects of the system behavior. For formal and semiformal methods see EN 61508-7:2010. (c) Model oriented procedures with hierarchical subdivision, description of all objects and their relationship, common database, and automatic consistency check. |  |  |  |  |  |

Furthermore, please refer to [IVP] Chapter 5.1, Table 7.

# END OF DOCUMENT

Please note that at this stage the focus of the development of the Generic Application and the Solution Element DFE is on Phase 1 and this is indicated by 1.0.0 – for the phases see 3.10

The identification refers to the key products/solutions included in the Digital Interlocking

Please note that this SEMP Edition is based on the 4th Edition of the offer placed to ÖBB at 12th of September 2025 and the negotiations process is ongoing. The KOM will take place after the contract has been signed. Current activities are based on the customer requirements [CRS]. SOR will be repeated after official KOM

On the SL please note that ÖBB and also EULYNX clearly asks for SL3, an end-to-end implementation in Phase 1 will most likely NOT be possible. However, the setup and the describing documents shall be prepared for SL3

All dates are under the assumption of a contract signature by end of December 2025 (=T0). For latest available dates see [IMP].

MS E03 Pflichtenheft Freigabe from Customer OBB defined in [PMP]. MS E03 is currently forecasted with April 2026. For latest available dates see [IMP].