Editions and Change History

| Edition | Date | Written by | Verified by | Approved by | Change Description |
| --- | --- | --- | --- | --- | --- |
| 01 PD | 2022-04-04 | Thales Austria / TEJR SEM P. Bargiel | Thales Austria / TQA QAM D. Kovac | Thales Austria / TEJR HoTEJR K. Ndue | Initial Proposal for milestone SOR |
| 01 RL | 2022-04-20 | Thales Austria / TEJR SEM P. Bargiel | Thales Austria / TQA QAM D. Kovac | Thales Austria / TEJR HoTEJR K. Ndue | Initial Edition for milestone SOR |
| 02 RL | 2023-01-31 | GTS Austria / TEJR SEM P. Bargiel | GTS Austria / TQA QAM D. Kovac | GTS Austria / TEJR HoTEJR K. Ndue | Changes see chapter 1.5.2 |
| 03 RL | 2023-07-05 | GTS Austria / TEJR SEM P. Bargiel | GTS Austria / TQA QAM C. Janneschitz | GTS Austria / TEJR HoTEJR K. Ndue | Changes see chapter 1.5.3 |

Table of Contents

1	SCOPE	6

1.1	Identification	6

1.1.1	General	6

1.1.2	WBS managed as Solution	6

1.1.3	WBS managed as Work Packages	6

1.1.4	Other component versions this engineering solution is based on	7

1.2	System overview	8

1.3	Key points	10

1.3.1	Milestones for Solution	10

1.3.2	Deliverables	10

1.4	Relation with other plans	11

1.5	Document version history	11

1.5.1	Edition 01	11

1.5.2	Edition 02	11

1.5.3	Edition 03	11

2	References and terms	12

2.1	Referenced documents	12

2.2	Process basis	12

2.3	Standards and procedures	13

2.4	Terms, abbreviations and acronyms	14

2.4.1	Role abbreviations	14

2.4.2	Terms, abbreviations and acronyms	14

3	Solution engineering and development process	16

3.1	Organization of solution engineering	16

3.1.1	Solution core team	16

3.1.2	Solution team	16

3.1.3	External project roles	17

3.1.4	Configuration Control Board (CCB)	18

3.1.5	Subcontractors	18

3.2	System engineering supplies	18

3.3	Input data	18

3.4	Preconditions / Related solutions	18

3.5	Technical objectives	19

3.6	Detailed First Level WBS for Work Packages	19

3.7	Special need for training of system engineering team	19

3.8	Constraints / Risks	19

3.9	Work Contained	20

3.10	Work not contained	20

3.11	Responsibility Assignment Matrix	20

3.12	Tools and Facilities	21

3.12.1	Management and Documentation Tools	21

3.12.2	Code Building Tools	21

4	Process Control	22

4.1	Control of Solution Development	22

4.1.1	Deviation	22

4.1.2	Metrics	22

4.2	Monitoring and Control of Solution Engineering Activities	24

4.2.1	Periodic Internal Reviews and Meetings	24

4.2.2	Milestone Reviews and Audits	24

4.2.3	Reporting	24

4.3	Critical Technologies	24

4.4	Risk and Opportunities Control	24

4.5	Corrective Action Process	24

4.6	Independent Evaluation and Verification	25

4.7	Estimate/Re-Estimate	25

4.8	Planning	25

4.9	Value Analysis and Design to Cost	25

4.10	Peer Reviews	25

5	Development scenario and tailoring of the System Engineering Process	26

5.1	Tailoring for this solution	26

5.1.1	Orient the Solution	26

5.1.2	Design the Solution	27

5.1.3	Develop the Solution	27

5.1.4	Integrate and Verify the Solution	27

5.1.5	Validate the solution	27

5.1.6	Documentation Management	27

5.2	Tailoring of milestones	27

5.2.1	Manage Project Milestones	27

5.3	Tailoring of role assignments	28

5.3.1	Role of IVVQM	28

5.3.2	Role of Verifier (VER) according CENELEC EN 50128 and EN 50129	28

5.3.3	Role of DM	28

5.4	Tailoring of the monitoring of project progress within an agile development environment	28

6	System Engineering Support	30

6.1	Data and Configuration Management	30

6.2	Confidentiality	30

6.3	Export Control	30

6.4	Capitalization	30

6.5	Measurements and Analysis	30

6.6	Technical and Non-technical Requirements Management and Control	30

6.7	Validation of Requirements	30

6.8	Decision Analysis and Resolution	30

6.9	Subordinate Plans	31

6.10	Quality Assurance	31

6.11	Certification Support Activity	31

6.12	HSE Plan	31

Appendix A :	Criteria for the Selection of Techniques and Measures	32

Table of Tables

Table 1: Solution Identification	6

Table 2: WBS managed as Solution	6

Table 3: WBS managed as Work Packages	6

Table 4: Other component versions	7

Table 5: Not released items in INT 23.02	8

Table 6: Milestones	10

Table 7: Deliverables	11

Table 8 : Referenced Documents	12

Table 9 : Standards and Procedures	13

Table 10 : Role abbreviations	14

Table 11 : Terms, Abbreviation and Acronyms	15

Table 12: Core team	16

Table 13: Team	17

Table 14: External project roles	17

Table 15: CCB	18

Table 16: Preconditions	18

Table 17: Detailed WBS	19

Table 18: Management and Documentation Tools	21

Table 19: Code Building Tools	21

Table 20: Metrics	23

Table 21: Reviews and Meetings	24

Table A1 Lifecycle Issues and Documentation (EN50128, A.1)	33

Table A2 Software Requirements Specification (EN 50128, A.2)	34

Table of Figures

Figure 1: Product Breakdown Structure	9

Figure 2: Manage the Product Policy (MPP)	26

Figure 3: Manage Project (PRJ)	26

Figure 4: Develop and Qualify the Solution (DDQS)	26

Figure 5: Agile Process according to TAT Agile Definition [S24]	29

# SCOPE

The combined PSEMP, Project Management Plan (PMP) and System Engineering Management Plan (SEMP) describe the organisation, work packages, milestones and application of the GTS Management System DDQS process J.2.2.2.

This Solution delivers ELEKTRA 2 product version International INT 2.10.0 (short PV INT 2.10.0) which realizes features and improvements according to the relevant Business Plan [12] and is fit for the intended purpose of the Hungarian and Bulgarian markets. Current plan for first use is in project HEGL1/HU and CSLK-2/HU.

## Identification

### General

| Cost collector: | 100021363 |
| --- | --- |
| Solution: | ATRENOA98 |
| Project category: | A0 |

Table 1: Solution Identification

### WBS managed as Solution

| WBS | Identification | SEM | SIL | Initial Product Version | Target Product Version | Target date |
| --- | --- | --- | --- | --- | --- | --- |
| ATRENOA98-E0 | (ELEKTRA) International | P. Bargiel | SIL4 | INT 2.9.1 | INT 2.10.0 | see FQR section 1.3.1 |

Table 2: WBS managed as Solution

### WBS managed as Work Packages

A detailed view on all WBS elements is listed in section 3.6. If a WBS below is not in scope of this solution (i.e. no change is planned on that WBS element), the initial version (and unchanged target version) is stated anyway.

| Solution: | ATRENOA98-E0 |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| WBS | Ident. | WPM | Initial Version | Target Version | Target date |  |
| ATRENOA98-E0.WP3.2. [WP-ID].OST | OREST | T. Neiger / TEJT | 15.00 | 15.02 | Milestone TQR1 |  |
| ATRENOA98-E0.WP3.2. [WP-ID].EBO | EBO2 | G. Barna / TEJM | INT_22.06 | INT_23.02 | Milestone TRR1-3 |  |
| ATRENOA98-E0.WP3.2. [WP-ID].EEC | NIC | K. Aichner / TEPR | NIC_HU_1.0.5 | NIC_HU_1.0.6 | Milestone TRR1 |  |
|  | SEC | K. Aichner / TEPR | SEC INT 2.0.0 | SEC INT 2.0.1 | Milestone TQR1 |  |
| ATRENOA98-E0.WP3.2. [WP-ID].ELE | ELEKTRA | P. Bargiel / TEJR | INT_22.06 | INT_23.02 | Milestone TQR1 |  |

Table 3: WBS managed as Work Packages

### Other component versions this engineering solution is based on

| Component |  | Version |  |
| --- | --- | --- | --- |
| Generic Product version |  | PV GEN 2.19.2 |  |
| MMI setup |  | MMI_SETUP_V3.2 |  |
| ESM |  | 2.1.1.2 |  |
| NIC |  | NIC HU 1.0.6 |  |
| consist of | EEC components | See below *) |  |
|  | NIC HW GEN | 1.0.3 |  |
| SEC |  | SEC INT 2.0.1 |
| consist of | EEC SW ITC *) | 3.2.1 |
|  | EEC SW GEN *) | 3.2.1 |
|  | EEC HW ITC *) | 2.0.1 |
|  | SEC HW GEN | 2.2.1 |
| HW Interfaces |  | included |  |
| Computing Hardware |  | MEN-D6/D10 |  |
| iLED Version |  | 1.6 |  |

Table 4: Other component versions

*) Note: Group identifier (see CMP [9]) NIC HU and SEC HU use the same EEC components EEC SW ITC, EEC SW GEN and EEC HW ITC.

## System overview

This Solution provides a safe and highly reliable solution to control the railway operation. The objective of this Solution is to upgrade the existing functionality of the product ELEKTRA International and the data preparation tool OREST with the scope as defined as follows:

- Scope of Change (SoC) [6] contains features, change requests and defect corrections which are planned to be released.

- Following items listed under Table 5 below are planned to start implementing till a stated target phase and are not part of this product version delivery. They will be tested and released in a successor product version.

| Package | ID | Description | Phase to be finished optionally |
| --- | --- | --- | --- |
| eBlock | PELINT-4563 | [INT:FL:FEA:0320] eBlock between ELEKTRA (without track code support) | Development phase |
| Forced direction change | PELINT-4387, PELINT-4706 (EBO2 part) | [INT:FL:FEA:0171] ELEKTRA 75Hz MÁV block Interface (with use of NIC) shall support the ‘forced direction change’ feature. The feature shall be realized in same way as realized with ELEKTRA and AKF (for the Station Zalaszentiván (ZIV)) | Development phase |

Table 5: Not released items in INT 23.02

The initial and target versions of this solution and their work packages for this engineering project are listed in Table 2 to Table 3. The product ELEKTRA International is described in system description [11].

ELEKTRA PV INT 2.10.0

HW component from

PV GEN

HW-IFS

Outdoor

Elements conv.

EEC SW ITC 3.2.1

Use SW from EEC GEN

Use HW from EEC GEN

ELEKTRA PV GEN 2.19.2

EEC SW GEN

3.2.1

Level1

Level2

Level3

BL INT 23.02

Use SW from PV GEN

EBO2 23.02

Use SW from PV GEN

SEC HW GEN

2.2.1

NIC HW GEN

1.0.3

EEC HW ITC 2.0.1

Figure 1: Product Breakdown Structure

## Key points

### Milestones for Solution

| Milestone | Target Date | Lead |
| --- | --- | --- |
| Business Plan Decision Review (BP DR) | 20.12.2021 | PLM |
| Kick Off (KOM) | 03.02.2022 | PM |
| Solution Orientation Review (SOR) | 20.04.2022 | SEM |
| Launch Review (LR) | See tailoring chapter 5.2 | PM |
| Development Launch Decision Review (DL DR) | Defined on level MPP | PLM |
| Solution Requirement Review (SRR) | 01.06.2022 | SEM |
| Solution Functional Review (SFR) | 01.08.2022 | SEM |
| Preliminary Design Review (PDR) | 01.08.2022 | SEM |
| Critical Design Review (CDR) | 01.08.2022 | SEM |
| Test Readiness Review 1-1 (TRR1-1)* | 15.09.2022 | SEM |
| Test Readiness Review 1-2 (TRR1-2)** | 30.11.2022 | SEM |
| Test Readiness Review 1-3 (TRR1-3)*** | 01.04.2023 | SEM |
| Technical Qualification Review 1 (TQR1) | 17.07.2023 | SEM |
| Test Readiness Review 2 (TRR2) | 17.07.2023 | SEM |
| Technical Qualification Review 2 (TQR2) | 07.08.2023 | SEM |
| Final Qualification Review (FQR) | 08.09.2023 | SEM |
| Acceptance Review (AR) | See tailoring chapter 5.2 | PM |
| Deployment Decision Review (DP DR) | Defined on level MPP | PLM |
| Closure Review (CR) | See tailoring chapter 5.2 | PM |

Table 6: Milestones

*) TRR1-1 scope of this milestone is WP Migration to PLF2.4, MEN-D10, see chapter 3.6

**) TRR1-2, scope of this milestone is WP LC Improvement package, see chapter 3.6

***) TRR1-3, scope of this milestone is WP Signal SEC HU 2.4.1, see chapter 3.6

### Deliverables

For Solution (Element) final date see Table 2. Additionally, deliverables in scope of this engineering project are listed below:

| Deliverable | Completion Date |
| --- | --- |
| Data preparation rules / directives | Milestone TQR1 |
| ClearCase views for customer data preparation containing delivered baseline and associated tools. | Milestone TQR2 |
| “Components of the Generic System” in case of generic changes. | Milestone TRR1 |
| Update of the customer documents "Maintenance and Repair" in case of changes. | Milestone TQR1 |

Table 7: Deliverables

## Relation with other plans

See Documentation Plan [1]

## Document version history

### Edition 01

Initial edition for Milestone SOR.

### Edition 02

Changes:

- Chapter 1.1.3 WPM + EBO MS update according to CMR [17]

- Chapter 1.1.4 update gen. prod. version 2.19.2 & MEN D2 de scope.

- Chapter 1.3.1 update of milestones according to CMR [16]

- Chapter 3.1.1 update of core team

- Chapter 3.1.2 update of solution team

- Chapter 3.1.4 update of CCB team like participated in last CCB meeting.

- Chapter 3.4 update of preconditions to new gen. prod. version

- Chapter 3.6 added WP PCRs for HEGL, CSLK2, ELIN PELIN according to CMR [16]

- Chapter 3.10 PELINT-4821, PELINT-4788 & PELINT-4787 testing activities are out of scope.

### Edition 03

- Chapter 1.3.1 update milestones.

- Chapter 2.1 update document versions.

- Chapter 2.3 update document name of [S24].

- Chapter 3.1 update roles QAM, VAL, ARC.

- Chapter 3.12.2 update CHILL version.

# References and terms

## Referenced documents

The relevant version of a document is referenced in the Documentation Plan [1]. Several planning documents are concurrent in progress until milestone SOR, therefore the edition 01 is referenced of Documentation Plan / Process Verification Report. Until milestone FQR the Documentation Plan / Process Verification Report for this Solution will be updated and tracked within the Version in TOL see TRN [1].

| Nr./Title | Reference | Version |
| --- | --- | --- |
| - Documentation Plan (DoP) | 3BU 15000 9179 ADAPA | 01 |
|  | TRN: 0001-0048022650 | latest |
| - Risk Report | TRN: 0001-0048070219 | latest |
| - Engineering Dashboard | TRN: 0001-0048072457 | latest |
| - Quality Management Plan, ELEKTRA 1.x & 2.x | 3BU 15000 5244 QMAPA | 06 |
| - Safety Plan, ELEKTRA 2.x | 3BU 15000 0602 DUAPA | 04 |
| - Scope of Change (SoC) | 3BU 15000 9179 QEAPA | 06 |
| - Thales Austria Software Development Tool Classification | 3BU 15000 5135 AAAPA 3BU 15000 5135 190EN | 25 01 |
| - Configuration Management Plan, ELEKTRA | 3BU 15000 3338 QMAPA | 09 |
| - Milestone Report Solution | TRN: 0001-0047675095 | latest |
| - Product Life Cycle Decision Review Report ELINT PV 2.10.x | 3BU 00603 0169 BCAPA | 01 PD02 |
| - System Description Interlocking System ELEKTRA International | 3BU 15000 9010 EDAPA | 11 |
| - Version Delivery Description, ELEKTRA Hardware | 3BU 15000 5225 ELAPA | 33 |
| - Integration and Verification Plan, ELEKTRA 2.x | 3BU 15000 0654 DUAPA | 02 |
| - Design Validation approval (DVa) project BIHAR | 3BU 61912 0001 BDAPA | 02 |
| - Design Validation Form (DVa) HEGL1 | 3BU 00603 0160 DEAPA | 09 |
| - Change Management Report PV INT 2.10.0 | 3BU 15000 9181 BCAPA | 04 |

Table 8 : Referenced Documents

## Process basis

The project is set up with the GTS Management System 2.0 Reference System, service release J.2.2.2 as process basis. Changes in this process basis (e.g. adaptation to a new service release of GTS Management System 2.0) have to be analysed, especially regarding the impact on already existing work products, and have to be documented and approved.

## Standards and procedures

| Nr./Title | Publishing Date/ Reference | Version/ Revision |
| --- | --- | --- |
| - ISO/TS 22163:2017 Railway applications — Quality management system — Business management system requirements for rail organizations: ISO 9001:2015 and particular requirements for application in the rail sector | 2017 |  |
| - EN 50128:2011 + A1:2020 + A2:2020 Railway application – Communication, signalling and processing systems – Software for railway control and protection systems | 2011/2020 |  |
| - EN 50129:2018 + AC:2019– Railway applications – Communication, signalling and processing systems – Safety related electronic systems for signalling | 2018/ 2019 |  |
| - ISO 9001 | 2015 |  |
| - EN 50126-1:2017 – Railway Applications – The Specification and Demonstration of Reliability, Availability, Maintainability and Safety (RAMS) – Part 1: Generic RAMS Process | 2017 |  |
| - EN 50126-2:2017 – Railway Applications – The Specification and Demonstration of Reliability, Availability, Maintainability and Safety (RAMS) – Part 2: Systems Approach to Safety | 2017 |  |
| - GTS Management System Process Manage Risks and Opportunities | Part of 0001-0050019330 (Chapter 8.6) | J.2.2.2 |
| - GTS Management System Process Manage Project | 0001-0050019330 | J.2.2.2 |
| - Minimum Requirements for the configuration management implementation | 87100077-CFG-GRP | 007 |
| - GTS Management System Process 6.1 DDQ-SW - Design develop and qualify the Software solution | 0001-0050019355 | J.2.2.2 |
| - GTS Management System Process Validate the Solution | Part of 0001-0050019360 | J.2.2.2 |
| - GTS Management System Process Integrate and Verify the Solution | Part of 0001-0050019360 | J.2.2.2 |
| - GTS Management System Process Design the Solution | Part of 0001-0050019360 | J.2.2.2 |
| - GTS Management System Process 9.7 CFG - Manage Configuration | 0001-0050019454 | J.2.2.2 |
| - GTS Management System Process 9.3 Control Export | 0001-0050019409 | J.2.2.2 |
| - GTS Management System Guarantee quality and manage continuous improvement | 0001-0050019226 | J.2.2.2 |
| - Protection of Group Information | 87201725-GOV-GRP-EN | 005 |
| - Personal Data Protection Policy | 87212828-GOV-GRP | 001 |
| - TAT Project Life Cycle | 83530275-DDQ-AUT-EN | 004 |
| - Document Management Rules | 83530061-DOC-AUT-EN | 010 |
| - Milestone Template Solutions | 83530019-DDQ-AUT-EN | 009 |
| - Document List and Review Matrix for engineering projects | 83530224-DOC-AUT-EN | 005 |
| - Thales Austria HSE Instruction | 83530048-HSE-AUT-DE | 019 |
| - Agile Definition SMP | 83530312-DDQ-AUT-EN | 001 |

Table 9 : Standards and Procedures

## Terms, abbreviations and acronyms

### Role abbreviations

| ARC | Architect |
| --- | --- |
| CM | Configuration Manager |
| DM | Document Manager |
| DPM | Data Preparation Manager |
| HoD | Head of Discipline |
| IVM | Integration, Verification Manager |
| PDA | Project Design Authority |
| PLA | Product Line Architect |
| PLM | Product Line Manager |
| QAM | Quality Assurance Manager |
| RAM-AM | Reliability, Availability, Maintainability Assurance Manager |
| RE | Requirements Engineer |
| RM | Requirements Manager |
| TM | Test Manager |
| SAM | Safety Assurance Manager |
| SEM | Solution Engineering Manager |
| SM | Senior Management |
| VAL | Validator |
| VER | Verifier |
| WPM | Work Package Manager |

Table 10 : Role abbreviations

### Terms, abbreviations and acronyms

| AKF | HU: Alcatel Kezelőfelület ; EN:Alcatel (Thales) user interface |
| --- | --- |
| BCWS | Budgeted Cost of Work Scheduled |
| CBB | Contract Budget Baseline |
| CCB | Configuration Control Board |
| CDR | Critical Design Review |
| CENELEC | European Committee for Electrotechnical Standardization |
| CHARM | Change and Request Management |
| CR | Change Request |
| DDQS | Design, Develop and Qualify the Solution |
| EDM | ELEKTRA Delivery Model |
| EEC | “ELEKTRA 4.0 Element Controlling” Remark: EEC is the umbrella term for the new way of controlling outdoor elements, including NIC, SEC |
| EL1 | ELEKTRA Generation 1 |
| EL2 | ELEKTRA Generation 2 |
| ESM | Electronic Storage Media |
| EV | Earned Value |
| FEA-ID | Feature Identifier from Feature List |
| FQR | Final Qualification Review |
| GEN | Generic |
| HW | Hardware |
| IFS | Interfaces |
| IVV | Integration, Verification and Validation |
| KOM | Kick of Meeting |
| M | Mandatory |
| NIC | Neighbour Interface Controller |
| N/A | Not applicable |
| O | Optional |
| PCM | Primavera Core Model |
| PCR | Problem Change Request |
| PDR | Preliminary Design Review |
| PEP | Personnel Efforts Planning |
| PiO | Put in Operation |
| PMP | Project Management Plan |
| QMP | Quality Management Plan |
| RAMS | Reliability, Availability, Maintainability and Safety |
| SE | Solution Element |
| SEC | Single Element Controller |
| SEMP | System Engineering Management Plan |
| SFR | Solution Functional Review |
| SIL | Safety Integrity Level |
| SOR | Solution Orientation Review |
| SRR | Solution Requirement Review |
| SubIT | Subsystem Integration Test |
| SW | Software |
| TAT | Thales Austria GmbH |
| TOL | Team OnLine |
| TQR | Technical Qualification Review |
| TRR | Test Readiness Review |
| TÜV | Technischer Überwachungsverein |
| WBS | Work Breakdown Structure |
| WP | Work Package |
| WPD | Work Package Description |

Table 11 : Terms, Abbreviation and Acronyms

# Solution engineering and development process

The Solution will be conducted according to GTS Management System J.2.2.2 (see also 2.2). As the GTS Management System is continuously improving, it has to be mentioned, that in the devolution of the Solution, for newly created documents within this project, the respective valid templates have to be used according to the up-to-date GTS Management System J.2.2.2 version. For maintenance and extension of existing documents the previously used template may remain.

## Organization of solution engineering

The description of the roles mentioned below can be found on the GTS Management System 2.0 Portal.

### Solution core team

| Role | Resource | Deputy Resource |
| --- | --- | --- |
| PLM | K. Schnabl / MP | W. Fuß / MP |
| PDA | A. Nemeth / TEJR | n/a |
| PM / SEM | P. Bargiel / TEJR | R. Strauß / TEJR |
| IVM | S. Bako / TEJR (starting with 01.09.2022) T. Szöke (01.02.2022 - 01.09.2022) | T. Szoeke / TEJR |
| VER* | H. Walenta / TEJS | I. Miler / TEJS |
| SAM | Ch. Sünder / TRS | F. Thun / TRS (01.02.2022 - 01.02.2023) R. Büger (starting with 1.1.2023) |
| QAM | D. Kovac / TQA (till 31.5.2023) C. Janneschitz / TQA (starting with 1.6.2023) | n/a |
| VAL | W. Luef / TRV | P. Satlek / TRV |
| RM | G. Eber / TEJS | I. Miler / TEJS |

Table 12: Core team

*) see tailoring of VER activities chapter 5.3.2

### Solution team

| Role | Resource | Deputy Resource |
| --- | --- | --- |
| PLA | W. Fuß / TCP | K. Schnabl / TCP |
| ARC | P. Kovacs / TEJR | A. Nemeth / TEJR |
| CM | J. Cutig / TEJT | G. Kocsis / TEJR |
| DM | See tailoring of DM activities chapter 5.3.3 | n/a |
| DPM | R. Kiss / TEJT | E. Müller / TEJT |
| RAM-AM | M. Scheuer / TRR | F. Moser / TRR |
| Software Engineer ELEKTRA | T. Heckenast / TEJR B. Molnar / TEJR T. Horvath / TEJR P. Hornyak / TEJR R. Kun / TEJR | n/a* |
| Tester ELEKTRA | G. Kocsis / TEJR A. Karner / TEJR G. Reif / TEJR I. Hegyi /TEJR B. Sari / TEJR V. Feher / TEJR R. Baranczo / TEJR S. Delaplace / TEJR | n/a* |
| CCB-Subit Testteam | A. Chita / TEJR D-M. Preoteasa / TEJR M. Stan / TEJR | n/a* |
| (E)EC-SubIT Testteam | M. Weigensam / TEJR V. Feher / TEJR L. Kritzl / TEJR | n/a* |
| Software Engineer EBO2 | G. Barna / TEJM M. Boronyai / TEJM Sz. Bodor / TEJM C.M. Scripca / T-RO A. Dascalu / T-RO H.A. Popescu / T-RO | n/a* |
| Software Engineer OREST | S. Krasny / TEJT D. Molnar / TEJT L. Pocs / TEJT T. Neiger / TEJT Sz. Szili-Kis / TEJT E. Müller / TEJT N. Yaneva / TEJT | n/a* |
| SAM - WP EEC SW ITC | K. Padourek / TRS | n/a* |
| SAM - WP EEC SW GEN | C. Sünder / TRS R. Büger / TRS | n/a* |
| Software Engineer – EEC | K. Aichner / TEPR A. Korlevic / TEPR | n/a* |

Table 13: Team

*) Deputy source is handled within team

### External project roles

| Role | Resource | Deputy Resource |
| --- | --- | --- |
| Safety Assessor | T. Schürer / Arsenal Race | n/a |

Table 14: External project roles

### Configuration Control Board (CCB)

| Role | Resource | Comment | M/O |
| --- | --- | --- | --- |
| PLM | see Table 12 | Budget, schedule, scope | M |
| SEM | see Table 12 |  | M |
| PDA | see Table 12 |  | M |
| SAM | see Table 12 |  | M |
| IVM | see Table 12 |  | O |
| VAL | see Table 12 |  | M |
| QAM | see Table 12 |  | M |
| HoD Project Engineering | O. Loibl / TEJ | Conflicts regarding resources in TEJ | O |
| HoD System Engineering (VER and REQ Mgmnt.) | T. Filzmoser / TEJS | VER and RM resources | O |
| HoD Route Control Projects | K. Ndue /TEJR | Development and Test resources | O |
| HoD Traffic Management Projects | G. Grossmayer / TEJM | EBO2 resources | O |
| Head of Engineering | M. Vana / TE | for priority conflicts regarding resources in TE | M |
| HoD Architecture, Technology and Innovation | H. Kantz / TEPR | EEC resources | O |
| PM HU Program | A. Zalezak | Financing operative projects | O |
| Head of Solution Design | A. Paul | Conflicts regarding PCRs from customer projects point of view | O |

Table 15: CCB

Other project team members are invited to the CCB as needed.

### Subcontractors

Not applicable in this project.

## System engineering supplies

Any reuse of a finished or purchased product will be stated in the Design Validation approval (DVa) Design Validation approval (DVa) project BIHAR[14], [15].

## Input data

See Table 4.

## Preconditions / Related solutions

| Deliverable | Completion Date | Provider |
| --- | --- | --- |
| ELEKTRA PV INT 2.9.1 (milestone TQR2) | 29.09.2022 | ATRENOA96 EL-INT 22.06 |
| Release test resources (individuals) | 15.08.2022 | ATRENOA96 EL-INT 22.06 |
| Signal SEC HU 2.4.0 - LWL Modem HW | 01.06.2022 | ATRENOA94 SEC HU 2.4.0 |
| ELEKTRA PV GEN 2.19.2 FQR | 10.03.2023 | ATRENDA92 ELEKTRA System Version PV GEN 2.19.2 |

Table 16: Preconditions

## Technical objectives

The technical objective of this Solution is to upgrade the existing functionality of product ELEKTRA International and data preparation tool OREST with developing change requests according Scope of Change (SoC) [6]. Those change requests shall be developed in a way to reuse it for all customers of product ELEKTRA International (currently on Hungarian and Bulgarian market) if applicable.

## Detailed First Level WBS for Work Packages

| WBS element ID | WBS element name | WBS element manager | Comments |
| --- | --- | --- | --- |
| ATRENOA95-E0.AC | Allocated Cost | SEM |  |
| ATRENOA95-E0.OC | Other contractual cost other | SEM |  |
| ATRENOA98-E0.WP3.GC | General Cost (Travel, Commitement, ....) | SEM |  |
| ATRENOA98-E0.WP3.BLM | BL Management | SEM |  |
| ATRENOA98-E0.WP3.DEV.LC | LC Improvement package | SEM | See SOC [6] |
| ATRENOA98-E0.WP3.DEV.MEND10 | Migration to PLF2.4, MEN-D10 | SEM | See SOC [6] |
| ATRENOA98-E0.WP3.DEV.FDC | Forced Direction Change | SEM | See Chapter 1.2 |
| ATRENOA98-E0.WP3.DEV.PCR | PCRs Bihar | SEM | See CMR [16] |
| ATRENOA98-E0.WP3.DEV.SEC241 | Signal SEC HU 2.4.1 | SEM | See SOC [6] |
| ATRENOA98-E0.WP3.DEV.EBLOCK | eBlock (without track code) | SEM | See Chapter 1.2 |
| ATRENOA98-E0.WP3.DEV.HEGL | PCRs HEGL | SEM | See CMR [16] |
| ATRENOA98-E0.WP3.DEV.CSLK2 | PCRs CSLK2 | SEM | See CMR [16] |
| ATRENOA98-E0.WP3.DEV.ELINPELIN | PCRs ELINPELIN | SEM | See CMR [16] |

Table 17: Detailed WBS

## Special need for training of system engineering team

No additional training for the Solution team is required.

## Constraints / Risks

Constraints which are not already considered in the Risk Report [2] are listed here:

The planning basis do not calculate with the correction of findings during EL2-SEC integrations test in ATRENOA96 EL-INT 22.06 project. There are risks how those findings can affect the ATRENOA98 EL-INT 23.02 timeline:

- findings need to resolve and test in ATRENOA98 EL-INT 23.02 can lead to additional effort and work package delivery delays in ATRENOA98 EL-INT 23.02.

- findings are resolved/corrected in ATRENOA96 EL-INT 22.06 can lead to later delivery and test team release from ATRENOA96 EL-INT 22.06 (= delayed start in ATRENOA98 EL-INT 23.02)

## Work Contained

Engineering of the scope mentioned in section 1.2 according to the applying parts of the relevant standards listed in section 2.3.

Delivery of the baseline documentation, including the Safety Cases.

Delivery of the items listed in section 1.3.2.

Coordination and execution of Factory Acceptance Tests (Customer labor-/integration-tests) and "resolution of item identified" - if a resolution of detected item is part of this project will be defined in the evaluation meeting. I.e. if not blocking then item can be moved to future baselines.

e) Assessment Certification for the solution. Details have to be documented in Chapter 5.1.5.

## Work not contained

While the work contained is already stated in section 3.9, the following topics are explicitly mentioned as not part of this solution in order to sharpen the responsibility:

- Coordination and agreements with non-Thales-internal customers.

Data preparation of non-testing railway stations.

On-site test (on-site access after milestone TQR1 then on-site test will be transferred to customer project).

Installation.

Industrialisation of HW components.

Any HW, product or solution development not mentioned in section 1.1.2 or 1.1.3.

Coordination and project management for SEC HU 2.5.0, is part of a separate engineering project.

Any other kind of customer- / user-documentation as described in section 3.9. The following examples are all in responsibility of PDA provided by department “Solution Design (TESD)”:

  - Update of the user document “User Manual Interlocking Bulgaria"

  - Update of the user document “User Manual Interlocking Hungary”

  - Update of the documents “Functional Requirement Specification" for Bulgaria and “[DE] Anforderungsspezifikation” for Hungary

Translation of documents from previous baselines into English.

Translation of customer documents into customer languages (Bulgaria, Hungary).

Training of new and external (Romanian, Hungarian) employees.

Requested additional Scope PELINT-4821 see CMR [17] (no SW change, only verification is open) for ALM + Hegyeshalom have PiO on 07/23, therefore the test execution and report will be performed by ATRATOA55 HEGL project, when function will be used with older PV before solution FQR see chapter 1.3.1.

Requested additional Scope PELINT-4788, PELINT-4787 see CMR [17] (SW change and verification is open) for PPL station PiO with delivery before 04/23 is not possible by this solution, planned delivery of milestone FQR see chapter 1.3.1. The SW-upgrade in SPDL2 on 04/2023 is planned with PV INT 2.9.1.

## Responsibility Assignment Matrix

The responsibilities of the roles at a Milestone Review can be seen in [S21]Milestone Template Solutions.

The milestone review TQR2 confirms the successful completion of product validation and the readiness of all needed elements for customer acceptance and that the Solution is ready for TÜV approval. The PLM confirms with the approval to milestone TQR2 that the delivered solution meets his/her expectations.

The milestone review FQR confirms that the Design, Development and Qualification activities including TÜV approval are complete and that the Solution is ready for production, deployment and transition to support.

## Tools and Facilities

The following subsections provide a rough overview of the project tool setup. For version information and tool classification see document Thales Austria Software Development Tool Classification [7].

### Management and Documentation Tools

| Tool Category | Tool | Note |
| --- | --- | --- |
| Project Management | Primavera PCM |  |
| Task Management | TIPI |  |
| Requirements Management | DOORS/RMF |  |
| Management Traceability | DOORS/RMF |  |
| Configuration Management | ClearCase Subversion Git |  |
| Change Management | CHARM on JIRA |  |
| Documentation Management | ClearCase DWF Team Online Subversion |  |
| Documentation Generation | DOORS RMF Java Doc MS Office |  |
| Build environment ELEKTRA | ClearCase ClearMake |  |
| Build environment EBO2 | Git Maven Hudson |  |
| Build environment OREST | Git ANT and Maven Sonar Jenkins |  |
| IVV Management | DOORS MS Excel |  |
| Build environment ELEPRO | ADA Compiler ClearCase |  |
| Build environment EEC | Git Maven BitBucket Jenkins |  |

Table 18: Management and Documentation Tools

### Code Building Tools

| Tool Category | Tool | Version | Note |
| --- | --- | --- | --- |
| Compiler | CHILL | 2.3.9 |  |
|  | GNU C/C++ | 4.4.7-plf2.1 | According to document 3BU_15000_5135_AAAPA |
|  | JAVA | 1.8 |  |
|  | PAMELA | 3.06 |  |
| IVV | GCOV | 3.3 |  |
|  | EPS | 05.26 |  |
|  | COTO | 01.31 |  |
|  | Audit Tools | 05.07 |  |

Table 19: Code Building Tools

# Process Control

## Control of Solution Development

The solution elements and assigned responsibilities are listed in Table 2.

### Deviation

The development of a Solution has to be planned and executed according to the DDQS Processes of GTS MANAGEMENT SYSTEM 2.0. Deviation to the description in TAT Project Life Cycle [S19] is described in chapter 5.

### Metrics

The used metrics for control of the engineering process are identified in the Engineering Dashboard [3].

The tailoring for this dashboard is listed below:

|  | Sheet | Tailoring |
| --- | --- | --- |
|  | Actions & Decisions | Used - no deviation. |
|  | Stability of Team Velocity | Used. See Note 5 below. |
|  | Visibility Point Burnup | Used. See Note 5 below. |
|  | Code Quality | Not used. |
|  | Code Reuse | Not used. |
|  | Defect management | Used. See "PCR (Problem Change Request)" |
|  | Documentation | Not used. |
|  | Finance | Used. See Note 1 below. |
|  | Interface testing progress | Not used. |
|  | IVV Test Writing | Used - no deviation |
|  | Master Plan | Used - no deviation. |
|  | Milestones | Used - no deviation. |
|  | OBS | Used - no deviation. |
|  | PCR (Problem Change Request) | Used. See Note 2 below. |
|  | Quality | Used. Data provided by QAM. |
|  | RAMS | Optional. Data provided by RAM-AM and SAM. |
|  | Release content progress | Optional. Not only features are tracked, but also legacy PCRs which are part of the scope as defined in section 1.2. |
|  | Remaining work burndown | Not used. |
|  | Requirement Analysis | Used. See Note 3 below. |
|  | Requirement Flowdown | Not used. |
|  | Sizing & critical performance | Not used. |
|  | Technical Risks | Used - no deviation. |
|  | Validate & qualify test progress | Not used. |
|  | Verification testing progress | Used. See Note 4 below. |
|  | WBS | Used - no deviation. |
|  | Workload | Used - no deviation. |
|  | Note 1: Guideline: - “BCWS Planned Spend” is the monthly planned costs of work. This value can be determined from PEP or PCM. It is the defined/updated at the time the CBB is defined or updated. - “Forecast” is the spending forecast from the last month with actuals to the end of the project (before this period it has to be empty). - “EV” is not used. |  |
|  | Note 2: Guideline: This metric deals with PCRs found in the phase “Integrate and Verify the Solution”. Hence no baseline can be given ahead. The “Raised Forecast” may be predicted after a few months of this phase from past data. |  |
|  | Note 3: Guideline: Only the table "requirements chart data" is filled out, where the - "Total number of Req.": is the sum of all approved requirements at the time of the reporting. The reporting is done every month - "Baseline": a new baseline is created, when a new release of the SSS is done and a new release label is generated in DOORS - "Analysis forecast": specifies the sum of current and new requirements. - Either a value in "Baseline" or in the "Analyses forecast" is filled out except in the current month, where both fields are filled out. Additionally to be filled out are: - "Analyzed Req.": sum of all requirements, which are analyzed and not changed - "Req. to be clarified": sum of requirements, which are currently not approved, new or changed, may not be the sum of the below attributes - "Obsolete Req": sum of requirements, which will be set to descoped - "Modified Req": sum of changed requirements - "New Req": sum of new requirements Requirements characterization can be generated via DOORS, via the menu "TRSS-AT" -> "Simple Functions" -> "KPI" -> "Input for Req. analysis tab". |  |
|  | Note 4: Guideline: Field “Req. conformity (%)” may be used as a percentage of tested and verified items of the scope defined in Scope of Change (SoC) [6]. |  |
|  | Note 5: Guideline: The monitoring of project progress within an agile development environment requires a set of metrics defined in the TAT Agile Definition [S24] document sections 9.2.1 ‘Stability of Team Velocity’ and 9.2.2 ‘Visibility Point Burnup’ and is expected by senior management to be displayed during the PPPRs. Furthermore, the tailoring of the monitoring of project progress within an agile development environment in chapter 5.4 must be taken into consideration to get an adequate information basis for the KPIs. |  |

Table 20: Metrics

## Monitoring and Control of Solution Engineering Activities

### Periodic Internal Reviews and Meetings

| Meeting | Responsible | Attendees | Frequency | Objectives |
| --- | --- | --- | --- | --- |
| periodically Core Team Meeting | SEM | Solution core team, ARC, WPM(s), PDA, IVM Only on demand: CM, RM, Program HU Mgmt., PLM, QAM | Weekly | Project status and action points. |
| Risk and opportunity review | SEM | SEM, PLM, PDA, IVM, SAM, ARC, QAM | Quarterly or on demand |  |
| Resource review | SEM | SEM, HoD Route Control Projects | monthly | Check utilisation and additional needs of solution team. |
| Cost tracking | Project controller | SEM, HoD Route Control Projects, Project Controller | monthly | Report of costs and progress to Financial Control Director. |
| Periodically Performance Project Review (PPPR) | SEM | SEM, HoD Route Control Projects, HoD Project Engineering, HoD Engineering, Program HU Mgmt. | monthly | Report of costs and progress, KPI dashboard, required decisions from SM to HoD Project Engineering, HoD Engineering, Progress Matrix |

Table 21: Reviews and Meetings

### Milestone Reviews and Audits

Milestone reviews [9]. Milestone Report Solution are done according Milestone Template Solutions[S21]. Quality Audits will be conducted through the QAM – see Quality Management Plan [4]. Safety Audits will be conducted through the SAM – see Safety Plan [5].

### Reporting

Reporting is done via the Engineering Dashboard [3] and Progress Matrix.

## Critical Technologies

Not applicable in this project.

## Risk and Opportunities Control

The Risk and Opportunities Control in this Solution will follow the GTS Management System Process Manage Risks and Opportunities [S7] and is monitored in the Risk Report [2].

## Corrective Action Process

Information about the Corrective Action Process can be found in the Quality Management Plan [4].

## Independent Evaluation and Verification

Independent evaluation and verification will be done by

- the verifier and domain experts upon instruction of the verifier (VER);

- the validator (VAL);

- the safety assurance manager (SAM).

## Estimate/Re-Estimate

The initial estimation is either an input for the phase “Orientation the Solution” or is done or verified during this phase. Re-estimation of remaining work is done during the progress of working packages typically on a monthly period. The method used for estimation is mainly “Expert estimations” based on past experience, educated assumptions and risk considerations.

## Planning

Planning is done in the tool PCM and can be found there with the identification listed in Table 1.

## Value Analysis and Design to Cost

Value Analysis and Design to Cost is done by the Engineering Dashboard [3].

## Peer Reviews

The Peer Reviews in this Solution will follow the Minimum Requirements for the configuration management implementation [S9]. An overview of mandatory Documents and Reviewer has to be done according to Document List and Review Matrix for engineering projects [S22].

# Development scenario and tailoring of the System Engineering Process

This development process follows the initialisation by GTS Management System 2.0 process Manage Product Policy (MPP) as described in TAT Project Life Cycle [S19].

Figure 2: Manage the Product Policy (MPP)

The Product Line Engineering (PLE) approach is applicable if there is a need to perform product evolution or product development without a concrete BID or if an enhancement, respectively change of a product is used for several customer contracts or markets. In this case PLE is a substitute for the process Manage Bid and guides the project over the whole project life cycle. The Product Line Manager (PLM) starts the PLE process with a Business Plan Decision Review (BP DR) and triggers the DDQS for product development.

The project will be conducted following the GTS Management System 2.0 processes Manage Project (PRJ) and Design, Develop and Qualify the Solution (DDQS) and their interfaces according to TAT Project Life Cycle [S19].

Figure 3: Manage Project (PRJ)

Figure 4: Develop and Qualify the Solution (DDQS)

The main characteristic of the time-boxed approach (see explanation below to Figure 4: ELEKTRA Delivery Model (EDM)) for DDQS is to deliver several baselines/product versions to fulfil the Business Plan. The Deployment Review uses the results of each final validation step (FQR) of the time-boxed delivered baselines/product versions.

The general approach for delivering new baselines for the product ELEKTRA is a twelve months timeboxed doubly nested one.

## Tailoring for this solution

The tailoring of the Product Line Engineering (PLE) is used as described in TAT Project Life Cycle [S19].

Due to the amount of change requests and the requested delivery dates of the stakeholder customer projects the timeboxed approach has been tailored. The defined baseline INT 22.12 has been renamed to INT 23.02.

### Orient the Solution

DVa does not apply to this A0 project. No further deviation to the description in TAT Project Life Cycle [S19].

### Design the Solution

No deviation to the description in TAT Project Life Cycle [S19].

### Develop the Solution

No deviation to the description in TAT Project Life Cycle [S19].

### Integrate and Verify the Solution

No deviation to the description in TAT Project Life Cycle [S19].

### Validate the solution

The assessment is needed for this product version. No other deviation to the description in TAT Project Life Cycle [S19].

### Documentation Management

The naming convention for the name “Firstname Lastname” of the author, verified by, approver of a document can also be “F. Lastname”.

No other deviation to the description in Document Management Rules [S20].

## Tailoring of milestones

### Manage Project Milestones

The tailoring of the Product Line Engineering (PLE) is used for this Solution as described in TAT Project Life Cycle [S19]. The Manage Project milestones are replaced by the Manage Product Policy milestones.

- Launch Review replaced by Development Launch Decision Review, in case scope have no deviation between Development Launch Decision Review and Launch Review.

- The Acceptance Review is performed by a planned acceptance test performed by the customer.

- Closure Review replaced by Deployment Decision Review.

## Tailoring of role assignments

### Role of IVVQM

The role IVVQM is not executed by a single person. The major IVVQM activities are distributed to other roles:

- Integration: is made by IVM

- Verification: is made by VER

- Validation: is made by VAL

- Qualification: is made by VAL (in case of HW development)

### Role of Verifier (VER) according CENELEC EN 50128 and EN 50129

The verification according CENELEC EN 50128 and EN 50129 of all documents is performed throw reviews by the roles defined in the review matrix [S22].The role VER is not executed by a single person. The major VER activities are distributed to other roles as also described in [13]:

- Process Verification: is made by QAM

- Final document Verification: is made by RM

- Software/Code Verification: a member from DEV team

- Deliverables Verification: is made by IVM

- Enabling systems Verification: is made by CM

- Lifecycle phases Verification: is made by VER

- Collection of Verification results in Verification-report: is made by VER

### Role of DM

The role DM is not executed by a single person. The major DM activities are distributed to other roles:

- new ANV: can be obtained by SEM

- Document Index: is made by CM or SEM

- Formal check at release of a document: is made by QAM

- Other DM activities: are made by author of the document

## Tailoring of the monitoring of project progress within an agile development environment

This chapter affects the agile working activities for the system components SEC and NIC.

The monitoring of project progress within an agile development environment requires a set of metrics defined in the TAT Agile Definition [S24] document sections 9.2.1 ‘Stability of Team Velocity’ and 9.2.2 ‘Visibility Point Burnup’ and is expected by senior management to be displayed during the PPPRs. These metrics are the basis for decision making and shall be reported by the team’s WPM or Product Owner after every sprint.

The generation of these metrics was automated in Excel (download at https://e2.at.thales/confluence/download/attachments/108463228/Agile_Metrics_Template.xlsm?api=v2), yet it expects some Jira setup in order to function correctly and to deliver insightful information. The expectations are presented below.

- A Scrum Board is defined in Jira and the team works in sprints.

- Estimations are filled in the Jira field ‘Story Points’, regardless of their real unit (complexity, days, function points etc.).

- Every issue is assigned to (at least) 2 different FixVersions (Jira Release): one for the complete project or baseline (e.g. INT23.02) and one indicating the specific deliverable (e.g. INT23.02-PDR, INT23.02-Lab1).

Figure 5: Agile Process according to TAT Agile Definition [S24]

Please note that on the example above all ‘Implementation Epics’ are linked to the ‘Deliverable/Milestone 3’, but some are also linked to the ‘Deliverable/Milestone 2’ (since the latter is just an intermediary deliverable, e.g. a Lab release, while the former represents the GTS MANAGEMENT SYSTEM milestone which includes all ‘Implementation Epics’).

# System Engineering Support

## Data and Configuration Management

Data and Configuration Management is carried out according to GTS Management System Process 9.7 CFG - Manage Configuration [S14], Document Management Rules [S20] and the specific Configuration Management plans Configuration Management Plan, ELEKTRA [8].

## Confidentiality

The rules as listed in Protection of Group Information [S17] apply.

## Export Control

Export Control is carried out according to GTS Management System Process 9.3 Control Export [S15].

## Capitalization

Capitalization is handled in the context of the related Manage Product Policy process.

## Measurements and Analysis

See section 4.

## Technical and Non-technical Requirements Management and Control

For Requirement Management the tool DOORS is used. The Requirements Manager ensures that requirements are

  - uniquely identified

  - unambiguous, testable and consistent

  - traced from origin through all systems

  - have all changes managed

The requirements manager manages changes throughout the life of the project. If requirements change, the impact will be reflected in the project plans, work products, and activities. Any inconsistencies between these customer- and/or system requirements and project plans, work products, and activities will be identified and resolved.

## Validation of Requirements

The validation is done in accordance with the Validation Qualification plans as listed in Documentation Plan [1].

## Decision Analysis and Resolution

Decision analysis and resolutions are part of design and review processes. The results are documented in design documents, review reports and in this document.

## Subordinate Plans

There are no subordinate plans.

## Quality Assurance

The Quality Assurance in this Solution will follow GTS Management System Guarantee quality and manage continuous improvement  [S16]. Additional information can be found in the Quality Management plans as listed in Documentation Plan [1].

## Certification Support Activity

See Safety Management plans as listed in Documentation Plan [1].

## HSE Plan

An HSE evaluation should be considered if for example an engineer is at the station for PiO or Test. No hardware development activities re planned within this Solution. Therefore no separate HSE Product Plan is necessary.

See Thales Austria HSE Instruction [S23].

Criteria for the Selection of Techniques and Measures

With each technique or measure in the tables there is a requirement for each software safety integrity level (SIL). In the version June 2011 of the EN50128, the requirements for software safety integrity levels 1 and 2 are the same for each technique. Similarly, each technique has the same requirements at software safety integrity levels 3 and 4. These requirements can be

“App” this column selects with “Yes” for all relevant "documentation", “technique” or “measure” for the actual project or “No” if this row isn’t mandatory for the project.

'M' this symbol means that the use of a technique is mandatory,

'HR' this symbol means that the technique or measure is Highly Recommended for this safety integrity level. If this technique or measure is not used then the rationale for using alternative techniques shall be detailed in the Software Quality Assurance Plan or in another document referenced by the

Software Quality Assurance Plan

'R' this symbol means that the technique or measure is recommended for this safety integrity level. This is a lower level of recommendation than an 'HR' and such techniques can be combined to form part of a package,

'-' this symbol means that the technique or measure has no recommendation for or against being used,

'NR' this symbol means that the technique or measure is positively “Not Recommended” for this safety integrity level. If this technique or measure is used then the rationale behind using it shall be detailed in the Software Quality Assurance Plan or in another document referenced by the Software Quality Assurance Plan.

| DOCUMENTATION | App | SIL 4 | References of Doc Type |
| --- | --- | --- | --- |
| Planning |  |  |  |
| 1. Software Quality Assurance Plan | Yes | HR | QMP |
| 2. Software Quality Assurance Verification Report | Yes | HR | QMR |
| 3. Software Configuration Management Plan | Yes | HR | CMP |
| 4. Software Verification Plan | Yes | HR | IVP |
| 5. Software Validation Plan | Yes | HR | VQP |
| Software requirements |  |  |  |
| 6. Software Requirements Specification | Yes | HR | SSS |
| 7. Overall Software Test Specification | Yes | HR | Test Plan |
| 8. Software Requirements Verification Report | Yes | HR | VoR and review reports of SSS documents |
| Architecture and design |  |  |  |
| 9. Software Architecture Specification | Yes | HR | SSDD |
| 10. Software Design Specification | Yes | HR | SSDD |
| 11. Software Interface Specifications | Yes | HR | SSDD |
| 12. Software Integration Test Specification | Yes | HR | TCS |
| 13. Software/Hardware Integration Test Specification | Yes | HR | TCS |
| 14. Software Architecture and Design Verification Report | Yes | HR | Verification Report |
| Component Design |  |  |  |
| 15. Software Component Design Specification | Yes | HR | SDD |
| 16. Software Component Test Specification | Yes | HR | SSCTR |
| 17. Software Component Design Verification Report | Yes | HR | Review reports of design documents |
| Component Implementation and Testing |  |  |  |
| 18. Software Source Code and supporting documentation | Yes | HR | ClearCase, GIT |
| 19. Software Component Test Report | Yes | HR | SSCTR |
| 20. Software Source Code Verification Report | Yes | HR | SSCTR |
| Integration |  |  |  |
| 21. Software Integration Test Report | Yes | HR | Integration Test Report |
| 22. Software/Hardware Integration Test Report | Yes | HR | Integration Test Report |
| 23. Software Integration Verification Report | Yes | HR | Verification Report |
| Overall Software Testing / Final Validation |  |  |  |
| 24. Overall Software Test Report | Yes | HR | ∑ Test Reports |
| 25. Software Validation Report | Yes | HR | Validation Report |
| 26. Tools Validation Report | Yes | HR | Tools classification report, handling of TACs in Verification Report |
| 27. Release Note | Yes | HR | VDD |
| Systems configured by application data/ algorithms |  |  |  |
| 28. Application Requirements Specification | No | HR | Not applicable since this is a generic application development. The customization of the application data for a specific application is not part of this development. |
| 29. Application Preparation Plan | No | HR |  |
| 30. Application Test Specification | No | HR |  |
| 31. Application Architecture and Design | No | HR |  |
| 32. Application Preparation Verification Report | No | HR |  |
| 33. Application Test Report | No | HR |  |
| 34. Source Code of Application Data/Algorithms | No | HR |  |
| 35. Application Data/Algorithms Verification Report | No | HR |  |
| Software deployment |  |  |  |
| 36. Software Release and Deployment Plan | Yes | HR | CMP |
| 37. Software Deployment Manual | Yes | HR | VDD |
| 38. Release Notes | Yes | HR | VDD |
| 39. Deployment Records | Yes | HR | VDD |
| 40. Deployment Verification Report | Yes | HR | Review Report of VDD |
| Software maintenance |  |  |  |
| 41. Software Maintenance Plan | Yes | HR | Feature List |
| 42. Software Change Records | Yes | HR | CHARM, DOORS |
| 43. Software Maintenance Records | Yes | HR | CHARM |
| 44. Software Maintenance Verification Report | Yes | HR | PCR Evaluation Report |
| Software assessment |  |  |  |
| 45. Software Assessment Plan | No | HR | Not applicable, External assessment is outside of PV development; therefore no evidence can be given. |
| 46. Software Assessment Report | Yes | HR | External assessment report if product version will be assessed |
| Documents 29, 30 and 31 being HR or R depends on the importance defined in the process and where the verification takes place. E.g. data may only be needed to be verified but tested in the system domain while more functional properties need both test and verification. In this case HR has been marked but can be optional R. |  |  |

Table A1 Lifecycle Issues and Documentation (EN50128, A.1)

| TECHNIQUE/MEASURE | App | SIL 4 | Remark |
| --- | --- | --- | --- |
| 1. Formal Methods (based on a mathematical approach) | No | HR | Method is not applied. See requirement 2) at the bottom of this table. For this product “structured methodology” is chosen as applied technique. |
| 2. Modelling | No | HR | Method is not applied. See requirement 2) at the bottom of this table. For this product “structured methodology” is chosen as applied technique. |
| 3. Structured methodology | Yes | HR | Based on requirements tool DOORS, system engineering methodology as addressed via GTS Management System and engineering guidelines |
| 4. Decision Tables | No | HR | Method is not applied. See requirement 2) at the bottom of this table. For this product “structured methodology” is chosen as applied technique. |
| Requirements: 1) The Software Requirements Specification shall include a description of the problem in natural language and any necessary formal or semiformal notation. 2) The table reflects additional requirements for defining the specification clearly and precisely. One or more of these techniques shall be selected to satisfy the Software Safety Integrity Level being used. |  |  |  |

Table A2 Software Requirements Specification (EN 50128, A.2)

# END OF DOCUMENT

The HW- components, interfaces and Outdoor Elements conventional are listed in VDD ELEKTRA Hardware [12]

For tailoring of milestones, see chapter 5.1

3 this milestone is done with the MAV-Acceptance Test

Role IVVQM is divided up into IVM and VAL.