Note to the author:

Do NOT edit this page (cover).

It will be updated by GBMS team.

Note to the author:

Do NOT edit this page (cover).

It will be updated by GBMS team.

Manage Project RAMS and Independent Validation Activities

G-prc s06001 rev.03

Manage Project RAMS and Independent Validation Activities

G-prc s06001 rev.03

| GBMS 2.0 | COUNTRY |
| --- | --- |
|  | ALL |
| Document TYPE | LANGUAGE |
| TEMPLATE based on G-TMP A01008 rev.04 <applies to the new/updated G/L-PRC> | EN |

REVISION HISTORY

| Rev. | Date | Author | Approver | Authorizer | Revision Description |
| --- | --- | --- | --- | --- | --- |
| 00 | Mar 2022 | C. Bortone | R. Castagna | P. Marmo | First Issue |
| 01 | Nov 2024 | S. Espin Oscar | R. Castagna | P. Marmo | Aligned actions PRM-02, PRM-06 and PRM-18 with G-MNL A1300 (BIM Governance for S&T Projects) |
| 02 | Apr 2025 | C. Bortone S. Espin Oscar | R. Castagna | P. Marmo | Updated PRM-15 action to include guidelines on Inspection Checklist and Report. |
| 03 | XXX 2026 | G. Di Grazia C. Bortone O. Samuel Espin | R. Castagna | O. Hochheid | Update for GBMS 2.0, (includes action BID-01 and TSI-38 well as split for PRM actions into PLN, SAF, RAM, IVL and MON) |

DOCUMENTS TREE

- -PRD S06000 RAMS

  - G-KPI S06001 RAMS KPIs

  - G-PRC S06001 Manage Project RAMS and Independent Validation Activities

TABLE OF CONTENTS

1	SCOPE	6

1.1	Purpose	6

1.2	Applicability	6

1.3	Effective Date	6

2	TERMS	7

2.1	Acronyms and Abbreviations	7

2.2	Definitions	8

3	REFERENCES	12

3.1	Hitachi Corporate Reference Documents	12

3.2	GBMS Reference Documents	12

3.3	Applicable Standards and Regulations	13

4	DESCRIPTION	14

4.1	RAMS Bidding	14

4.1.1	Contribute to bid (BID-01)	14

4.2	Set Up RAMS and IVAL Team	14

4.2.1	Assign the Project RAMS Manager (SUP-02)	14

4.2.2	Participate to the Kick-off meeting (SUP-03)	15

4.2.3	Define the Work Package structure and Project RAMS Team (SUP-04)	15

4.3	Plan RAM, Safety, IVAL and V&V Activities	16

4.3.1	Review the Initial Contract and Risk & Opportunities (PLA-05)	16

4.3.2	Identify expenditures/commitments before PHA/PAM (PLA-06)	16

4.3.3	Define the Project RAMS and IVAL Schedule (PLA-07)	16

4.3.4	Project Budget and Workload (PLA-08)	17

4.3.5	Manage RAM, Safety, IVAL and V&V Plan development (PLA-09)	18

4.4	Perform RAM, Safety and IVAL Activities	19

4.4.1	Perform Generic Activities	19

4.4.2	Perform Safety Activities	26

4.4.3	Perform RAM, LCC and FRACAS Activities	27

4.4.4	Perform Independent Validation Activities	28

4.5	Monitor RAM, Safety and IVAL Activities	31

4.5.1	Monthly/Quarterly Project Reviews (MON-32)	31

4.5.2	Periodical Coordination Meetings (MON-33)	31

4.5.3	Project RAMS Schedule and Workload Update (MON-34)	32

4.5.4	Periodical Risk Review (MON-35)	32

4.5.5	Project RAMS and IVAL Reporting (MON-36)	33

4.5.6	Key Performance Indicators (MON-37)	33

4.6	Manage Safety Incidents	33

4.6.1	Manage Safety Incidents (TSI-38)	33

5	RECORDS	35

6	ANNEXES	36

Annex 1 - Executive Summary	36

Annex 2 - Tailoring Matrix Guidelines	41

Annex 3 – PRM context diagram	43

Annex 4 – Project Execution - RAMS 2nd level Organizational chart	44

# SCOPE

## Purpose

This document describes how to plan, execute, monitor, and control the Signalling and Rail Solutions (SRS) project Independent Validation, Reliability, Availability, Maintainability and Safety (RAMS) activities pertaining to the Signalling and Rail Solution (systems, subsystems, parts or components), consistently with the required standards.

## Applicability

Refer to the table below for the applicability of this document.

| Legal Entities | All RSBU Legal Entities |
| --- | --- |
| Line of Business (LoB) | Signalling and Rail Solutions (SRS) |
| Project/Bid Type/Criteria | Applies to all projects (R&D, Customer, Products & Solutions Roadmap, Service, etc.). |
| Additional Criteria and Notes | None |

## Effective Date

This document is applicable as soon as it is published.

# TERMS

## Acronyms and Abbreviations

| BS | Business Segment |
| --- | --- |
| CBS | Cost Breakdown Structure |
| CCB | Change Control Board |
| CR | Change Request |
| FM | Functional Manager |
| GA | Generic Application |
| GP | Generic Product |
| ISA | Independent Safety Assessor |
| IVAL | Independent Validation |
| JV | Joint Venture |
| KPI | Key Performance Indicator |
| LoB | Line of Business |
| MoM | Minutes of Meeting |
| MPR | Monthly Project Report |
| MWPM | Main Workpackage Manager |
| PAM | Project Approval Meeting |
| PDM | Product Data Management |
| PE | Project Engineer |
| PHA | Project Handover Assessment |
| PJC | Project Controller |
| PJP | Project Planner |
| PM | Project Manager |
| PMP | Project Management Plan |
| PQM | Project Quality Manager |
| PQMP | Project Quality Management Plan |
| PRM | Project RAMS Manager |
| PTS | Purchase Technical Specification |
| QPR | Quarterly Project Review |
| RAM | Reliability, Availability, and Maintainability |
| RAMS | Reliability, Availability, Maintainability, and Safety |
| RSA | Railway Safety Authority |
| RSBU | Railway Systems Business Unit |
| SA | Specific Application |
| SIG | Signalling |
| SoW | Scope of Work |
| SRAC | Safety-Related Application Condition |
| SyRS | System Requirements Specification |
| SSyRS | Subsystem Requirements Specification |
| S&P | Sales & Projects |
| SRS | Signalling and Rail Solutions |
| TxCR | Technical Change Request |
| V&V | Verification & Validation |
| WBS | Work Breakdown Structure |
| WP | Work Package |
| WPL | Work Package Leader |
| WPM | Work Package Manager |
| WPX | WPM or WPL |

## Definitions

| CBTC RAMS WPM/WPL | Member of RAMS Function organizational unit, appointed for the project with responsibility for CBTC technology related Safety activities. |
| --- | --- |
| CBTC V&V referent | Member of CBTC BS organizational unit, appointed for the project with responsibility for CBTC signalling technology related V&V activities. |
| Deliverable | A deliverable is any unique and verifiable output (product, service, or result) produced upon the completion of a process or a specific process step. |
| ERTMS V&V referent | Member of Wayside/Onboard BS organizational unit, appointed for the project with responsibility for ERTMS signalling technology related V&V activities. |
| External Provider | Provider that is not part of the RSBU organization. |
| Functional Manager | Managers/Head of an organizational unit providing resources to the project. |
| GP RAMS WPM/WPL | Member of RAMS Function organizational unit, appointed for the project with responsibility for Product technology related Safety activities. |
| GP V&V referent | Member of Wayside/Onboard BS or CBTC BS organizational units, appointed for the project with responsibility for the V&V activities related to the product of competence. |
| Handover Dossier | Collection of all available contractual and tender documents relevant to the project. |
| Independent Validation | Is the activity, based on the analysis of objective evidence, responsible for providing a judgment that determines whether a Signalling and Rail Solution (system, subsystem, part or component), fulfils its intended use, in a safe, reliable, maintainable, and available manner, with emphasis on the suitability of its operation in accordance to its purpose, when placed in its intended environment. |
| IXL V&V referent | Member of Wayside/Onboard BS organizational unit, appointed for the project with responsibility for IXL signalling technology related V&V activities. |
| IVAL WPM/WPL | Member of RAMS Function organizational unit, appointed for the project with responsibility for Independent Validation activities, eventually in addition to other responsibilities for RAM or Safety. |
| Main Work Package Manager | Level 1 reporting to the Bid or Project Manager, accountable for the first level of breakdown of the WBS (often related to an overall function such as RAMS) |
| Onboard RAMS WPL | Member of RAMS Function organizational unit, appointed for the project with responsibility for Onboard signalling technology related Safety activities. |
| Onboard V&V referent | Member of Wayside/Onboard BS organizational unit, appointed for the project with responsibility for Onboard signalling technology related V&V activities. |
| Organisation | Person or group of people that has its own functions with responsibilities, authorities and relationships to achieve its objectives (ISO 9000:2015). |
| Product Data Management | Function within product lifecycle management to manage and publish product data. |
| Project | Unique process, consisting of a set of coordinated and controlled activities with start and finish dates, undertaken to achieve an objective conforming to specific requirements, including the constraints of time, cost and resources (ISO 9000:2015). |
| Project Team | A dedicated team of resources from all the functions involved in the delivery activities, led by the Project Manager. |
| Project Team Member | A dedicated Project Team resource involved in delivery activities, acting as the project interface to their related organisational function, reporting functionally to the Project Manager and hierarchically to their Functional Manager. |
| Provider | Organization that provides a product or a service (ISO 9000:2015). |
| RAM and Safety Approver | Entity responsible for one or more RAM & Safety Approval activities. |
| RAM and Safety Main Approver | Entity accountable for the RAM & Safety Approval activity. For Document type WPRs, the Main Approver is the one configured as RAM & Safety Approver in the PDM system and responsible for sending the document to the other RAM & Safety Approvers. |
| RAM WPM/WPL | Member of RAMS Function organizational unit, appointed for the project with responsibility for all RAM related activities. |
| RAMS WPM/WPL | Member of RAMS Fucntion organizational unit, appointed for the project with responsibility for RAM and/or Safety related activities. |
| Safety WPM/WPL | Member of RAMS Function organisational unit, appointed for the project with responsibility for the Turnkey System, Wayside, Onboard, CBTC or Product activities according to the project Scope of Work. |
| Signalling System RAMS WPM/WPL | Member of RAMS Function organizational unit, appointed for the project with responsibility for Signalling System related Safety activities. |
| System RAMS WPM/WPL | Member of RAMS Function organizational unit, appointed for the project with responsibility for Turnkey System related Safety activities. |
| System Validator | Member of relevant BS organizational unit, appointed for the project with responsibility for the planning of System Verification and Validation activities, for the integrated System, and for any relevant subsystem. |
| V&V referent | Member of relevant BS organizational unit, appointed for the project with responsibility for V&V activities. |
| Wayside RAMS WPM/WPL | Member of RAMS Function organizational unit, appointed for the project with responsibility for Wayside Safety related activities. |
| Work Breakdown Structure (WBS) | A hierarchical breakdown of the scope of work of the project into activities/work units, down to the basic elements. |
| Work Package (WP) | A deliverable or project work component at the lowest level of each branch of the Work Breakdown Structure. |
| Work Package Leader (WPL) | Responsible for the delivery of a Work Package specific to a functional area; WPL reports to the relevant Project Team key member (WPM). |
| WPM/WPL SIG | Member of relevant BS organizational unit, appointed for the project with responsibility for Design and/or Generic Application and/or Specific Application related activities. |
| Work Package Manager | Level 2 or lower to the Bid or Project Manager, reporting to a MWPM or another WPM with accountability for a section of the WBS and the management of subordinate work packages. |

# REFERENCES

## Hitachi Corporate Reference Documents

Unless otherwise noted, references apply to the latest approved revision.

| {code rev.XX} | {Title} <optional> Location: {add link to web page containing document} |
| --- | --- |

## GBMS Reference Documents

Unless otherwise noted, references apply to the latest approved revision.

| G-PRD S06000 rev.02 | SRS RAMS |
| --- | --- |
| G-KPI S06001 rev.00 | SRS RAMS KPIs |
| G-TRN S06001 rev.00 | SRS RAMS Transition Rules |
| G-PRC S06002 rev.00 | Manage Safety Activities * Under harmonisation |
| G-PRC S06003 rev.00 | Manage RAM, LCC and FRACAS Activities * Under harmonisation |
| G-TRN A08001 rev. 00 | RSBU Project Team Organisation Transition Rules |
| G-PRC G0503 rev.00 | Audit Programme, Audit Conduction and Auditors Management * Process yet to start harmonisation |
| G-PRC K0401 rev.01 | Project Management Activities |
| G-PRC S0101 rev.00 | Interface Management * Process yet to start harmonisation |
| G-PRC S0201 rev.00 | Configuration Management Activities * Process yet to start harmonisation |
| G-PRC S0402 rev.00 | Design Review * Process yet to start harmonisation |
| G-PRC S0701 rev.00 | WPR Verification * Process yet to start harmonisation |
| G-PRC S0702 rev.00 | WPR Validation * Process yet to start harmonisation |
| G-PRC S0703 rev.00 | Technical Verification and RAM and Safety Approval at System and Subsystem level * Process yet to start harmonisation |
| G-FOR S0702 rev.00 | RAM & Safety Approval Report * Process yet to start harmonisation |
| G-PRC K02001 rev. 01 | Bid Qualification |
| G-PRC K02002 rev. 02 | Bid Preparation and Approval |
| G-PRC K02003 Rev. 01 | Bid Submission and Contract Signature |

## Applicable Standards and Regulations

| ISO 9000:2015 | Quality management systems - Fundamentals and Vocabulary |
| --- | --- |

# DESCRIPTION

## RAMS Bidding

### Contribute to bid (BID-01)

According to project complexity and scope of work, the relevant RAMS Regional Manager may appoint a bid PRM from their team, involve the relevant RAMS BS Manager for appointing a bid PRM from their team (for multi-Entity projects) or suggest a Functional Manager (FM) from the main RAMS units involved on the project to appoint a RAMS WPM acting as a bid PRM.

The bid PRM, in accordance with the assigned bid Scope of Work (SoW), defines a bid Work Package (WP) structure and shares it with all accountable RAMS FMs, asking for a RAMS Work Package Manager or Leader (RAMS WPM or WPL) for each identified WP.

During the bid, the appointed bid PRM and RAMS and IVAL WPM/WPLs define the RAMS and IVAL strategy and approve the conceptual Bid solution of the System/Subsystem accordingly. They produce the relevant Technical Bid RAMS, IVAL and LCC (if applicable) documentation, RAMS and IVAL bid estimates with related list of assumptions, risk & opportunities, are to be submitted as an integral part of the overall Bid Proposal (see G-PRC K02001, G-PRC K02002 and G-PRC K02003 respectively for bid qualification, preparation and submission detailed tasks).

When requested by tender requirements, a bid Project Assurance Manager shall be designated; depending on the contract and complexity, the role could be taken by the bid PRM but it is a different role (bid PRM could be considered a layer 2 role in case the bid Project Assurance Manager is requested). While neither responsible nor accountable for the definition of technical requirements, the bid Project Assurance Manager responsibility deals with governing the relevant system engineering project processes supported by the relevant stakeholders (including the accountable for Safety and RAM).

Main inputs for this activity: Tender Documents.

## Set Up RAMS and IVAL Team

### Assign the Project RAMS Manager (SUP-02)

For awarded contracts, a dedicated Project Team is assembled by the appointed Project Manager (PM). According to G-PRC K0401, the PM requests the involved RAMS Regional Manager to appoint a Project RAMS Manager (PRM) as Project Team key member from RAMS (first layer of the Project Team).

According to project complexity and scope of work, the relevant RAMS Regional Manager may appoint a PRM from their team, involve the relevant RAMS BS Manager for appointing a PRM from their team (for multi-Entity projects) or suggest a Functional Manager (FM) from the main RAMS units involved on the project to appoint a RAMS WPM acting as a PRM.

According to G-TRN_A08001, it must be ensured that a single individual (MWPM) maintains ultimate accountability even in complex cross Business Segment, or cross Legal Entity projects.

The PRM directly interacts with the Project Team members (e.g. Project Engineer (PE), PM) and with external parties (i.e. Suppliers, Independent Safety Assessor (ISA), the Customer, the Railway Safety Authority (RSA), JV partners), as shown in Annex 3 – PRM context diagram.

When requested by the contract, a Project Assurance Manager shall be designated; depending on the contract and complexity, the role could be taken by the PRM but it is a different role (PRM could be considered a layer 2 role in case the Project Assurance Manager is requested). While neither responsible nor accountable for the definition or validation of technical requirements, the Project Assurance Manager responsibility deals with governing the relevant project system engineering processes, interfacing external stakeholders (e.g. client) supported by the relevant internal stakeholders (including the accountable for Safety and RAM).

### Participate to the Kick-off meeting (SUP-03)

The staffed PRM participates with all the members of the Project Team to the project kick-off meeting launched by the Project Manager.

In advance of the kick-off meeting, the PM distributes the Handover Dossier (see definition in §2.2) to the Key Project Team Members.

During this meeting, the PRM discusses with the other Key Project Team Members the main contract/project information, such as Project Presentation, product configuration, Contract Terms & Conditions, Contractual Project Master Schedule, Key Milestones, Tender WBS, Whole Life Financials and Assumptions, Risks & Opportunities.

Main inputs for this activity: Handover Dossier.

### Define the Work Package structure and Project RAMS Team (SUP-04)

The PRM, in accordance with the assigned Scope of Work (SoW), defines a Work Package (WP) structure and shares it with all accountable RAMS FMs, asking for a RAMS Work Package Manager or Leader (RAMS WPM or WPL) for each identified WP. The RAMS FMs have to ensure that resources assigned to the project are adequately skilled and qualified to undertake the allotted tasks.

The RAMS WPs/WPXs structure depends on the project type and involved technologies (see Annex 4 – Project Execution - RAMS 2nd level Organizational chart).

Main inputs for this activity: Handover Dossier.

## Plan RAM, Safety, IVAL and V&V Activities

### Review the Initial Contract and Risk & Opportunities (PLA-05)

Once the Project RAMS and IVAL team organization has been set-up, the PRM holds a start-up meeting to address the RAMS and IVAL activities of the project.

The PRM drives the analyses for the contract and project requirements, in order to share within the Project RAMS and IVAL Team the SoW, Contract Terms and Conditions, Contractual Project Master Schedule, Project WBS, stakeholder’s analysis (e.g. ISA, RSA, etc..), and reviews the assumptions defined during the Bid Phase to confirm the match. In case of inconsistencies and/or assumptions no longer valid, the PRM shall consult the PM and the PE.

The PRM records key discussions and decisions taken during the meeting in a MoM, which is then distributed to the RAMS and IVAL Team members and stored on the project’s document management and team collaboration tool.

Main inputs for this activity: Handover Dossier.

### Identify expenditures/commitments before PHA/PAM (PLA-06)

As per G-PRC K0401, the Project RAMS and IVAL Team identifies and quantifies all those activities to be launched in advance of Project Handover Assessment (PHA) (and Project Approval Meeting (PAM), if needed) because necessary to ensure project start-up and the execution of urgent and critical activities to meet project milestones.

The PRM provides costs to the Project Controller (PJC) who collects and analyses all above data and submits them to the PM for validation and budget approval.

Main inputs for this activity: Handover Dossier.

### Define the Project RAMS and IVAL Schedule (PLA-07)

At an early project stage, the PRM coordinates with the RAMS and IVAL WPM/WPLs to define a Second Level Schedule relevant to all the activities to be executed during the whole project lifecycle. The scheduled activities shall meet the project milestones, project requirements, and respective RAMS and IVAL targets, in alignment with the Project Master Schedule prepared by the Project Planner (PJP), and the budget agreed by the PM.

The overall RAMS and IVAL schedule shall reflect the agreed WPs structure. Therefore, the RAMS and IVAL WPM/WPLs shall cooperate with the PRM and the PJP to define the schedule of RAMS and IVAL activities related to their own WPs, according to G-PRC K0401. The PRM is accountable for sharing the RAMS and IVAL schedule with the PM in order to integrate it within the Project Master schedule.

RAMS WPM/WPLs are accountable for the RAMS schedule related to their own WP.

The responsibility for V&V activities schedule belongs to the WPM/WPL SIG (supported by the V&V Referents) for the subsystems and to the System Validator for the system. RAMS and IVAL WPM/WPLs shall check that V&V activities have been planned, detailed, and integrated within the Project Master Schedule.

The PRM, with the support of RAMS and IVAL WPM/WPLs, have to analyse the Project Master schedule to:

- identify any criticalities affecting the inputs needed to perform the safety and IVAL activities. RAMS and IVAL WPM/WPLs shall notify each identified criticalities to the relevant project stakeholder (e.g. WPM/WPL SIG), with the related impact;

- confirm with the WPM/WPL SIG/System Validator whether the schedule for the V&V activities is adequate. RAMS WPM/WPLs, depending on their work breakdown structure level (Signalling/System/Subsystem), shall discuss with the WPM/WPLs SIG/ System Validator/V&V referents any identified criticality (e.g. related to insufficient time or to missing inputs for V&V activities) to identify an agreed action on the Project Master schedule. If no agreement can be reached, these criticalities shall be escalated by the RAMS WPM/WPLs to the PRM and by the WPM/WPLs SIG/System Validator to the FMs responsible for V&V activities within the Global Signalling Unit’s organisational unit of competence or the System Validator’s FM, as appropriate.

Main inputs for this activity: Handover Dossier, Consolidated WBS and CBS, Budget, Second Level Schedule, Project Management Plan.

### Project Budget and Workload (PLA-08)

The PRM is accountable for the management of project budget and workload, related to RAMS and IVAL activities, supported by the RAMS and IVAL WPM/WPLs, each for the WPs under own responsibility. This includes analysing, reporting and monitoring the estimated RAMS and IVAL activities workload, on the basis of the project WBS structure detailed up to appropriate level (e.g. WBS level 5).

This is needed to control the project RAMS and IVAL activities in relation with the budget, the cost to complete and the actual cost spent on each WP. Furthermore, the PRM requests RAMS FMs to allocate the resources on the project according to the agreed workload.

The estimated workload related to each WP, included within the project WBS structure, has to be defined by the RAMS and IVAL WPM/WPLs and the System Validator, keeping the PRM informed.

The V&V budget and workload responsibility belongs to the WPM/WPL SIG (supported by the V&V Referents) and to the System Validator, who shall acknowledge the RAMS and IVAL WPM/WPL of the related technology and the PRM, in order to check that the resources to perform the activities are adequate.

RAMS and IVAL WPM/WPLs are responsible for evaluating the RAMS budget/workload adequacy related to their own WP. Instead, as per G-PRC S0702, the V&V Referents/System Validator are responsible for defining and updating the V&V budget and workload related to their own WP.

RAMS WPM/WPLs/PRM shall check with WPM/WPLs SIG/System Validator if the V&V budgets are deemed adequate by them. If any criticality (e.g. related to an insufficient budget) is shared, these criticalities shall be escalated to the PRM as appropriate.

RAMS and IVAL WPM/WPLs are responsible to provide the PRM with budget estimations for the activities in their scope. The PRM is responsible to provide such estimations to the PM. WPL SIG are responsible to collect the budget estimations from the V&V Referents of the related technology.

Moreover, the PRM is responsible to collect the RAMS and IVAL WPM/WPLs contributions to the project budget Actuals and Forecasts definition or update, according to PM requests. In addition, such information is reported to SRS RAMS FMs.

Main inputs for this activity: Handover Dossier, Consolidated WBS and CBS, Budget, Second Level Schedule, Project Management Plan.

### Manage RAM, Safety, IVAL and V&V Plan development (PLA-09)

Based on project milestones requiring RAM, Safety and V&V activities and deliverables, the PRM shall guarantee that, drafted on standard templates, are developed:

- System and Subsystems RAM Plan (see G-PRC S0603),

- Safety Plan (see G-PRC S0602),

- Independent Validation Plan,

- Verification and Validation Plan.

The purpose of these plans is to define the RAM, Safety, IVAL, and V&V processes and respective related activities to be performed during the project lifecycle, in order to provide the evidence that the required RAM, Safety, IVAL and V&V requirements have been met. Regarding project safety organisation, role independency requirements are foreseen where applicable according to norms (see G-MNL A0800 and G-TRN A08001).

The RAMS and IVAL WPM/WPLs are responsible for the RAM, Safety and IVAL Plans, while the V&V Referents/System Validator are responsible for the definition and delivery of V&V Plans. According to contract, applicable norms or any major project changes occurred during lifecycle, the RAM, Safety and IVAL Plans shall be updated at any time. Coherently, the V&V Plan shall be updated accordingly, if impacted.

All RAMS and IVAL deliverables shall be identified by RAMS and IVAL WPM/WPLs and agreed with PE by PRM (supported by RAMS and IVAL WPM/WPLs) to be recorded in the project documentation plan. Furthermore, V&V project deliverables, which are necessary inputs to the planned RAMS and IVAL deliverables, shall be identified by RAMS and IVAL WPM/WPLs from the project documentation plan and agreed with PE by PRM (supported by RAMS and IVAL WPM/WPLs) to be recorded in the project documentation plan for being issued, within PDM tool, under “RAM and Safety Approval” (see G-PRC S0701).

Main inputs for this activity: Handover Dossier, Consolidated WBS and CBS, Budget, Second Level Schedule, Project Management Plan.

## Perform RAM, Safety and IVAL Activities

### Perform Generic Activities

#### RAMS Technical Interfaces Management (PRM-10)

The RAMS and IVAL WPLs are responsible for supporting the definition and resolution of technical interfaces, from RAM, Safety and Validation point of view, related to their own WPs scope of works, in accordance with related Interfacing Party (e.g. WPM/WPLs SIG, external stakeholder). For details, see G-PRC S0101.

The PRM shall ensure that all RAMS and IVAL WPM/WPLs properly manage and monitor, from RAM, Safety and Validation point of view, the activities for their related interfaces (e.g. the Interface Control and Definition Document, validation of the traceability between SyRS and SSyRSs).

Main inputs for this activity: Contractual/Project requirements, Project Management Plan, Safety Plan, RAM Plan, IVAL Plan and V&V Plan.

#### RAMS External Providers Coordination (PRM-11)

In complex projects, e.g. as system integrator of several technologies, SRS LoB is accountable for different subcontractors providing technologies not developed by SRS LoB (e.g. Vehicles, Platform Screen Doors, SCADA, etc.). In such projects, the PRM is not accountable for all RAMS activities of the External Providers for the related integration. However, the PRM shall check, with support from the RAMS and IVAL WPM/WPLs and System Validator (the latter for the V&V documentation relevant to integrated System), the suitability of the RAMS and V&V input received from the External Providers. For example, the externally provided documents shall be checked to be coherent with the strategy in the System Integration Safety Plan, System Integration RAM Plan, IVAL Plan and System Integration V&V Plan (provided by SRS LoB to the providers of these subsystems for input and alignment).

In this context, it is necessary that the External Providers of the subsystems manage the subsystem’s RAMS and V&V related activities and documentation, including RAM analysis, Safety cases and V&V reports, according to SRS Organisation’s requirements (e.g. System allocated Safety Integrity Level requirements) and under relevant BS WPM/WPL’s coordination.

In order to guarantee the SRS LoB’s expectations, minimize ambiguities and standardize, as much as possible, the RAMS and V&V processes and related activities, the PRM, supported by the RAMS and IVAL WPM/WPLs/System Validator, shall contribute to the development of the Purchase Technical Specification (PTS) detailing:

- expected RAMS and V&V activities and deliverables;

- project contractual requirements and processes;

- timing and project schedule constraints (time to answer to comments, time to perform analyses and develop documentation, etc.);

- tools to be used for the project;

- internal and external standards to comply with.

The PRM, RAMS and IVAL WPM/WPLs and System Validator are responsible for sharing relevant project related documentation with all external providers, including but not limited to:

- System RAM, Safety, IVAL and V&V Plans;

- System RAM and Safety Allocation documents;

- Hazard Management Process;

- SRACs Management Process;

- System Analyses for emergency and evacuation scenarios;

- All comments, for each specific provider, sent by External Parties (e.g. Customer, ISA).

The PRM and RAMS and IVAL WPM/WPLs are responsible to constantly monitor, with support from relevant BS WPLs, that the RAMS and V&V activities performed by External Providers are compliant with the PTS. In case of discrepancy, PRM is responsible to inform the PM.

The PRM, supported by RAMS and IVAL WPM/WPLs, may either propose and agree External RAM and Safety process project audits directly with PQM, or put (through Regional RAMS Referent) request to Audit & Laboratories unit for planning specific V&V process project Audits (according to G-PRC G0503).

The PRM shall support RAMS WPM/WPLs on the creation and continuous update of a Hazard Log and related management of hazards among the different subsystems. Moreover, PRM is accountable for managing formal communication with External Parties (e.g. Customer, ISA).

Main inputs for this activity: Contractual/Project requirements, Risk/Opportunity/Contingency, Second level schedule, Project Management Plan, Safety Plan, RAM Plan, V&V Plan.

#### Contract Change Request Management (PRM-12)

Contractual Change Request (CR) raised during the project lifecycle, affecting either the SoW, cost, or schedule baselines (e.g. changes requested by Customer, planned technical changes), shall be managed in accordance with G-PRC S0201. The PRM and the RAMS and IVAL WPM/WPLs shall analyse any required extra effort and provide a project impact evaluation, including any increase in cost and time, related to the RAMS and IVAL activities. Any identified budget shortfall shall be formally reported by the PRM to the PM (by TxCR tool or per the specific project rules); the CR shall be monitored up to the formal extra budget approval (or rejection) and inclusion within the Project RAMS and IVAL budget by PM.

If the contract contains requirements not fully specified regarding the owner of activities or deliverables, the PRM has to inform the PM in order to resolve the issues with the Customer. This agreement includes, but is not limited to, responsibilities for activities and deliverables, required effort, required budget, and re-schedule of project milestones.

Main inputs for this activity: Contractual/Project requirements, Updated WBS/CBS/budget, Risk/Opportunity/Contingency, Second level schedule, Project Management Plan, Safety Plan, RAM Plan, IVAL Plan, V&V Plan, Authorization of Change.

#### Independent Validation implementation (PRM-13)

The purpose of the Independent Validation is to confirm, based on the analysis of objective evidence, that a Signalling and Rail Solution (system, subsystem, part or component), fulfils its intended use, in a safe, reliable, maintainable, and available manner, with emphasis on the suitability of its operation in accordance to its purpose, when placed in its intended environment  and in compliance with applicable standards, the project-relevant National Railway Authority’s rules, the SRS Organisation procedures, project requirements and the V&V Plan (in alignment with RAM and Safety Plans) delivered for the project.

The PRM and the RAMS and IVAL WPM/WPLs are responsible for monitoring the correct application of the V&V strategy, defined by the V&V teams, described in the V&V Plans and approved by RAMS (PRM or RAMS and IVAL WPM/WPL), and its adherence to the applicable standards. The monitoring may include the following activities (for further details see here):

- Inspection planning and execution and/or contribute Audit planning: depending on project complexity, budget and needs, the RAMS and IVAL WPM/WPLs/PRM shall plan and execute inspections to the project System Validator/V&V referents. Inspections shall check and confirm that the related V&V activities are well planned, executed, controlled and monitored with reference to the relevant standards. Additionally, the PRM, with the support of RAMS and IVAL WPM/WPLs may propose to the PQM and/or to the Regional RAMS Referent to request Audit & Laboratories unit to plan V&V audits specifically for the project, according to project requirements, budget and governance needs.

  - V&V inspections: V&V inspections aim to monitor the status of V&V activities in order to fulfil the Independent Validation, for every project and for every technology.

Any RAMS and IVAL WPM/WPL is responsible for the eventual planning and the execution of Independent Validation inspections for its own relevant scope. The inspections frequency can be set depending on the status of the project and can be planned and set up in agreement with the relevant WPM/WPL SIG/PE and V&V referent/System Validator. For each phase of the project, at least one inspection is recommended. The list of participants shall include:

    - For System V&V Inspection, at least the PE and the System Validator;

    - For Subsystem V&V Inspection, at least the WPM/WPL SIG and the relevant project V&V referent.

V&V inspections must be conducted using V&V inspection checklist; further topics could be added during the inspection if deemed useful or prior to the inspection, to tailor the checklist to project specificities. Independent Validation inspection plans and reports may be stored in the Project document management and team collaboration tool.

  - Audits planning:

    - The PRM, supported by RAMS and IVAL WPM/WPLs, may either:

      - propose and agree V&V process project audits directly with PQM;

      - or put (through Regional RAMS Referent) request to Audit & Laboratories unit for planning specific V&V process project Audits.

    - V&V process project audits shall be managed according to G-PRC G0503.

    - V&V process project audits may use, extend and/or tailor V&V inspection checklist.

    - V&V process project audits may include the PRM and/or RAMS and IVAL WPM/WPLs involved on the project under audit, either as technical expert or as an auditor (if qualified according to G-PRC G0503).

- Test campaigns monitoring: The PRM, RAMS and IVAL WPM/WPL could require and participate to System/Subsystems test witnessing sessions, if needed.

- Staffed resources evaluation: The PRM and the RAMS and IVAL WPM/WPLs shall confirm with FMs responsible for V&V activities and System Validator’s FM, that the V&V resources appointed for the project have been properly staffed and have the needed competences to perform the activities.

- Problem Report evaluation: As per G-PRC S0201, the RAMS and IVAL WPM/WPL shall be involved and participate in Change Control Board (CCB) meetings, to evaluate the impact of any System/Subsystems work items coming from V&V activities (e.g. Laboratory tests, site tests, data verification process) and stored into the company’s tool for bug tracking. For all the not solved work items, the RAMS and IVAL WPM/WPLs shall evaluate if they have impact on RAM or on the safety and agree a proper action with the WPM/WPLs SIG/PE.

- V&V Reports monitoring: The RAMS and IVAL WPM/WPL shall check the V&V Reports are submitted for verification (technical verification and RAM and Safety Approval), at least during the two main project phases (Design and Physical implementation phases). V&V reports shall clearly provide, along with all V&V evidences, the overall traceability amongst requirements, tests specifications and test reports.

- V&V budget and V&V schedule adequacy: the PRM and the RAMS and IVAL WPM/WPLs shall get confirmation from the WPM/WPLs SIG/System Validator about the adequacy of the scheduled V&V activities and the budgets for their execution.

PRM and RAMS and IVAL WPM/WPLs shall discuss with the WPLs SIG/System Validator, with the support of FMs responsible for V&V activities or System Validator’s FM, of any criticality identified during the monitoring of V&V activities to define the proper actions to be put in place. The PRM/relevant RAMS and IVAL WPM/WPLs shall practically monitor the issues tracking tool and its notifications and analyse them with the support from WPM/WPL SIG/System Validator/PE for risky/blocking defects detected by the validation activities. During CCB/ project meetings the relevant issues shall be raised.

Finally, the PRM and the RAMS and IVAL WPM/WPLs, in accordance with PE and/or WPM/WPLs SIG, may involve the V&V Referents/System Validator in the project internal (WPM/WPLs of other departments) and external (ISA, Customer, RSA, Suppliers, JV Partners) meetings when necessary.

Main inputs for this activity: Contractual/Project requirements, Updated WBS/CBS/budget, Risk/Opportunity/Contingency, Second level schedule, Safety Plan, RAM Plan, V&V Plan, Project RAMS and IVAL Reports.

#### Issue Management and Escalation (PRM-14)

During the Project lifecycle, both PRM and WPLs are responsible to manage all critical issues that might arise. The PRM is responsible to highlight such issues as soon as they arise and to bring them to the attention of the WPM/WPLs, PE and PM for resolution.

The PRM shall define and manage its own Issues Register, to be shared with the RAMS WPM/WPLs and stored on the Project collaborative tool. The main objective of the Issues Register is to collect all issues raised by all RAMS and IVAL WPM/WPLs and manage and track them until their resolution, evaluate their impact, assign possible owners and a due date to resolve them, before they may become a project risk.

In those instances where an issue cannot be solved at a due date, the PRM shall escalate it to his Regional Manager and provide all the support information in order to well manage the criticality.

A record of the issue arisen should be added to the Project RAMS and IVAL Report (§4.5.5).

Main inputs for this activity: Contractual/Project requirements, Updated WBS/CBS/budget, Risk/Opportunity/Contingency, Second level schedule, Safety Plan, RAM Plan.

### Perform Safety Activities

#### Manage Safety Documentation development (SAF-15)

The Safety and IVAL WPLs are responsible to develop all Safety and IVAL documents related to owned WPs, based on the project needs, and to check that they have been correctly defined and integrated within the Project Deliverables list in agreement with PE (see G-PRC S0401). As per G-PRC S0701 and G-PRC S0702, the V&V Referents/System Validator similarly are responsible for the development and submittal of V&V documents.

If, during an V&V inspection or audit (see §4.3.7) or during preparation of Safety and IVAL activities, a necessary direct input from V&V activities is considered "not available" or not approvable in “RAM and Safety Approval" step, the issue shall be timely raised to PRM (eventually escalated according to §4.3.8).

The PRM is accountable to ensure that all safety and IVAL documents, defined for the project, are issued according to the schedule, project deliverables list, and to the Safety and IVAL Plan.

The PRM, supported by the Safety and IVAL WPM/WPLs, is accountable to take action and eventually escalate in case some V&V documents input to Safety and IVAL documents have not been issued for “RAM & Safety Approval”. V&V documents input to Safety documents are expected to be issued in coherence with the Safety and IVAL Plan, project agreement and project deliverables list (as defined for the specific project, see §4.2.5) and in accordance with the schedule for the Safety and IVAL deliverables.

Hazard and Safety Analysis are safety-related project activities preceding the Safety Case, which is ultimately the document demonstrating the correctness and the safety integrity of the system/ signalling technology/signalling Generic Product (GP) under consideration. The PRM, as accountable of the Safety Case compliance with applicable standards, shall also ensure that the Safety Case includes the evidence of the quality management section to be shared and completed involving the Project Quality Manager (PQM). For details on safety-related project activities, see G-PRC S06002.

Main inputs for this activity: Contractual/Project requirements, Updated WBS/CBS/budget, Risk/Opportunity/Contingency, Second level schedule, Project Management Plan, Project RAMS Schedule, Safety Plan, RAM Plan.

#### Perform Safety Approval (SAF-16)

As per G-PRC S0701, RAM and Safety Approval of selected Work Products (WPRs) (e.g. System Requirement Specification, V&V Plans, V&V Reports, etc.) shall be performed by one or more “RAM and Safety” Approvers, under the direction of a Main RAM and Safety Approver. For document type WPRs, the results shall be recorded in PDM tool using G-FOR S0702. Please refer to G-PRC S0703 for approval criteria.

Main inputs for this activity: Contractual/Project requirements, Second level schedule, Updated WBS/CBS/budget.

#### Safety Design Reviews (SAF-17)

The PRM shall check if the Design Reviews are planned within the Project Master Schedule and executed by the PE. Besides the PRM shall check if the RAM, safety and operational suitability-related open points are correctly listed and managed. The Design Reviews shall be recorded in accordance with G-PRC S0402.

In addition, during the project lifecycle, the PRM must organize with the Project Team some dedicated meetings, in agreement with Design Reviews (see G-PRC S0402), in order to ensure that each part involved in the main project phases has acknowledged and implemented the safety conditions/implications.

All agreements, deviations, actions deriving from the above reviews should be officially reported and made available for the Customer, Operator, ISA, and Safety Authorities in a transparent way.

Main inputs for this activity: Contractual/Project requirements, Risk/Opportunity/Contingency, Project Management Plan, Safety Plan, RAM Plan, V&V Plan.

### Perform RAM, LCC and FRACAS Activities

#### Manage RAM, LCC and FRACAS Documentation development (RAM-18)

The RAM and IVAL WPM/WPLs are responsible to develop all RAM and IVAL documents related to owned WPs, based on the project needs, and to check that they have been correctly defined and integrated within the Project Deliverables list in agreement with PE (see G-PRC S0401). As per G-PRC S0701 and G-PRC S0702, the V&V Referents/System Validator similarly are responsible for the development and submittal of V&V documents.

If, during an V&V inspection (see §4.3.7) or during preparation of RAM and IVAL deliverable, a necessary direct input from V&V activities is considered "not available" or not approvable in "RAM and Safety Approval" step, the issue shall be timely raised to PRM (eventually escalated according to §4.3.8).

The PRM is accountable to ensure that all RAM and IVAL documents, defined for the project, are issued according to the schedule, project deliverables list, and to the RAM and IVAL Plan.

The PRM, supported by the RAM and IVAL WPM/WPLs, is accountable to take action and eventually escalate in case some V&V documents input to RAM and IVAL documents have not been issued for “RAM & SafetyApproval” in coherence with the RAM and IVAL Plan, project agreement and project deliverables list (as defined for the specific project, see §4.2.5) and in accordance with the schedule for the RAM and IVAL deliverables.

For Turnkey projects Subsystems RAM reports are RAM activities preparatory for the System RAM report, which is ultimately the document demonstrating the compliance with the System RAM requirements and System performance parameters. For details on RAM activities, see G-PRC S06003 ** under development.

Main inputs for this activity: Contractual/Project requirements, Updated WBS/CBS/budget, Risk/Opportunity/Contingency, Second level schedule, Project Management Plan, Project RAMS Schedule, Safety Plan, RAM Plan.

#### Perform RAM Approval (RAM-19)

As per G-PRC S0701, RAM and Safety Approval of selected Work Products (WPRs) (e.g. System Technical Specification, Maintenance Manuals, etc.) shall be performed by one or more “RAM and Safety Validation” Approvers, under the direction of a Main RAM and Safety Approver. For document type WPRs, the results shall be recorded in PDM tool using G-FOR S0702. Please refer to G-PRC S0703 for approval criteria.

Main inputs for this activity: Contractual/Project requirements, Second level schedule, Updated WBS/CBS/budget.

### Perform Independent Validation Activities

#### Perform Intended Use Analysis (IVL-20)

At the beginning of the project, the RAMS and IVAL WPM/WPLs shall review all project documents describing the project scope of work in order to get an understanding on the project scope of work, with emphasis on the its purpose and its intended environment.

#### Perform GAP Analysis (IVL-21)

The RAMS and IVAL WPM/WPLs at GA level shall review and analyse independent validation reports of other generic applications for the GA baseline selection.

#### Implement Independent Validation Planning (IVL-22)

The RAMS and IVAL WPM/WPLs shall define its activities in the RAMS and/or IVAL Plans, with the aim to plan the collection of objective evidence which demonstrates the project implementation fulfils its intended use when placed in its intended environment and report its judgement and provide its judgement and eventual approval at design, implementation project stages as well as its approval for system/sw release.

#### Perform Requirements Review (IVL-23)

The RAMS and IVAL WPM/WPLs shall review all requirements, including the traceability matrices, against the intended environment/use and judge whether all requirements are consistently traceable across user requirements, system/subsystem requirements to test cases.

#### Perform Test Specification Review (IVL-24)

The RAMS and IVAL WPLs shall review all test specifications and judge whether the verification and test cases are correctly, consistently, adequately and completely specified against the requirements and the intended environment/use.

#### Perform Design Stage approval (IVL-25

The RAMS and IVAL WPM/WPLs shall assess the compliance with the validation process of the activities performed during project design phase.

The PRM supported by the RAMS and IVAL WPM/WPLs shall judge the correctness, consistency, conformity and adequacy of the verification during design stage based on:

- Previous activities

- As required:

  - Audits and inspections performed during the project design stage

- By reviewing technical documents (specification documents, architecture and detailed design documents, safety documents, and user manuals).

- By reviewing Verification plan, verification results and more in general the compliance of verification activities performed with those planned.

#### Perform Test Result Review (IVL-26)

The Independent Validator shall review the results of verification and test execution reported in test reports and judge whether the verification and test results are correct, consistent, adequate and complete against the requirements and the intended environment/use.

To fulfil this task the Independent Validator can:

- Witness laboratory as well as site test campaigns.

- Add specific tests, if needed.

#### Perform Safety and RAM Requirements Implementation Review (IVL-27)

The Safety and IVAL WPM/WPLs shall review the project hazard logs in order to judge and make sure all hazards have been closed out in an appropriate manner, through elimination or risks control/transfer measures.

In addition, the RAM and IVAL WPM/WPLs shall review the System and Subsystem RAM reports to judge if all RAM requirements have been correctly validated.

#### Perform Defect Assessment (IVL-28)

The IVAL WPM/WPLs shall review and assess all detected deviations from specifications, with emphasis on:

- Assessment of open defects (with respect to RAMS relevance and operational impact)

- Provide a contribution to the definition of application restrictions with emphasis on keeping the suitability of operation in accordance to system/sw purpose, when placed in its intended environment.

#### Perform Physical Implementation Stage approval (IVL-29)

The IVAL WPM/WPLs shall assess the compliance of the activities performed at project physical implementation phase with the validation process.

As required, the IVAL WPM/WPLs shall judge the correctness, consistency, conformity and adequacy of the verification during physical implementation phase based on:

- Previous activities

- As required:

  - Audits and inspections performed during the project physical implementation phase.

  - Review technical documents (e.g. safety documents, and user manuals)

The IVAL WPM/WPLs shall make sure that all activities planned in the system/sw RAMS and/or IVAL plan have been carried out

#### Perform Safety and RAM Application Conditions’ Assessment and constraints definition (IVL-30)

The RAMS and IVAL WPM/WPLs shall review and assess RAM and safety-related application conditions (ACs), including the SRACs of underlying components and enabling systems (e.g. compilers, test simulators), and analyse their impact for the intended use of the product/system in the defined environment.

Based on the deviations from the plan and the open items, the RAMS and IVAL WPM/WPLs shall contribute to the definition of all the Application Conditions (Safety and Non-Safety Related) and limitations.

#### Develop Independent Validation Reporting (IVL-31)

Based on the evidence from all previous activities, as well as the review of conclusions on Safety Cases and RAM Reports, the RAMS and IVAL WPM/WPLs develop the IVAL Reportings and eventually agree with the release of the system/sw in scope.

## Monitor RAM, Safety and IVAL Activities

### Monthly/Quarterly Project Reviews (MON-32)

The PRM shall timely inform the Project Team about criticalities in the achievement of the project milestone, in order to identify corrective actions and recovery plans.

A review of the project progress is shared among all team members during dedicated Monthly Project Review (MPR) convened by the PM. Formal Quarterly Project Review (QPR) with Head of Region, involving the PE as required, are held for Key Projects only.

Upon the QPR meeting above, the PM is solely responsible for authorising any budget deviation of the Work Breakdown Structure (WBS)/Cost Breakdown Structure (CBS) from the original budget and for approving the allocation of an additional budget to Design activities.

Main inputs for this activity: Contractual/Project requirements, Updated WBS/CBS/budget, Risk/Opportunity/Contingency, Second level schedule, Safety Plan, RAM Plan, V&V Plan, Project RAMS and IVAL Reports.

### Periodical Coordination Meetings (MON-33)

Depending on the project complexity and specific requirements, the PRM may be involved on regular basis in coordination meetings with internal or external parties.

Meetings with internal parties are typically as follows:

- RAMS and IVAL project meetings held with RAMS and IVAL WPM/WPLs involving RAMS Engineers and System Validator when needed: these meetings are organized by the PRM in order to periodically analyse and report the status of the RAMS and V&V activities/deliverables and criticalities on the project. The PRM is accountable for determining the right schedule of these meetings according to the project progress and needs.

Meetings with external parties are Project meetings held with:

- Customer: can be requested periodically or case by case. Meeting contents and goals are usually defined by the Customer.

- RSA: typically done if a direct interface between SRS Organisation and RSA is required by contract. In some circumstances, only a support for these meetings is requested (e.g. by the Customer, operator, joint venture) even if SRS Organisation does not have in its scope of works a direct interface with the RSA.

- ISA: typically done if a direct interface between SRS Organisation and ISA is required. In some circumstances only a support for these meetings is requested (e.g. by the Customer, operator, joint venture etc.) even if SRS Organisation does not have in its scope of works a direct interface with the ISA.

- External Providers: in order to analyse and report the status of the activities/deliverables and criticalities for that Provider.

Main inputs for this activity: Contractual/Project requirements, Updated WBS/CBS/budget, Risk/Opportunity/Contingency, Second level schedule, Safety Plan, RAM Plan, Project RAMS and IVAL Reports.

### Project RAMS Schedule and Workload Update (MON-34)

The RAMS WPLs update the workload associated to their own WP on a monthly basis in order to:

- report all the regular changes related to the actual cost spent;

- reflect the WP economic progress and;

- reflect any possible deviations regarding the agreed project program and respective RAMS schedule.

Any deviation can have an impact on the evolution of the milestones and the respective planned workload and resources allocation. The PRM is accountable for checking if all the information provided by the RAMS and IVAL WPM/WPLs is consistent with the project needs.

In case of any deviation, the PRM and RAMS and IVAL WPM/WPLs should promptly perform a root cause analysis, evaluate the economic impact on contractual commitments, and propose a recovery plan. The PRM, even if not having the ownership of the recovery plan, is responsible for monitoring the progress of the RAMS recovery plan implementation, ensuring that all required inputs to finalize the plan are available. The PRM has to share all the impacts with the RAMS Regional Manager and the PM for approval.

In addition, this issue shall be reported in QPR and in the SharePoint issue/log register.

Main inputs for this activity: Contractual/Project requirements, Updated WBS/CBS/budget, Risk/Opportunity/Contingency, Second level schedule, Safety Plan, RAM Plan, V&V Plan, Project RAMS and IVAL Reports, Authorization of Change.

### Periodical Risk Review (MON-35)

Regular Risk Review Meetings with the Risk Manager are taken by the PM with the involvement of and support from the relevant Project Team Members.

During the Risk Review Meetings, the PRM, under the coordination of the PM and, when applicable, with support from the Risk Manager, reviews the risks in terms of rationale, economic impact, action plan, closing date. At completion of the activity, the PM updates the risk register.

Main inputs for this activity: Contractual/Project requirements, Updated WBS/CBS/budget, Risk/Opportunity/Contingency, Second level schedule, Safety Plan, RAM Plan, V&V Plan, Project RAMS and IVAL Reports.

### Project RAMS and IVAL Reporting (MON-36)

The PRM and RAMS and IVAL WPM/WPLs should report all the planning, monitoring and control activities within the Project RAMS and IVAL Report which constitutes the official tool including all the main contents and information related to the project progress in terms of:

- Project Schedule;

- Milestones evolution;

- Critical Path Inputs and Activities Management;

- Workload evolution and resource request;

- Potential critical issues management;

- Budget Progress;

- Risks and Opportunities Management.

The Project RAMS and IVAL Report shall be updated on a monthly basis by the PRM, collecting WPM/WPLs contributes. The PRM is accountable for sharing the project RAMS IVAL Report with the RAMS FMs and then with the PM, in order to face all the critical issues needing their intervention.

Moreover, a further periodic report could be required by external parties (e.g. Customer or ISA) in order to monitor the progress of RAMS and V&V activities on the project. A list of actions should be managed by PRM and RAMS and IVAL WPM/WPLs in order to trace and monitor the status of actions coming from daily activities.

Main inputs for this activity: Contractual/Project requirements, Updated WBS/CBS/budget, Risk/Opportunity/Contingency, Second level schedule, Safety Plan, RAM Plan, V&V Plan, Project RAMS and IVAL Reports.

### Key Performance Indicators (MON-37)

The SRS RAMS Incident Management and Lessons Learned Authority is responsible for reporting TSI related KPIs (see G-KPI S06001 “SRS RAMS KPI”). These are  collected in TSIDB tool according to G-PRC S06005 “Manage Technical Safety Incidents”).

Main inputs for this activity: TSIDB Tool.

## Manage Safety Incidents

### Manage Safety Incidents (TSI-38)

The SRS RAMS assess and manage functional safety-related problems, ensuring the screening, classification and governing the timely evaluation, formal investigation and implementation of safety-related actions ensuring resolution of Technical Safety Incidents. For more details see G-PRC 06005.

Main inputs for this activity: WPR Problem Report or Product Incident.

# RECORDS

The table hereafter provides the list of records relating to this document.

< Please ensure consistency among actions description, records table, and input/output section >

| Description | Identification | Retention | Retention period | Storage |
| --- | --- | --- | --- | --- |
| Minutes of Customer Meetings | As per project document numbering defined in PMP/PQMP | PRM | Project document management and team collaboration tool | Minutes of Customer Meetings |
| Inspection Reports | Sequential numbering and Project name | RAMS and IVAL WPM/WPL | Project document management and team collaboration tool | Inspection Reports |
| Project RAMS and IVAL Report | Sequential numbering and Project name | PRM | Project document management and team collaboration tool | Project RAMS and IVAL Report |

# ANNEXES

## Annex 1 - Executive Summary

| INPUTS - During Project Launch/Planning: Handover Dossier, Consolidated WBS and CBS, Budget, Second Level Schedule, Project Management Plan. Iteratively during Project Execution: Updated WBS/CBS/budget, Risk/ Opportunity/Contingency, Second level schedule, Authorization of Change. Note: Input indices are aligned with G-PRD input. Internal input - Safety Plan (see G-PRC S06002 ** under development) - RAM Plan (see G-PRC S06003 ** under development) |  |  | OUTPUTS - During Project Launch/Planning: Initial Contract and Risk Analysis review, Budget up to PHA/PAM. Iteratively during Project Execution: Regular review of Project progress and deliverables, Functional Change Impact Estimation. - External Safety/V&V Audit yearly programme. Note: Output indices are aligned with G-PRD output. |  |  |
| --- | --- | --- | --- | --- | --- |
| MEASURES As per G-TRN S06001, please refer to RMS-KPI-01, RMS-KPI-02 and RMS-KPI-03 defined in G-KPI S0601. |  |  |  |  |  |
| WORK ENVIRONMENT STANDARD < Define standard work environment (tools, infrastructures) that shall be used while performing actions. > < Please ensure consistency with the same section of the G-PRD; each tool listed here must be detailed in at least one action. > |  |  |  |  |  |
| R.A.C.I. < If procedure actors (e.g., responsible, accountable, etc.) are related to organisational Units instead of Project Team or roles required by International Standards (e.g., Verifier, Developer, Tester, etc.), please use, as appropriate, one of the following formats to point out the involved entity both in action descriptions and the R.A.C.I. table: - X Unit (e.g. HR Unit, Strategy Unit, etc.). - Role of X Unit (e.g. Head of Organisation and Development Unit, Head of Strategy Unit). Where the “X Unit” is to be addressed or reviewed from the latest Organisational chart. Please make sure to be consistent with the RACI of the parent document (PRD/PRC). > Note: each row must contain only one action. |  |  |  |  |  |
| Action ID & Name | R = Responsible | A = Accountable |  | C = Consulted | I = Informed |
| BID-01 | Tender RAMS, WPLs, Tender, PRM | Tender PRM |  | RAMS FMs, Tender PE | Bid Manager |
| SUP-02 | RAMS Regional Manager | RAMS Regional Manager |  | PM, RAMS FMs |  |
| SUP-03 | PRM | PRM |  | PM, Risk Manager, Project Team |  |
| SUP-04 | PRM | RAMS FMs |  |  |  |
| PLA-05 | RAMS WPL, PRM | PRM |  | PM, PE |  |
| PLA-06 | RAMS WPL, PRM | PRM |  | PJC |  |
| PLA-07 | RAMS WPLs, System Validator | PRM |  | PM, WPLs SIG, V&V Referents |  |
| PLA-08 | RAMS WPLs, System Validator ,PRM | PRM |  | PM, WPLs SIG, V&V Referents, RAMS FMs |  |
| PLA-09 | RAMS WPLs, System Validator | PRM |  | WPLs SIG, V&V Referents | PM |
| PRM-10 | RAMS WPLs | PRM |  | WPLs SIG, V&V Referents | PM, PE |
| PRM-11 | RAMS WPLs, System Validator | PRM |  | WPLs SIG, V&V Referents, relevant BS WPLs | PM, PE |
| PRM-12 | PRM, RAMS and IVAL WPLs, System Validator | PRM |  | WPLs SIG, V&V Referents, PM, PE |  |
| PRM-13 | PRM, RAMS and IVAL WPLs | PRM |  | WPLs SIG, V&V Referents, System Validator, PE | PM |
| PRM-14 | PRM, RAMS WPLs | PRM |  | WPLs SIG, V&V Referents, System Validator, PM, PE |  |
| SAF-15 | RAMS and IVAL WPLs | PRM |  | WPLs SIG, System Validator, V&V Referents | PM, |
| SAF-16 | Safety and IVAL WPLs | PRM |  | WPLs SIG, V&V Referents, System Validator, PE | PM |
| SAF-17 | PRM, RAMS and IVAL WPLs | PRM |  | WPLs SIG, V&V Referents, System Validator, PM, PE |  |
| RAM-18 | RAMS and IVAL WPLs | PRM |  | WPLs SIG, System Validator V&V Referents | PM |
| RAM-19 | RAM and IVAL WPLs | PRM |  | WPLs SIG, V&V Referents, System Validator, PE | PM |
| IVL-20 | RAMS and IVAL WPLs | PRM |  | WPLs SIG, V&V Referents, System Validator, PE | PM |
| IVL-21 | RAMS and IVAL WPLs | PRM |  | WPLs SIG, V&V Referents, System Validator, PE | PM |
| IVL-22 | RAMS and IVAL WPLs | PRM |  | WPLs SIG, V&V Referents, System Validator, PE | PM |
| IVL-23 | RAMS and IVAL WPLs | PRM |  | WPLs SIG, V&V Referents, System Validator, PE | PM |
| IVL-24 | RAMS and IVAL WPLs | PRM |  | WPLs SIG, V&V Referents, System Validator, PE | PM |
| IVL-25 | RAMS and IVAL WPLs | PRM |  | WPLs SIG, V&V Referents, System Validator, PE | PM |
| IVL-26 | RAMS and IVAL WPLs | PRM |  | WPLs SIG, V&V Referents, System Validator, PE | PM |
| IVL-27 | RAMS and IVAL WPLs | PRM |  | WPLs SIG, V&V Referents, System Validator, PE | PM |
| IVL-28 | RAMS and IVAL WPLs | PRM |  | WPLs SIG, V&V Referents, System Validator, PE | PM |
| IVL-29 | RAMS and IVAL WPLs | PRM |  | WPLs SIG, V&V Referents, System Validator, PE | PM |
| IVL-30 | RAMS and IVAL WPLs | PRM |  | WPLs SIG, V&V Referents, System Validator, PE | PM |
| IVL-31 | RAMS and IVAL WPLs | PRM |  | WPLs SIG, V&V Referents, System Validator, PE | PM |
| MON-32 | PRM | PM |  | RAMS WPLs |  |
| MON-33 | RAMS WPLs, System Validator | PRM |  | PM, PE |  |
| MON-34 | RAMS WPLs, System Validator | PRM |  | WPLs SIG, V&V Referents |  |
| MON-35 | PRM | PM |  | Risk Manager, Project Team |  |
| MON-36 | RAMS WPLs, System Validator | PRM |  | WPLs SIG, V&V Referents |  |
| MON-37 | SRS RAMS Incident Management and Lessons Learned Authority, SRS RAMS Head of Region | Head of SRS RAMS |  | SRS RAMS Head of Business Segment | PRM, RAMS and IVAL WPLs |
| TSI-38 | PIRT RAMS Referent, SIRT, RAMS WPL, PRM | Head of SRS RAMS |  | PIRT members, SRS RAMS Head of Business Segment/Region, Legal and Compliance unit, External Communications unit, Internal Communications unit, SRS Product QAunit, REB/CEB | SRS RAMS GPO, SRS RAMS Head of Region, PIRT members |
| Note: “Head of” is not intended as the specific job title of an individual, rather it represents the link to the latest organisational structure. < R = Responsible: those who do the work to achieve the task; A = Accountable: the one ultimately answerable for the correct and thorough completion of the deliverable or task, and the one who delegates the work to those responsible. As a general rule, only one accountable role can be specified for each task or deliverable. In case of multiple accountable roles are required, each of them shall be accountable for the steps of the action in their scope. Use a “/” to separate them. Stating a Team or a Unit as accountable is not allowed. C = Consulted: those whose opinions are sought (typically subject matter experts) and with whom there is two-way communication; Do not include people already mentioned as “responsible” or “accountable”. I = Informed: those who are kept up-to-date on progress, and with whom there is just one-way communication. Do not include people already mentioned as “responsible”, “accountable”, or “consulted”. > |  |  |  |  |  |

## Annex 2 - Tailoring Matrix Guidelines

< OPTIONAL >

< HIGHLY RECCOMENDED for project-related processes.

If no tailoring matrix is required, state “All actions are mandatory” and delete the content below. >

The table below describes the minimum level of compliance to this procedure unless additional requests are made by interested parties such as – for example – Corporate Company and Customers.

O = optional action, R = recommended action, M = mandatory action (i.e. cannot be skipped).

Regardless of the minimum level of compliance (O, M, R), tailoring details at action level can be found in Annex 4.

< Customise column titles as per relevant criteria.

As an example, for execution processes, {Criteria} could be “Project Type” and column names could include R&D Projects (CapEx/Spent), Customer Projects… >

| {Criteria} Action | {Criteria #1} | {Criteria #1} |  |  | … | … | … | … | … | … | … | {Criteria #N} |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| {Action Name} ({Action ID}) | {M, R, O} | {M, R, O} | {M, R, O} | {M, R, O} | {M, R, O} | {M, R, O} | {M, R, O} | {M, R, O} | {M, R, O} | {M, R, O} | {M, R, O} | {M, R, O} |
| {Action Name} ({Action ID}) |  |  |  |  |  |  |  |  |  |  |  |  |
| … |  |  |  |  |  |  |  |  |  |  |  |  |

Table 1 Tailoring Matrix Reference Table

The list of selected actions shall be captured in a tailoring matrix (or equivalent deliverable) describing the customised procedure, the rationale for tailoring and relevant approval scheme.

< Add additional details on the tailoring matrix in terms of deliverable and approval flow.

As an example, and with reference to requirements and interface management, this could be articulated as follows:

Each project or product development initiative is required to complete an Interface Management Plan (IMP) which is to be updated as necessary throughout the lifecycle of the project. Specific tailoring guidelines to be implemented for the project, as related to the implementation of Interface Management, shall be defined within the IMP, which shall be reviewed and approved in accordance with the Requirements & Interface Management Process. >

## Annex 3 – PRM context diagram

RAMS and IVAL WPM/WPLs

RAMS and IVAL WPM/WPLs

## Annex 4 – Project Execution - RAMS 2nd level Organizational chart

From technical point of view, the hierarchical structure depicted here below is aligned to typical hierarchy of the project RAM Analyses and Safety Cases.

- For Signalling projects, the Signalling System Safety and IVAL WPM/WPL shall report technical issues directly to the PRM;

- RAM activities are under the responsibility of the RAM and IVAL WPM/WPL, who directly reports for all issues to the PRM;

- System and Subsystems Safety and IVAL WPM/WPLs are accountable for all activities related to Generic Application (GA) and Specific Application (SA), where applicable, affecting the WP under their own responsibility. At the same time, they exercise a proper governance on the V&V activities, related to their WP, as described further in the document;

- For each signalling technology of a given project, depending on project complexity, one or more GP Safety and IVAL WPM/WPL accountable for all activities related to a specific GP belonging to such signalling technology shall be appointed. The GP Safety and IVAL WPM/WPLs exercises the Independent Validation activities similarly to the Subsystems Safety and IVAL WPM/WPLs;

- For technical issues, each GP Safety and IVAL WPM/WPL interacts directly with the Safety and IVAL WPM/WPL accountable for the related Application.

Within the overall Project Team, the Safety and IVAL WPM/WPLs interact directly with the respective WPLs SIG. In addition, the PRM with the support of Safety and IVAL WPM/WPLs shall check if the V&V Referents/System Validator have been appointed by the relative organizational unit’s FMs, for each signalling technology of competence and for the signalling/turnkey system.

WPM

System Validation

WPM

System Validation

WPX Safety&IVAL

Subsystem #n

WPX Safety&IVAL

Subsystem #n

WPX Safety&IVAL

Subsystem #1

WPX Safety&IVAL

Subsystem #1

WPM Safety&IVAL

System &

Signalling

WPM Safety&IVAL

System &

Signalling

SubSystem #1 V&V Referent

SubSystem #1 V&V Referent

SubSystem #n V&V Referent

SubSystem #n V&V Referent

WPM RAM&IVAL

WPM RAM&IVAL

For Budget and workload management issues, all the WPM/WPLs directly report to the PRM (see Annex 3 – PRM context diagram).