## Review register
# | Para | Severity | Category | Finding | Quoted from the document | Quotation checked | Proposed | Applied as | Reason
1 | 2526 | High | Availability / change management | The requirement promises uninterrupted railway operation and zero operational downtime, but the proposed solution/comment allows controlled shutdowns and maintenance windows for some software or hardware changes. This is a material qualification, not evidence of compliance. Please identify which change classes can be executed without loss of service and obtain explicit AG agreement for any exceptions, including the permitted service impact and acceptance criteria. | Der Bahnbetrieb muss weiterhin unterbrechungsfrei gewährleistet sein und es dürfen keine betrieblichen Ausfallzeiten entstehen. | verified against the cited paragraph |  | Comment | judgement required -- raised as a comment
2 | 2304 | High | FRACAS / deliverable scope | The requirement calls for a FRACAS system to be made available to the AG, while the proposed response offers a process and reports and expressly excludes access to internal IT tools or databases. Clarify whether AG access to a working FRACAS tool is required; otherwise obtain agreement to the narrower process/reporting deliverable and define the data/interface and reporting arrangements. | Der AN muss ein FRACAS-System gemäß CENELEC-Norm EN50126-1 dem AG für alle zu liefernden Systeme und Subsysteme zur Verfügung stellen. | verified against the cited paragraph |  | Comment | judgement required -- raised as a comment
3 | 2325 | High | Availability / system boundary | The five-year FRACAS demonstration explicitly covers the data centre, VSTW, FES and OC, but the response limits the proof to systems/components in Hitachi Rail scope and makes AG-provided data a precondition. Reconcile the boundary before commitment: state who supplies validated data and who demonstrates each listed system, how AG-provided/data-centre performance is included, and what happens if data or population are insufficient. | Der AN muss mittels FRACAS die Einhaltung der geforderten Verfügbarkeitswerte (Rechenzentrum, VSTW, FES, OC) innerhalb von 5 Jahren nach IBN des ersten VSTW nachweisen. | verified against the cited paragraph |  | Comment | judgement required -- raised as a comment
4 | 1431 | Medium | Availability / maintainability metric | This defines MRT as active technical repair time and excludes travel, access, spares, approvals and waiting. The supplied DIL/VIL RAM plan defines MTTR to restart operation and assumes 0.5 h MRT for manual recovery. Align the meanings and boundary: distinguish active repair MRT from elapsed restoration/operational downtime, and state which is used in each availability target and empirical FRACAS calculation. | Die MRT umfasst ausschließlich die aktive technische Instandsetzungszeit unter definierten Voraussetzungen. Anfahrt, Logistik, Ersatzteilbeschaffung, betriebliche Freigaben, Zugang zur Anlage und Wartezeiten aufgrund von AG-Prozessen sind nicht Bestandteil der produktbezogenen MRT, sofern nicht ausdrücklich anders vereinbart. | verified against the cited paragraph |  | Comment | judgement required -- raised as a comment
5 | 837 | Medium | Maintainability / architecture consistency | This solution describes PULSE as part of ADM, whereas the solution for MDSTW-21821 states that PULSE is not integrated into ADM and has a separate interface. Reconcile the Phase 1 architecture and responsibility boundary so the diagnostic and maintenance solution, interfaces and availability scope are unambiguous. | PULSE ist nicht in ADM integriert und verfügt in Stufe 1 über eine eigene Benutzeroberfläche mit abweichendem Bedien- und Erscheinungsbild. | verified against the cited paragraph |  | Comment | judgement required -- raised as a comment
6 | 2346 | Medium | FRACAS / verification method | The source requirement can be read as requiring monitoring and proof for every individual DSTW component, while the response interprets it as a statistical product-population result rather than an individual-device proof. Please obtain AG confirmation of this interpretation and define the population grouping, minimum data/sample criteria, and how each system/component availability target is reported. | Mittels dem FRACAS-System muss die Verfügbarkeit jeder einzelnen DSTW-Komponenten (VSTW, Feldelementstation, OC) überwacht und die Einhaltung der Verfügbarkeitsanforderungen nachgewiesen werden. | verified against the cited paragraph |  | Comment | judgement required -- raised as a comment
7 | 1599 | Medium | Availability / calculation basis | The formula uses MTTF, but its meaning for a repairable system and the included downtime boundary are not stated here. The supplied DIL/VIL RAM plan describes restoration as failure-to-restart and assumes a manual recovery MRT of 0.5 h. Define the up-time term and whether MTTR/MRT includes only repair or all time until service restoration; otherwise independent availability calculations and FRACAS results may not be comparable. | A = MTTF/(MTTF+MTTR) | verified against the cited paragraph |  | Comment | judgement required -- raised as a comment
8 | 2367 | Medium | FRACAS / reporting acceptance | “Regular” reporting is not objectively verifiable. The solution defers the interval and content to the RAM Plan/service concept, so ensure that document is contractually controlled and specifies frequency, cut-off date, required metrics/failure coding, format, recipients and escalation thresholds before this commitment is baselined. | Das FRACAS-System muss dem AG regelmäßige Reports bereitstellen. | verified against the cited paragraph |  | Comment | judgement required -- raised as a comment

## Summary
Document | EL4_PH_PleaseReview_Clean.docx
Findings | 8
Comment | 8
Note | A finding becomes a tracked change only when the correction is mechanical and its target is unambiguous. Everything else is a comment, and every refusal is listed above with its reason.