System Engineering Management Plan

ZIVD IL Solution

ZIVD ETCS Solution

| APPROVAL |  |  |
| --- | --- | --- |
|  | Name and Role/Job Title | Esignature |
| Written by | R. Szalay / SEM |  |
| Verified by | D. Daylan / QAM |  |
| Approved by | M. GOLLINGER / HoD. |  |

| LOG OF CHANGES |  |  |  |
| --- | --- | --- | --- |
| Revision | Date | Author | Change Description |
| 01 PD 01 | 2026-10-02 | Hitachi Austria GmbH / OEDERS SEM Robert Szalay | First Draft for ZIVD |

Contents

1	SCOPE	10

1.1	Identification	10

1.2	Project objective	11

1.3	Main systems affected	11

1.4	Deliverables Overview	11

1.5	Main modifications	12

1.6	Reused systems and assets	12

1.7	Key exclusions	13

2	Target System Definition:	14

2.1	Interlocking	14

2.2	ETCS	14

2.3	Level Crossing Modifications	15

2.4	Other Modifications	16

3	Topological Overview	17

4	High Level System Overview – Target State	18

5	High Level System Architecture, Target State	19

6	Management System Milestone Overview	20

6.1	Interlocking Solution Milestones	21

6.2	ETCS L2 Solution Milestones	23

7	Target Product Baseline	25

7.1	INTERLOCKING Solution	25

7.2	ETCS Solution	26

8	Deliverables	28

8.1	Interlocking Solution Deliverables	28

8.2	ETCS Solution Deliverables	29

9	Relation with other Plans	31

10	Configuration Management	32

10.1	General rules	32

10.2	Interlocking solution labels	32

10.3	ETCS solution labels	33

11	Change History	34

11.1	Edition 01	34

12	References and Terms	35

12.1	Referenced Documents	35

12.2	Standards and Procedures	36

12.3	Terms, Abbreviations and Acronyms	37

12.3.1	Role Abbreviations	37

12.3.2	Terms, Abbreviations and Acronyms	38

12.3.3	Abbreviations used in the project	40

13	Solution Engineering and Development Process	42

13.1	Organization of Solution Development and Engineering	42

13.1.1	Solution Core Team ETCS.	42

13.1.2	Solution Team	43

13.1.3	External Project Roles	44

13.1.4	Configuration Control Board	46

13.2	System Engineering Supplies	47

13.3	Input Data	47

13.4	Preconditions	48

13.5	Related Solutions / Projects	50

13.6	Technical Objectives	50

13.7	WBS/OBS and Engineering Work Packages	50

13.8	Training of System Engineering Team	50

13.9	Constraints	50

13.10	Work Contained	50

13.11	Work not contained	50

13.12	Responsibility Assignment Matrix	50

13.12.1	Involvements	51

13.13	Development Approach	53

13.14	Tools and Facilities	53

13.14.1	Project Management	54

13.14.2	Task Management	54

13.14.3	Requirements Management	54

13.14.4	Management Traceability	54

13.14.5	Configuration Management	55

13.14.6	Change Management	55

13.14.7	Documentation Management	55

13.14.8	Documentation Generation	56

13.14.9	Model Driven Engineering	56

13.14.10	Code Building	56

13.14.11	Hardware Engineering Environment	58

13.14.12	IVV Management	58

14	Process Control	60

14.1	Control of Solution Development	60

14.1.1	Deviation	60

14.1.2	Metrics	60

14.2	Monitoring and Control of System Engineering Activities	61

14.2.1	Periodic Internal Reviews and Meetings	61

14.2.2	Milestone Reviews and Audits	62

14.2.3	Reporting	63

14.3	Critical Technologies	63

14.4	Risk and Opportunities Control	63

14.5	Corrective Action Process	63

14.6	Independent Evaluation and Verification	64

14.7	Estimate/Re-Estimate	64

14.8	Planning	64

14.9	Value Analysis and Design to Cost	64

14.10	Peer Reviews	64

15	Development Scenario / ZIVD TAILORED DDQS	65

15.1	ZIV Delta milestone list	66

15.2	Hungarian-specific extensions to the ZIVD Tailored Milestones	68

16	System Engineering Support	69

16.1	Data and Configuration Management	69

16.2	Confidentiality	69

16.3	Export Control	69

16.4	Capitalization	69

16.5	Measurements and Analysis	69

16.6	Technical and non Technical Requirements Management and Control	69

16.7	Validation of Requirements	69

16.8	Decision Analysis and Resolution	69

16.9	Subordinate Plans	69

16.10	Quality Assurance	69

	Approach and Criteria used for Tailoring of the System Engineering Process	70

	Certification Support Activity	71

	Open Items	72

Appendix A :	Criteria for the Selection of Techniques and Measures	73

END OF DOCUMENT	85

List of Tables

Table 1: Solution Identification	10

Table 2: Milestones ZIV Delta IL Solution	22

Table 3: Milestones ZIV Delta ETCS Solution	24

Table 4: INTERLOCKING Solution Baseline Definition	25

Table 5: ETCS Solution Baseline Definition	27

Table 6: Interlocking Solution Deliverables	28

Table 7: ETCS Solution Deliverables	30

Table 8: Subordinate Planning Documents	31

Table 9 : Referenced Documents	35

Table 10 : Standards and Procedures	37

Table 11 : Role Abbreviations	38

Table 12 : Terms, Abbreviation and Acronyms	40

Table 13 : Abbreviations used in the project	40

Table 14 : Station Abbreviations	41

Table 15: Core Team	42

Table 16: Solution Team	43

Table 17: External Project Roles	45

Table 18: CCB	46

Table 19: Suppliers Input Data	47

Table 20: Preconditions CSLK ETCS	49

Table 21: Related Solutions and Projects	50

Table 22: Involvements – design and laboratory readiness	51

Table 23: Involvements – field IVVQ, assessment and qualification	52

Table 24: Project Management	54

Table 25: Task Management	54

Table 26: Requirements Management	54

Table 27: Management Traceability	55

Table 28: Configuration Management	55

Table 29: Change Management	55

Table 30: Documentation Generation	56

Table 31: Documentation Generation	56

Table 32: ETCS Tools	57

Table 33: Internal Used Products	58

Table 34: IV Management	59

Table 35: Metrics	60

Table 36: Reviews and Meetings	61

Table 37: Milestone Reviews	63

List of Figures

Figure 1: Topological Overview, Target State	17

Figure 2: High Level System Overview, Target State	18

Figure 3: High Level System Architecture, Target State	19

# SCOPE

The System Engineering Management Plan (SEMP) describes the Solution Work Plan and Engineering Process as it is to be applied to the engineering elements of the “ZIVD IL Solution” and “ZIVD ETCS Solution” for the customer project “Zalaszentiván Delta Track”.

## Identification

| Project: | Zalaszentiváni deltavágány építése Zalaszentivan Delta Track (abbr. ZIVD) |
| --- | --- |
| Solution: | ZIVD IL ZIVD ETCS |
| Identification: | ATRELOA42 |
| Contract: | Zalaszentiváni deltavágány építése |
| Customer: | V-Híd Network Kft. |
| End User: | GYSEV |
| SIL Level | SIL4 |

Table 1: Solution Identification

## Project objective

The project objective is to deliver the signalling and ETCS L2 trackside changes required for the new Zalaszentiván delta track, creating a direct connection between railway lines 17 and 25. The Hitachi solution includes replacement of the existing ELEKTRA 1 station interlocking by ELEKTRA 2, modification of ETCS L2, extension of AKF remote control, integration of new trackside objects, testing, validation, commissioning, documentation, training, tools and spares.

## Main systems affected

Station interlocking and associated ELEKTRA interfaces.

ETCS L2 trackside subsystem, including RBC, DAKO, balises and operator/diagnostic functions.

AKF and Super AKF remote-control presentation and data.

Signals, point machines, axle counters and block interfaces.

Station and line level crossings.

Interlocking power supply and signalling equipment room.

Railway telecommunications required for signalling and ETCS connectivity.

Security equipment associated with the new signalling room.

Testing, safety, RAM, cybersecurity, approval and commissioning processes.

## Deliverables Overview

ELEKTRA 2 station interlocking solution with project-specific data.

ETCS L2 delta-track integration and RBC data/interface changes.
•  AzLM solution with project-specific data

AKF, Super AKF and relevant KÖFI changes.

New or modified signals, points, axle-counter sections and level-crossing interfaces.

New balises, modified balise telegrams and RBC linking.

Interlocking and ETCS design, manufacturing, installation and as-built documentation.

Verification, validation, laboratory and field-test evidence.

Safety cases, ISA support and certification evidence.

Operation and maintenance documentation, training, tools and spares.

## Main modifications

Migration from ELEKTRA 1 to the proposed ELEKTRA 2 solution.

Extension of the station control area onto the delta track.

Relocation of entry signals C and D and construction of new station signals.

Reduction of the line 17 block arrangement from three block sections to two.

Integration of AS1438, AS486 and AS495 as station level crossings.

Construction of new SR5.

Renaming of the former SR1 as SR9.

ETCS boundary, balise, telegram and RBC-interface changes.

Modification of AKF screen data and GYSEV KÖFI functions.

## Reused systems and assets

Existing RBC, DAKO, HIS/operator and diagnostic structure is modified rather than identified as fully replaced.

Existing AKF monitor arrangement is retained, with its Zalaszentiván image supplemented.

Existing Super AKF structure is retained.

The existing AS502A switched balise is retained and supplemented by AS502A2.

Existing positioning balise groups near the 1–3 point connection remain, with renamed identifiers and modified telegram content.

SR9 retains the existing road signals, barrier arm and initiation system.

Selected level-crossing concrete houses are to be dismantled so they remain suitable for reuse and reinstallation.

## Key exclusions

Only explicit exclusions are recorded:

Hardware modernisation of AKF equipment on line 25 is not part of this project.

No additional AKF monitors or modification of the existing monitor arrangement are required.

Customer risk analysis under CSM is identified as customer scope in the DVA.

DeBo and NoBo assessment are identified as customer scope in the DVA, while the contractor/Hitachi scope includes assessment support and submission of evidence.

VEZIR interface implementation, associated HW upgrades and associated SW upgrades.

Full CRA external compliance certification activities.

Internal corporate cybersecurity remediation programs intended to upgrade legacy products to full SL-C2 compliance.

# Target System Definition:

## Interlocking

ELEKTRA 1 → ELEKTRA 2 migration

Replacement of ELEKTRA 1 by ELEKTRA 2, expected product version PV INT 2.9.1A with BL INT_22.07. This is a New Delivery / Modification / Database Update / Integration / Commissioning item.

New and modified equipment

New CC, Communication, AzLM and Interface cabinets.

New entry and exit signals.

Relocated C and D entry boundaries using new signals.

New or modified point interfaces and electrohydraulic point machines.

Intermediate end-position monitoring for points 101, 103 and 111.

New axle-counter sections and activation points.

Modified block and level-crossing interfaces.

Extended power-supply cabinets.

Modified operating display and data.

Reused elements

Existing compatible line equipment remains where explicitly stated.

Existing station and line arrangements are reused where unchanged.

Level-crossing houses may be dismantled and reinstalled.

Dismantled signals and other outdoor interlocking equipment are not reusable. 
•  Existing WEM cards from the ELEKTRA1 
• The existing data transmission system will be used between the stations

## ETCS

Modify ETCS L2 to represent the new station limits, track layout, signals, points and level crossings.

Move the ETCS boundary from the Egervár direction to the new C entry signal.

Integrate the delta track into the existing RBC area and operator interface.

Integrate AS486/AS495 as SR7/SR1 and newly include AS1438 as SR3.

Add AS502A2 as a switched balise. (LEU boards of dismantled line level crossings can be used for driving the new switched balise,)

Add fixed-fixed balise groups at new signals.

Rewrite balise telegram for BG:08428.

Add repositioning balises before points 101 and 111.

Survey installed balises and perform final RBC linking.

Apply LT supplementary-cable entry for the specified diagonal routes.

Retain the basic RBC/DAKO/HIS architecture, subject to project-specific data and software changes.

## Level Crossing Modifications

AS495 line crossing → SR1 station crossing

  - Position of road signals unchanged

  - Classification: Modification / Integration

Existing SR1 → Renamed to SR9

  - Road signals unchanged

  - Barrier arm unchanged

  - Initiation arrangement unchanged

  - Classification: Reused / Renamed

AS1438 line crossing → SR3 station crossing

  - Road signals remain in position

  - Barrier arms remain in position

  - Classification: Modification / Integration

None → New SR5 on delta track

  - Train-controlled

  - Signal-supervised

  - Classification: New Delivery

AS486 line crossing → SR7 station double-track crossing

  - Signal "a" relocated

  - Signal "b" remains unchanged

  - Classification: Modification

SR2

  - Protection mode unchanged

  - Activation points/distances modified

  - Classification: Modification

SR4

  - Protection mode unchanged

  - Activation points/distances modified

  - Classification: Modification

AS512

  - Transfer of the approach warning transmission connection from AS486.

  - Classification: Open Item

## Other Modifications

AKF: Data and station screen modification; no additional monitors.

Super AKF: Retained with modified connected AKF data.

GYSEV KÖFI: Modification is explicitly required.

Power supply: Extension for interlocking and associated equipment.

Telecom: Relocation/protection of affected line and optical cables, new connectivity and interference measurements.

Security: Extension of the existing intrusion-detection system into the new signalling room.

Equipment rooms: New signalling room in the former traffic control room; associated adaptation and climate/power provisions.

Migration: Final software update after final track and object installation; phased software updates are not required by the customer requirement.

ELEKTRA 1 removal: Removal, disposal of not used legacy components

# Topological Overview

Current State

Zalaszentiván is a junction station connecting Railway Line 17 (Szombathely – Zalaszentiván – Nagykanizsa) and Railway Line 25 (Boba – Zalaegerszeg – Őriszentpéter). Train movements between the two corridors currently require movement through the station and, for certain relations, operational constraints caused by the existing topology.

Target State

The project extends the Zalaszentiván station area by constructing a new Delta Track directly linking Lines 17 and 25. The station topology will be expanded westwards and operated by a new ELEKTRA 2 interlocking with integrated ETCS Level 2 functionality. The modified layout introduces new signals, points, axle-counter sections, ETCS balises and level-crossing interfaces, while extending the ETCS supervised area and AKF/KÖFI control functions to the new route. The result is a direct operational connection between both railway corridors without changing the surrounding line architectures.

Figure 1: Topological Overview, Target State

# High Level System Overview – Target State

As illustrated in the architecture overview, the ZIV Delta project extends the existing Zalaszentiván (ZIV) installation by upgrading the station interlocking from ELEKTRA 1.x to ELEKTRA 2.x (PV 2.9.1.A / INT_22.07) while maintaining integration with the existing railway network and ETCS infrastructure. The new Delta Track topology is integrated into the station without changing the neighboring interlocking systems at Andráshida (AHI), Zalaegerszeg-Ola (OLE) and Pókaszepetk (POK).

The solution reuses the existing RBC HW Release 3.1, RBC HU 1.2.1.A, DAKO, AKF, and Super AKF infrastructure while extending the station with additional field elements, including 8 new main signals, 5 new shunting signals, 6 new points, 36 axle-counter sections and 1 new level crossing interface required for the Delta Track operation.

ETCS Level 2 functionality remains based on the existing BOBA ETCS architecture, with updates limited to application data, balise configuration, DAKO configuration, HIS software, and RBC interfaces necessary to support the new topology. No RBC hardware upgrade is planned.

Overall, the target architecture delivers a new ELEKTRA 2 + AzLM + AKF + ETCS L2 station configuration under the solution baseline ZIVD_MAV_ZIV_13.00, while maximizing reuse of the existing ETCS, AKF, Super AKF, RBC, and neighboring system infrastructure.

Figure 2: High Level System Overview, Target State

# High Level System Architecture, Target State

The architecture shows how the upgraded Zalaszentiván (ZIV) station becomes the central integration point between the neighboring stations, ETCS Level 2 infrastructure, and remote-control systems. The existing railway interfaces towards Andráshida, Zalaegerszeg-Ola, Pókaszepetk, Egervár–Vasboldogasszony, and Nagykapornak are preserved while the new Delta Track topology is integrated into the station.

The main system change is the replacement of ELEKTRA 1 with ELEKTRA 2, supported by new AzLM axle counters, updated AKF data, ETCS L2 application updates, and additional field equipment. The ETCS architecture reuses the existing RBC HW 3.1, RBC HU 1.2.1.A, DAKO, HIS, and Siemens balise platform while extending the supervised area to the Delta Track.

Figure 3: High Level System Architecture, Target State

# Management System Milestone Overview

For the Zalaszentiván Delta Track Project (ZIVD), the Management System milestone chain is tailored to the delivery and approval strategy of the Interlocking (IXL) and ETCS L2 solutions. The standard milestone names and governance principles are retained, while the milestone application is extended by project-specific Hungarian design approval, Operator submission and approval, construction readiness, laboratory and field testing, DeBo assessment, Dark Operation, Putting into Operation (PIO), standby-period closure, authority certification and customer-acceptance gates.

The same overall Management System milestone framework applies to both the IXL and ETCS solutions. The reviews may be planned and approved at different dates for each solution, according to their respective design, data-preparation, IVVQ, validation and approval maturity. The brief objectives below provide the governing milestone intent; the detailed entry criteria, outputs and Hungarian-specific extensions are defined in the respective milestone descriptions and review reports.

The following tables present the planned DDQS milestone sequence separately for the ZIV Delta Interlocking and ETCS L2 solutions. Each table identifies the milestone, the planned target date and the brief decision objective. The detailed entry criteria, outputs and Hungarian-specific extensions are controlled in the tailored milestone matrix and the applicable milestone review report.

## Interlocking Solution Milestones

| Milestone | Target Date A (Actual) / P (Planned) | Brief Objective |
| --- | --- | --- |
| Solution Orientation Review (SOR) | 10/2026 P | Approve the target architecture, development strategy and technical basis for solution design. |
| Solution Requirements Review (SRR), including Approval Plan Package | 11/2026 P | Approve the requirements baseline and Hungarian Approval Plan Package, including the required initial approval and assessment evidence. |
| Solution Functional Review (SFR), including Preliminary Design Package | 11/2026 P | Confirm design compliance and release the Preliminary Design Package for submission to the Operator. |
| Preliminary Design Review (PDR), including Operator Approval | 12/2026 P | Approve the preliminary design, obtain Operator approval and authorize application data preparation. |
| Critical Design Review (CDR), including Start of Installation | 01/2027 P | Approve the detailed design and construction plans, confirm site and material readiness, finalize data preparation and authorize installation and data-preparation verification. |
| TRR1-LAB, Start Laboratory IVVQ | 02/2027 P | Release the controlled LAB version for internal Hitachi Rail and customer laboratory testing. |
| TRR1-FIELD, Start Field IVVQ | 02/2027 P | Release the customer-approved LAB baseline for field testing and confirm verified field installation. |
| TQR1 / TRR2, Technical Qualification Review 1 and Test Readiness Review 2 | 06/2027 P | Close integration and verification and confirm that the verified solution is ready for validation in the operational environment. |
| TQR2-1, Initial Validation and Assessment Handover | 07/2027 P | Complete the first validation evidence set and hand it over to DeBo for authorization to proceed toward PIO. |
| FQR-1, Start Dark Operation and PIO | 08/2027 P | Confirm DeBo approval and all Hungarian operational prerequisites for Dark Operation and Putting into Operation. |
| TQR2-2, Finished PIO and Standby Period | 08/2027 P | Close PIO and the standby period and update the final validation, quality and safety evidence. |
| FQR-2, Final Qualification Review | 08/2027 P | Confirm completed validation and external assessment and declare readiness for customer acceptance and transition to support. |

Table 2: Milestones ZIV Delta IL Solution

## ETCS L2 Solution Milestones

| Milestone | Target Date A (Actual) / P (Planned) | Brief Objective |
| --- | --- | --- |
| Solution Orientation Review (SOR) | 11/2026 P | Approve the target architecture, development strategy and technical basis for solution design. |
| Solution Requirements Review (SRR), including Approval Plan Package | 12/2026 P | Approve the requirements baseline and Hungarian Approval Plan Package, including the required initial approval and assessment evidence. |
| Solution Functional Review (SFR), including Preliminary Design Package | 12/2026 P | Confirm design compliance and release the Preliminary Design Package for submission to the Operator. |
| Preliminary Design Review (PDR), including Operator Approval | 02/2027 P | Approve the preliminary design, obtain Operator approval and authorize application data preparation. |
| Critical Design Review (CDR), including Start of Installation | 02/2027 P | Approve the detailed design and construction plans, confirm site and material readiness, finalize data preparation and authorize installation and data-preparation verification. |
| TRR1-LAB, Start Laboratory IVVQ | 05/2027 P | Release the controlled LAB version for internal Hitachi Rail and customer laboratory testing. |
| TRR1-FIELD, Start Field IVVQ | 05/2027 P | Release the customer-approved LAB baseline for field testing and confirm verified field installation. |
| TQR1 / TRR2, Technical Qualification Review 1 and Test Readiness Review 2 | 09/2027 P | Close integration and verification and confirm that the verified solution is ready for validation in the operational environment. |
| TQR2-1, Initial Validation and Assessment Handover | 10/2027 P | Complete the first validation evidence set and hand it over to DeBo for authorization to proceed toward PIO. |
| FQR-1, Start Dark Operation and PIO | 12/2027 P | Confirm DeBo approval and all Hungarian operational prerequisites for Dark Operation and Putting into Operation. |
| TQR2-2, Finished PIO and Standby Period | 12/2027 P | Close PIO and the standby period and update the final validation, quality and safety evidence. |
| FQR-2, Final Qualification Review | 12/2027 P | Confirm completed validation and external assessment and declare readiness for customer acceptance and transition to support. |

Table 3: Milestones ZIV Delta ETCS Solution

# Target Product Baseline

## INTERLOCKING Solution

| System / Component | Current Baseline | Target Baseline |
| --- | --- | --- |
| Interlocking Solution | MAV_ZIV_12.00 (ELEKTRA 1 + AKF + A3 based operational baseline) | ZIVD_MAV_ZIV_13.00 (ELEKTRA 2 + AzLM + AKF solution baseline) |
| Interlocking Platform | ELEKTRA 1 | ELEKTRA 2 |
| Taget Interlocking Dataprep Label | MAV_ZIV_12.00 | MAV_ZIV_13.00 |
| ELEKTRA2 Lab | - | MAV_ZIV_13.00_01 / MAV_ZIV_13.00_02 |
| Axle Counter Technology | A3 Axle Counter | A3 + AzLM 7.6 Axle Counter |
| Target AzLM Label | - | MAV_ZIV_AX_01.00 |
| AzLM 7.6 Lab | - | MAV_ZIV_AX_01.00_01 |
| AKF PV | akf-1.7.0 | akf-1.7.0 ??? |
| AKF | akf-mav-hodos 1.4.1 | akf-mav-hodos 1.4.1 ??? |
| AKF DB | app-akf-mav-hodos 1.5.0 | app-akf-mav-hodos 1.5.0 (updated station data only) ??? |

Table 4: Interlocking Solution Baseline Definition

## ETCS Solution

| ETCS Solution Overall | etcs_boba_01.05 | etcs_boba_02.00 |
| --- | --- | --- |
| ETCS Solution Overall Lab |  | etcs_boba_02.00_01 |
| Target ETCS L2 Baseline | etcs_l2_boba_01.24 | etcs_l2_boba_02.00 |
| ETCS L2 Lab | etcs_l2_boba_01.24 | etcs_l2_boba_02.00_01 |
| Target TSR | boba_tsr_01.10 | boba_tsr_02.00 |
| TSR / Level Crossing Lab | boba_tsr_01.10 | boba_tsr_02.00_01 |
| ETCS L1 Fallback | zs-or_01.06 | zs-or_01.04 (planned unchanged according target-label definition) |
| UNISIG | SRS 2.3.0d | SRS 2.3.0d (unchanged) |
| RBC Generic Software | RBC HU 1.2.1.A | RBC HU 1.2.1.A (unchanged) |
| RBC | RBC_HU.1.2.1.0_b01 | RBC_HU.1.2.1.0_b01 (unchanged) |
| RBC HW | HW Release 3.1 | HW Release 3.1 (no HW upgrade) |
| RCS | RCS_8.0.1.2 | RCS_8.0.1.2 (unchanged) |
| DAKO Application | DAKO_PV_01.02.02 / DAKO_SW_01.02.06 | DAKO_PV_01.02.02 / DAKO_SW_01.02.06 with updated Specific Application only |
| DAKO Definition | DAKO_DEF-HU_1.0 | DAKO_DEF-HU_1.0 (unchanged) |
| HIS Generic | HIS_RBC_MAV_2.4.0.10 client baseline identified in operational system | BL HIS_RBC_GSV_2.15.0.11 ???? |
| HIS | BUILD_HIS_RBC_1.12 | BUILD_HIS_RBC_1.12 (not identified as changing) |
| MCE | MCEProjectCD2.3.1 | MCEProjectCD2.3.1 (not identified as changing) |
| Balises | Siemens S21 ERL6 Eurobalises | Siemens S21 ERL6 Eurobalises with updated topology and telegrams |
| VEZIR Interface | Not implemented in baseline solution | Excluded from project scope |

Table 5: ETCS Solution Baseline Definition

# Deliverables

## Interlocking Solution Deliverables

The following table identifies the principal Interlocking solution deliverables for the ZIV Delta project. In addition to the ELEKTRA 2, AzLM and AKF configuration items, the deliverables include the associated design, verification, validation, safety, approval, testing, commissioning and documentation outputs required to achieve solution acceptance and operational release.

| INTERLOCKING Deliverable | A (Actual) / P (Planned) | Customer / End User |
| --- | --- | --- |
| Accepted generic ELEKTRA 2 product baseline evidence: PV INT 2.9.1A / BL INT_22.07, including applicable generic safety, assessment and user documentation | 08/2026 A | V-Híd Network Kft. / GYSEV |
| ZIVD Interlocking preliminary design package, including target architecture, interfaces, Mengengerüst 1.0 and operator-submission documentation | 11/2026 P | V-Híd Network Kft. / GYSEV |
| ZIVD Interlocking detailed design and construction package, installation documentation and initial Product Baseline definition | 12/2026 P | V-Híd Network Kft. / GYSEV |
| ELEKTRA 2 station interlocking hardware and project-specific application data, target label MAV_ZIV_13.00_X | 01/2027 P | V-Híd Network Kft. / GYSEV |
| AzLM 7.6 axle-counter hardware and project-specific application data, target label MAV_ZIV_AX_01.00_X | 01/2027 P | V-Híd Network Kft. / GYSEV |
| AKF / ProLAN station-display and database update, including Super AKF and applicable GYSEV KÖFI integration changes | 01/2027 P | V-Híd Network Kft. / GYSEV |
| Interlocking field baseline, installation-verification evidence, field-test reports and verified solution evidence | 06/2027 P | V-Híd Network Kft. / GYSEV |

Table 6: Interlocking Solution Deliverables

## ETCS Solution Deliverables

The following table identifies the principal ETCS solution deliverables for the ZIV Delta project. The deliverables cover the ETCS L2, TSR and supporting application-data baselines together with all related engineering documentation, verification and validation evidence, safety and assessment deliverables, commissioning activities and customer handover documentation required for Putting Into Operation.

| ETCS Deliverable | A (Actual) / P (Planned) | Customer / End User |
| --- | --- | --- |
| ETCS L2 preliminary design package for delta-track integration, RBC area/interface changes, DAKO/HIS changes, balise topology and level-crossing integration | 12/2026 P | V-Híd Network Kft. / GYSEV |
| ETCS L2 detailed design, specific-application data and controlled configuration set: etcs_l2_boba_02.00, boba_tsr_02.00 and overall etcs_boba_02.00 | 02/2027 P | V-Híd Network Kft. / GYSEV |
| DAKO specific-application update and HIS configuration/software update required for the ZIVD topology; existing RBC HU 1.2.1.A and RBC HW Release 3.1 retained | 08/2027 P | V-Híd Network Kft. / GYSEV |
| Siemens S21 ERL6 Eurobalises, including new/modified balise groups, telegram data, survey records and final RBC linking | 05/2027 P | V-Híd Network Kft. / GYSEV |
| ETCS laboratory baseline and laboratory test evidence: etcs_boba_02.00_01, etcs_l2_boba_02.00_01 and boba_tsr_02.00_01 | 05/2027 P | V-Híd Network Kft. / GYSEV |
| ETCS field baseline, installation-verification evidence, field-test reports and verified solution evidence | 09/2027 P | V-Híd Network Kft. / GYSEV |
| Qualified ZIVD ETCS solution, including validation, quality, safety, DeBo/assessment evidence and readiness for customer acceptance | 12/2027 P | V-Híd Network Kft. / GYSEV |
| Customer documentation package: as-built design, operation and maintenance documentation, operator handbook, release/configuration records and station documentation | 12/2027 P | V-Híd Network Kft. / GYSEV |
| Customer training for Interlocking and ETCS operation/maintenance, including applicable training material and completion records | 12/2027 P | V-Híd Network Kft. / GYSEV |
| Project-specific tools, instruments and spare parts for the delivered Interlocking and ETCS scope, including handover records | 12/2027 P | V-Híd Network Kft. / GYSEV |
| Putting-into-operation, standby-period and final handover evidence for the Interlocking and ETCS solutions | 12/2027 P | V-Híd Network Kft. / GYSEV |

Table 7: ETCS Solution Deliverables

# Relation with other Plans

The SEMP describes the application of the Management System Solutions Engineering Processes (DDQS) to the design, development and deployment.

| Title | Description | Ref. |
| --- | --- | --- |
| Project Management Plan | Focuses on Management System including organization, policies and plans that are carried out by Hitachi Rail in relation to the Project. | [1] |
| Configuration Management Plan | Provides details of the formal Configuration Management process. | [11] |
| Quality Management Plan | Describes requirements for all quality assurance measures and quality assurance activities to be carried out in the solution as contribution to the fulfilment of the project goals. | [12] |
| RAM Plan | Provides details of the tasks and activities about Reliability, Availability and Maintainability of the Solution. | [4] |
| Safety Plan | Provides details of the tasks and activities of Solution safety management and Solution safety engineering required to identify, evaluate and eliminate or control hazards throughout the life cycle. | [5] |
| IV Plan | Is the general overview how is it planned and manage to test the solution. | [7] |
| VQ Plan | Is the general overview how is it planned and manage to validate the solution. | [7] |
| Documentation Plan | Provides overview about document planning and status. | [8] |
| Solution Milestone Reports | Is providing planning and status report of the milestones with input and output criteria. | [7] |

Table 8: Subordinate Planning Documents

# Configuration Management

This chapter defines the project-specific configuration identification and labelling rules for the ZIV Delta Interlocking and ETCS solutions. Detailed configuration-management activities, responsibilities, change control, status accounting and audits remain governed by the applicable Configuration Management Plans and Management System processes.

## General rules

Each released solution state shall be uniquely identified by a controlled baseline label. The baseline links the applicable application data, product versions, supporting evidence and documentation required to reproduce or assess that solution state.

The Product Baseline tables in the SEMP define the current and target field baselines. Laboratory increments use the additional numeric suffix shown below. A label without the laboratory suffix identifies the field or released target baseline.

Only approved configuration items shall be included in a released baseline. Changes after baseline establishment shall be processed through the applicable defect and change-management process and shall result in an updated controlled baseline where required.

## Interlocking solution labels

The Interlocking solution is controlled at solution level and at product/application-data level as follows:

| Configuration level | Target field label | Laboratory label | Application |
| --- | --- | --- | --- |
| Overall Interlocking solution | ZIVD_MAV_ZIV_13.00 | ZIVD_MAV_ZIV_13.00_01, _02, … | Solution-level configuration and documentation set |
| ELEKTRA 2 data preparation | MAV_ZIV_13.00 | MAV_ZIV_13.00_01, _02, … | ELEKTRA application data and product-related artifacts |
| AzLM data preparation | MAV_ZIV_AX_01.00 | MAV_ZIV_AX_01.00_01, _02, … | AzLM application data and product-related artifacts |
| AKF / ProLAN configuration | Controlled product and database versions | As identified in the applicable release record | AKF product, application database and related ProLAN artifacts |

DWF labelling rule. The ELEKTRA product label MAV_ZIV_13.00[_nn] is applied only to ELEKTRA product-related artifacts, such as Funkbed, Logbuch, RLP, ProdVerz and the application database. The overall label ZIVD_MAV_ZIV_13.00[_nn] identifies the complete Interlocking solution baseline.

Documentation rule. Interlocking documents required to define, reproduce, verify, validate, approve or maintain the station solution shall carry the overall solution baseline label. This includes design and data-preparation documentation, SSDD and architecture documents, test documentation, management plans, protocols, assessment reports, certificates, approvals, third-party evidence, and solution-related ELEKTRA 2, AzLM and AKF artifacts.

## ETCS solution labels

The ETCS solution baseline is composed of the overall solution label and its controlled subsystem labels:

| Configuration item | Target field label | Laboratory label |
| --- | --- | --- |
| ETCS overall solution | etcs_boba_02.00 | etcs_boba_02.00_01 |
| ETCS L2 specific application | etcs_l2_boba_02.00 | etcs_l2_boba_02.00_01 |
| TSR / level-crossing application | boba_tsr_02.00 | boba_tsr_02.00_01 |
| ETCS L1 fallback | zs-or_01.04 | Unchanged; no new ZIVD laboratory increment defined |

The ETCS overall baseline record shall identify the corresponding L2, TSR/level-crossing and L1 fallback labels and the applicable generic product versions. ETCS documents and files shall use the label of the configuration item to which they belong. Solution-level documents covering the complete ETCS delivery shall use the overall ETCS solution label.

# Change History

## Edition 01

PROPOSAL 1

First Proposal for ZIVD

# References and Terms

## Referenced Documents

The latest relevant version of a document is referenced in the Documentation Plan.

| No | Nr./Title | Reference | Edition/Version |
| --- | --- | --- | --- |
| [1] | Project Management Plan | 3BU_61914_0001_DPAPQ | 01 |
| [2] | Design Validation Form (DVa) | 3BU_00603_0207_DEAPA | 01 |
| [3] | Contract Data Requirements List | NCEE project ZIV Delta - Sharepoint |  |
| [4] | Generic RAM Plan | 3BU_15000_1712_DUAPA | 07 |
| [5] | Generic Safety Plan | 3BU 61900 0060 DUAPA | 04 |
| [6] | Validation and Qualification Plan | 3BU 15000 6253 DUAPA | 08 |
| [7] | Solution IL Milestone Report | 3BU_61914_0011_BCAPA |  |
| [8] | Documentation Plan | 3BU_61914_0000_ADAPA | 01 |
| [11] | Generic Configuration Management Plan for International Customer Projects ETCS Track Side System | 3BU 61906 0008 QMAPA | 04 |
| [12] | Specific Quality Management Plan | 3BU_61914_0003_ADAPA | 01 |

Table 9 : Referenced Documents

## Standards and Procedures

You can find below the standards and processes followed in the IL and ETCS Solution.

| Nr./Title | Publishing Date/ Reference |
| --- | --- |
| ISO/TS 22163:2023 Railway applications — Quality management system – Business management system requirements for rail organizations: ISO 9001:2015 and particular requirements for application in the rail sector | 2015 |
| EN 50128:2011 + A1:2020 + A2:2020 Railway applications – Communication, signalling and processing systems – Software for Railway Control and Protection Systems | 2011 |
| EN 50129:2018 +AC:2019 – Railway applications – Communication, signalling and processing systems – Safety related electronic systems for signalling | 2018 |
| EN ISO 9001:2015 Quality management systems — Requirements | 2015 |
| EN 50121-4:2016 + A1:2019 Railway applications – Electromagnetic compatibility -Part 4: Emission and immunity of the signalling and telecommunications apparatus | 2016 |
| EN 50124-1:2017 Railway applications - Insulation coordination Part 1: Basic requirements - Clearances and creepage distances for all electrical | 2017 |
| EN 50126-1:2017 Railway Applications – The Specification and Demonstration of Reliability, Availability, Maintainability and Safety (RAMS) – Part 1: Generic RAMS Process | 2017 |
| EN 50126-2:2017 Railway Applications – The Specification and Demonstration of Reliability, Availability, Maintainability and Safety (RAMS) – Part 2: Systems Approach to Safety | 2017 |
| EN 50159:2010 +A1:2020 – Railway application – Communication, signaling and processing: Safety-related communication in transmission systems | 2010 |
| Compliance Assessment of the ERTMS/ETCS system according Article 6 of Directive (EU) 2016/797 | 2016 |
| Document Management Rules: 83530061-DOC-AUT-EN, Rev.014 | - |
| [Management System] | 2026-06 |

Table 10 : Standards and Procedures

## Terms, Abbreviations and Acronyms

### Role Abbreviations

| APM | Acquisition Project Manager |
| --- | --- |
| ARC | Architect |
| CM | Configuration Manager |
| DM | Document Manager |
| DPE | Data Preparation Engineer |
| IM | Industrial Manager |
| IVM | Integration, Verification Manager |
| LDM | Local Deployment Manager |
| PDA | Project Design Authority |
| PLM | Product Line Manager |
| PM | Project Manager |
| QAM | Quality Assurance Manager |
| RAM-AM | Reliability, Availability, Maintainability Assurance Manager |
| RM | Requirements Manager |
| SAM | Safety Assurance Manager |
| SEM | System Engineering Manager |
| SAM | Safety Assurance Manager |
| TM | Test Manager |
| TST | Tester |
| VAL | Validator |
| WPM | Work Package Manager |

Table 11 : Role Abbreviations

### Terms, Abbreviations and Acronyms

| APP | Application Preparation Plan |
| --- | --- |
| CCB | Configuration Control Board |
| CEC | Centralised ETCS Controller |
| CDR | Critical Design Review |
| CLC | Centralised LEU |
| CMP | Configuration Management Plan |
| CTC | Centralized Traffic Control |
| DDQS | Design, Develop and Qualify the Solution |
| DPP | Data Preparation Plan |
| DWF | Document Web Frontend |
| ECM | Enterprise Content Management |
| FCA | Functional Configuration Audit |
| FIS | Functional Interface Specification |
| FQR | Final Qualification Review |
| Hitachi -AT | Hitachi Rail Austria GmbH (Gesellschaft mit beschränkter Haftung) |
| Hitachi -HU | Hitachi Rail Hungary Kft. |
| ILS | Integrated Logistic Support |
| IVV | Integration, Verification and Validation |
| I&V | Integration and Verification |
| KOM | Kick-off Meeting |
| MP | Maintenance Plan |
| LUT | Label Unit Tracking |
| M | Mandatory |
| MR | Milestone Report |
| NA | Not applicable |
| O | Optional |
| PCA | Physical Configuration Audit |
| PCB | Printed Circuit Board |
| PCM | Primavera Core Model |
| PDR | Preliminary Design Review |
| PMP | Project Management Plan |
| QMP | Quality Management Plan |
| RAM | Reliability, Availability and Maintainability |
| SE | Solution Element |
| SEMP | System Engineering Management Plan |
| SFR | Solution Functional Review |
| SOR | Solution Orientation Review |
| SRR | Solution Requirement Review |
| SubIT | Subsystem Integration Test |
| SW | Software |
| TM | Test Manager |
| TQR | Technical Qualification Review |
| TRR | Test Readiness Review |
| VA | Validation |
| WBS | Work Breakdown Structure |
| WP | Work Package |
| WPM | Work Package Manager |

Table 12 : Terms, Abbreviation and Acronyms

### Abbreviations used in the project

| AsBo | Assessment Body |
| --- | --- |
| AzLM | Axle Counter („Achszähler Lorenz Mehrabschnitt“) |
| DeBo | Designated Body |
| HMI | Human Machine Interface |
| LCSI | Level Crossing Safety installation |
| GySEV | Győr-Sopron-Ebenfurti Vasút Zrt. (Raaberbahn) |
| NoBo | Notified Body |
| RBC | Radio Block Centre |
| RIC | Remote Interface Controller |
| FOR | Traffic Monitoring System |
| ZIVD | Zalaszentiván Delta Track Reconstruction Project |

Table 13 : Abbreviations used in the project

| Station-Term | Definition |
| --- | --- |
| ZIV | Zalaszentiván |

Table 14 : Station Abbreviations

# Solution Engineering and Development Process

The ZIVD solutions are developed in accordance with the applicable Hitachi Management System [Management System] and DDQS processes. Project-specific tailoring, including the adapted milestone sequence, decision gates and Hungarian approval and deployment requirements, is defined in Chapter 15.

## Organization of Solution Development and Engineering

The description of the roles mentioned below can be found on the Hitachi Management System Portal.

### Solution Core Team ETCS.

| Role | Resource |
| --- | --- |
| Project Manager (PM) | Gábor Papp |
| Project Engineer / System Engineering Manager (SEM) | Róbert Szalay |
| Project Design Authority (PDA) | Stefan Németh |
| System Architect (ARC) | József Jr. Bíró |
| Project Quality Manager / Quality Assurance Manager (QAM) | Derya Daylan |
| Project RAM Assurance Manager (RAM-AM) | Florian Moser |
| Safety Manager Interlocking | Gábor Pataki |
| Safety Manager ETCS | Monica Nanu |
| Integration and Verification Manager (IVM) | Bernhard Hofstetter |
| Validation and Qualification Manager (VQ Manager / VAL) | Manfred Gronau |
| Work Package Manager – Local Deployment (LDM) | Dávid Tóth |
| CAE Engineering / Data Preparation – Interlocking | Daniel Pick |
| CAE Engineering / Data Preparation – ETCS L2 | Georg Hammer |

Table 15: Core Team

### Solution Team

| Role | Resource |
| --- | --- |
| Project Controller | Werner Wimmer |
| Contract Manager | Róbert Hegedűs |
| HSE Referent | Lilla Pásztor |
| Supply Chain and Procurement Manager | Tamás Hitzinger |
| Project Planner | Gábor Papp |
| Requirements Manager (RM) | Samantha Chum |
| Security Manager | Peternel Sanja |
| Documentation Manager (DM) | János Ujhelyi |
| PMO | Mohamed Alarsan |
| PMO Support | Adrienn Bikszády |
| Configuration Manager (CM) | Róbert Szalay |
| ETCS Tester / Data Verification ETCS L2 | Levente Halász |
|  | Csaba Kotogány |
| Interlocking Tester | Balázs Máté; Csaba Kotogány |
| Data Verification Interlocking | Károly Szőnyi |
| Validation – Interlocking | Manfred Gronau |
| Validation – ETCS | Manfred Gronau |
| Installation / Site Manager – Interlocking and ETCS | Tamás Szendi |
| Customer Training – ETCS | Imre Török |
| Customer Training – Interlocking | László Kukk |

Table 16: Solution Team

### External Project Roles

| Role | Resource / Organisation | Project-specific comments |
| --- | --- | --- |
| Customer / Contracting Authority | GYSEV Zrt. | Project customer and contracting authority. |
| Infrastructure Manager / End User | GYSEV Zrt. | Operator/end user for the ZIV Delta project. MÁV Zrt. is also an affected infrastructure manager/end user on railway line No. 25 and for affected assets/interfaces. |
| Main Contractor | V-S Zala Consortium: Swietelsky Vasúttechnika Kft. (consortium leader) and V-Híd Network Kft. (consortium member) | Main contractor scope includes trackside, overhead contact line, civil works, utilities, cable ducting, interlocking, ETCS and telecommunications. |
| Independent Engineer | FŐBER Zrt. | Independent engineer / technical supervision organisation. |
| Level 1 Subcontractor to Main Contractor | Hitachi Rail Hungary Kft. | Contracted scope: interlocking, ETCS and telecommunications. |
| Level 2 Subcontractor / Technical Solution Partner | Hitachi Rail Austria | Scope: interlocking and ETCS. Current project stakeholder material states that the contract is under preparation. |
| External Designer – Signalling / Interlocking | BiLogik Kft. | Design of signalling plans and interlocking-related design deliverables. |
| Independent Safety Assessor – CENELEC (ISA) | ARSENAL RACE | Independent CENELEC assessment for the Hitachi interlocking and ETCS deliveries. |
| Notified Body (NoBo) | KÉMI / KTI |  |
| Designated Body (DeBo) | KÉMI / KTI | National-rule conformity assessment. Assessment and appointment are in the customer / contracting-authority certification scope; contractor provides full technical support. |
| Hungarian Railway Authority | Hungarian Transport Authority | Authority interface for permits, approval and commissioning. Exact competent authority and current organisational designation to be confirmed in the Approval Plan. |
| MÁV Interlocking Safety Organisation | MÁV Zrt. Interlocking System Safety Organisation | Performs safety-related examinations for new systems and structural elements affecting MÁV assets and requirements. |
| Operator / Asset Manager – affected line 25 scope | MÁV Zrt. | Affected infrastructure manager and operator for line No. 25 interfaces, work areas, approvals, supervision and ETCS integration. |
| Operator / Asset Manager – GYSEV scope | GYSEV Zrt. | Provides operator approvals, access, specialist supervision, operational coordination and acceptance for GYSEV-managed assets. |
| CTC / AKF and Super AKF Supplier | Prolan Zrt. | Provides/modifies AKF and Super AKF functions and databases required for the new delta topology. |
| Level-Crossing Interface Hardware Supplier | AXON 6M Kft. | Expected supplier for interface/adaptation hardware associated with station level-crossing interfaces. |
| Eurobalise Supplier | Siemens | Supplier of Siemens S21 ERL6 Eurobalises and associated holders used in the ETCS solution. |

Table 17: External Project Roles

### Configuration Control Board

| Role | Mandatory | Optional |
| --- | --- | --- |
| Project Manager (PLM) |  |  |
| Product Line Manager (PLM) |  |  |
| Project Design Authority (PDA) |  |  |
| System Engineering Manager (SEM) |  |  |
| Head of Department (HoD) | (budget, schedule, resources) |  |
| Safety Assurance Manager (SAM) | (requirements, scope) |  |
| Quality Assurance Manager (QAM) | (schedule, quality) |  |
| Test Manager (IVM) | (requirements, scope, quality) |  |
| Validator (VAL) | (requirements, scope, quality) |  |

Table 18: CCB

Other project team members are invited to the CCB if specifically needed.

## System Engineering Supplies

Any reuse of a finished or purchased product will be stated in the DVa [2]

## Input Data

| Input item | Version | Generic baseline / applicable configuration | Provider |
| --- | --- | --- | --- |
| ELEKTRA 2 generic Interlocking baseline | ELINT PV 2.9.1A | BL INT_22.07; MMI SW EBO2_INT_22.06; NIC HU 1.0.5; SEC INT 2.0.0 | Hitachi Rail Austria |
| ETCS L2 / RBC generic baseline | RBC HU 1.2.1.A | UNISIG SRS 2.3.0d; existing RBC HW Release 3.1 is retained | Hitachi Rail Germany |

Table 19: Suppliers Input Data

In case of any customer specific adaptions of generic deliveries a Change Management Process will be initiated by the SEM.

## Preconditions

| Solution | Precondition | Project-specific application | Status / required point |
| --- | --- | --- | --- |
| Interlocking | Generic baseline available and accepted | ELEKTRA 2 ELINT PV 2.9.1A, including BL INT_22.07, EBO2_INT_22.06, NIC HU 1.0.5 and SEC INT 2.0.0, shall remain released and applicable. The generic baseline has been presented to GYSEV and found technically acceptable for on-site deployment subject to its stated conditions. | Fulfilled / maintain under configuration control |
| Interlocking | Final infrastructure and field configuration available | The final station track layout and the new indoor/outdoor signalling objects, including signals, points, axle counters, level-crossing interfaces, power supply and equipment-room adaptations, shall be installed or represented by an approved test configuration. The tender clarification states that the software update is to be performed after the final track layout and all new external and internal objects are installed. | Required before final field configuration and commissioning tests |
| ETCS L2 | Existing ETCS L2 environment available | The existing Line 25 ETCS L2 TSS, RBC hardware Release 3.1, RBC HU 1.2.1.A generic baseline and the current RBC, DAKO, operator and diagnostic infrastructure shall remain available as the integration environment for the ZIV Delta extension. | Existing basis / maintain available |
| ETCS L2 | Interlocking functions available for ETCS testing | The ZIV Delta interlocking application and the safety-relevant indications/interfaces required by the RBC shall be operational and stable. Laboratory ETCS testing may use an approved representative interlocking/test configuration; dynamic field testing requires the commissioned or formally released-for-test interlocking configuration. | Key sequencing precondition for ETCS field testing |
| ETCS L2 | Trackside and telecommunications readiness | Balises and associated trackside elements shall be installed and verified, and the required communication links, site access, track possessions and test-train arrangements shall be available. | Required before dynamic field testing |
| ETCS L2 | Approval and operational readiness | ETCS verification and validation evidence, specific Safety Case, external-assessment/certification inputs, approved test specifications, operating documentation and customer/operator authorisation for testing shall be available. | Required before field testing and ETCS PIO |

Table 20: Preconditions CSLK ETCS

## Related Solutions / Projects

| Project / Solution | Solution | Responsibility |
| --- | --- | --- |
| None |  |  |

Table 21: Related Solutions and Projects

## Technical Objectives

For the project technical objectives see DVA [2].

## WBS/OBS and Engineering Work Packages

Engineering and customer specific work packages are available in in the PMP [1]

## Training of System Engineering Team

Training of the System Engineering Team on demand.

## Constraints

Constraints which are not already considered in the Risk Report are listed here.

None.

## Work Contained

- See chapter SCOPE.

## Work not contained

- See Chapter Key exclusions

## Responsibility Assignment Matrix

Types of Involvement

A	Approve

R	Responsible for organization (incl. contribution)

C	Contribute

AR	Attend on request

### Involvements

Design and preparation milestones

| Stakeholder | SOR | SRR | SFR | PDR | CDR | TRR1-LAB |
| --- | --- | --- | --- | --- | --- | --- |
| PM | C | C | C | C | C | C |
| PDA | A | A | A | A | A | A |
| ARC | C | C | C | C | C | C |
| SEM | R | R | R | R | R | C |
| RM | C | R | C | C | C | AR |
| VAL | C | C | C | C | C | C |
| IVM | C | C | C | C | C | R |
| CM | C | C | C | C | C | C |
| QAM | C | C | C | C | C | C |
| PLM | AR | AR | AR | AR | AR | AR |
| RAM-AM | C | C | C | AR | AR | AR |
| SAM | C | C | C | C | C | C |
| Security Manager | C | C | C | C | C | C |
| DM | C | C | C | C | C | C |
| LDM | AR | AR | AR | C | C | C |
| DeBo / ISA | AR | C | AR | AR | AR | AR |

Table 22: Involvements – design and laboratory readiness

Integration, validation and deployment milestones

| Stakeholder | TRR1-FIELD | TQR1 / TRR2 | TQR2-1 | FQR-1 | TQR2-2 | FQR-2 |
| --- | --- | --- | --- | --- | --- | --- |
| PM | C | C | C | C | C | C |
| PDA | A | A | A | A | A | A |
| ARC | C | C | AR | AR | AR | AR |
| SEM | C | C | R | R | R | R |
| RM | AR | C | C | C | C | C |
| VAL | C | C | C | C | C | C |
| IVM | R | R | C | C | C | C |
| CM | C | C | C | C | C | C |
| QAM | C | C | C | C | C | C |
| PLM | AR | AR | AR | AR | AR | AR |
| RAM-AM | AR | C | C | C | C | C |
| SAM | C | C | C | C | C | C |
| Security Manager | C | C | C | C | C | C |
| DM | C | C | C | C | C | C |
| LDM | R | C | C | R | R | C |
| DeBo / ISA | AR | AR | C | C | C | C |

Table 23: Involvements – field IVVQ, assessment and qualification

## Development Approach

Application data preparation for Interlocking and ETCS.

## Tools and Facilities

In this chapter the needed System Engineering tools will be identified.

The following chapters show the minimum version that should be applied. Actual versions might be higher during project life cycle.

### Project Management

| Name | Version |  | Rationale |
| --- | --- | --- | --- |
| PCM Project Planner | P6-PRO |  |  |
| Pertmaster Project Risk |  |  |  |
| Estimation Worksheet | 8 |  |  |
| OTL Timesheets | R12 |  |  |

Table 24: Project Management

### Task Management

| Name | Version |  | Rationale |
| --- | --- | --- | --- |
| Jira Confluence | 5.10.8 |  | Collaboration |
| Jira AT Task Management (TIPI) | v6.4.14 |  | Task management |

Table 25: Task Management

### Requirements Management

| Name | Version |  | Rationale |
| --- | --- | --- | --- |
| IBM Rational DOORS | 9.6 |  |  |
| RMF Add-On | 6.1.0.9 |  |  |
| Polarion |  |  |  |

Table 26: Requirements Management

### Management Traceability

| Name | Version |  | Rationale |
| --- | --- | --- | --- |
| Reqtify | 1.1.3 |  |  |
| DOORS | RMF 9.6 |  |  |
| Polarion |  |  |  |

Table 27: Management Traceability

### Configuration Management

| Name | Version |  | Rationale |
| --- | --- | --- | --- |
| ClearCase | 7.8 |  |  |
| ClearCase UCM |  |  | not used |
| CVS |  |  | Legacy |
| GIT |  |  | Client only |
| HG |  |  | Client only |
| Subversion |  |  | not used |
| Subversion UCM |  |  | not used |

Table 28: Configuration Management

### Change Management

| Name | Version |  | Rationale |
| --- | --- | --- | --- |
| ClearQuest |  |  | not used |
| ClearQuest CHARM |  |  | not used |
| Gnats |  |  | Legacy |
| Jira |  |  | not used |
| Jira CHARM | JIRA v7.6.12 |  | For defect tracking and change management |

Table 29: Change Management

### Documentation Management

| Name | Version |  | Rationale |
| --- | --- | --- | --- |
| CMCS | 3.8 |  | TDE documents |
| Clear Case, DWF | 1.7 |  | Hitachi AT+HU documents |
| SharePoint |  |  | Contract documents, dashboards, letters, etc. |
| PleaseReview | 7.6.0 |  | For review of documents |
| Modulo |  |  | not used |
| Subversion |  |  | not used |

Table 30: Documentation Generation

### Documentation Generation

| Name | Version |  | Rationale |
| --- | --- | --- | --- |
| Doxygen |  |  | not used |
| Java Doc |  |  | not used |
| Mozart |  |  | not used |
| Soda |  |  | not used |
| WEXP (Doors RMF) |  |  | Partly |
| Hitachi Rail AT Word Exporter |  |  | Partly |
| Polarion |  |  |  |

Table 31: Documentation Generation

### Model Driven Engineering

N.A.

### Code Building

N.A.

#### GTS Control - Continuous Build

N.A.

#### Hitachi AT Build

N.A.

#### Eclipse Development

N.A.

#### Programming Languages / Compiler

N.A.

#### Hitachi AT Elektra Tools

N.A.

#### Hitachi AT ETCS Tools

Note: The below versions are the minimum versions to be used. Higher versions might be used during integration.

| Name | Version | App | Rationale |
| --- | --- | --- | --- |
| Audit Tools |  |  | not used |
| Release Tools |  |  | not used |
| Generated Configure. Spec. |  |  |  |
| DMT | 16.25 |  |  |
| DPVT | 4.3.12.7-1 |  |  |
| TVS | TVS_PV_5.5.6 |  |  |

Table 32: ETCS Tools

#### Hitachi AT Legacy Tools

N.A.

#### Hitachi AT Internal Used Products

| Name | Version | App | Rationale |
| --- | --- | --- | --- |
| Data Prep. Tool AWS |  |  | not used |
| Data Prep. Verif. Tool AWS |  |  | not used |
| ELEPRO (Seibersdorf) |  |  | not used |
| Orest |  |  |  |
| TAS Platform | TAS_2.3.0.6_d6.10_c6.05 |  |  |

Table 33: Internal Used Products

#### Development Platform

N.A.

### Hardware Engineering Environment

N.A.

### IVV Management

| Name | Version | App | Rationale |
| --- | --- | --- | --- |
| DOORS |  |  |  |
| Coverity |  |  |  |
| Expect |  |  |  |
| GCOV |  |  |  |
| Mercury Win Runner |  |  |  |
| QF Test |  |  |  |
| Quick Test |  |  |  |
| Rational Test RT Mercury Loader |  |  |  |
| QAC |  |  |  |
| PurifyPlus |  |  |  |
| ICOV |  |  |  |
| EPS |  |  |  |
| SOS (SCWS outside Area Simulator) |  |  |  |
| TestRail |  |  |  |
| VIVALDI |  |  |  |
| Polarion |  |  | Testing Tool |

Table 34: IV Management

# Process Control

## Control of Solution Development

### Deviation

The development of a Solution has to be planned and executed according to the DDQS Process of Management System.

### Metrics

| ID | Name | App | Type |
| --- | --- | --- | --- |
| 1 | Schedule | M | Indicators |
| 1.1 | MTA | M | Metrics |
| 1.2 | Actual Milestones | O | Metrics |
| 2 | EAC vs CBB | M | Indicators |
| 2.1 | CBB-EAC Synthesis | O | Metrics |
| 2.2 | WP CBB-EAC | O | Metrics |
| 2.3 | Workload diagram | O | Metrics |
| 3 | Subcontractor | M | Indicators |
| 3.1 | Subcontractor Status | O | Info |

Table 35: Metrics

## Monitoring and Control of System Engineering Activities

### Periodic Internal Reviews and Meetings

| INTERNAL REVIEWS & MEETINGS |  |  |  |  |
| --- | --- | --- | --- | --- |
| Meeting | Responsible | Attendees | Frequency | Objectives |
| Project Reviews (PPPR) | PM | SEM, SeniorM, PLM, QAM, ContractM, PMO | Monthly | Project status, discussion about deviation from project plan and problems which cannot be solved inside the project team, decision finding |
| Technical Core Team Meeting | SEM | Technical Core Team | weekly | Solution Engineering progress, deviations and decision findings. |
| Project Core Meeting | PM | Project core team | weekly | Project status progress, decision finding, etc. |
| Configuration Control Board | SEM | See chapter 13.1 | On demand |  |
| Risk and opportunity review | PM | Project Risk Team (see PMP) | Quarterly | Review and Update of project risks and opportunities. |

Table 36: Reviews and Meetings

### Milestone Reviews and Audits

The following table consolidates the organization, principal attendees and decision objective for the tailored ZIVD DDQS milestone reviews. Detailed entry criteria, evidence, mandatory participation and approval records remain controlled in the applicable milestone template, review matrix and milestone report.

| Review | Responsible for organization | Principal attendees |
| --- | --- | --- |
| SOR | SEM | PDA; PM; ARC; RM; QAM; SAM; RAM-AM; Security Manager; DM; other contributors as required |
| SRR, including Approval Plan Package | SEM | PDA; PM; ARC; RM; QAM; SAM; RAM-AM; Security Manager; DM; other contributors as required |
| SFR, including Preliminary Design Package | SEM | PDA; PM; ARC; RM; QAM; SAM; Security Manager; DM; design and IVVQ contributors |
| PDR, including Operator Approval | SEM | PDA; PM; ARC; RM; QAM; SAM; CM; LDM; design, data-preparation and Operator representatives as required |
| CDR, including Start of Installation | SEM | PDA; PM; ARC; RM; QAM; SAM; CM; LDM; IVM; design, installation and supply contributors |
| TRR1-LAB, Start Laboratory IVVQ | IVM | PDA; SEM; PM; ARC; VAL; QAM; SAM; CM; DM; laboratory test and integration team |
| TRR1-FIELD, Start Field IVVQ | IVM | PDA; SEM; PM; VAL; QAM; SAM; CM; DM; field installation, test and deployment team |
| TQR1 / TRR2 | IVM | PDA; SEM; PM; ARC; RM; VAL; QAM; SAM; CM; LDM; DM; verification and test team |
| TQR2-1, Initial Validation and Assessment Handover | SEM | PDA; PM; VAL; IVM; QAM; SAM; RAM-AM; Security Manager; CM; DM; LDM; DeBo/ISA representative |
| FQR-1, Start Dark Operation and PIO | SEM | PDA; PM; VAL; IVM; QAM; SAM; RAM-AM; Security Manager; CM; DM; DeBo/ISA representative; Operator and deployment representatives as required |
| TQR2-2, Finished PIO and Standby Period | SEM | PDA; PM; VAL; IVM; QAM; SAM; RAM-AM; Security Manager; CM; DM; DeBo/ISA representative; operation and deployment contributors |
| FQR-2, Final Qualification Review | SEM | PDA; PM; VAL; IVM; QAM; SAM; RAM-AM; Security Manager; CM; DM; LDM; DeBo/ISA representative; service/support representatives |

Table 37: Milestone Reviews

Audits will be conducted through the Quality Assurance Manager. See therefore the Quality Management Plan.

### Reporting

Solution Engineering Manager Report to Project Management and to Head of discipline on Bi-weekly basis.

## Critical Technologies

No critical technologies are planned to be used in this solution.

## Risk and Opportunities Control

The Risk and Opportunities Control in this Solution will follow the Management System Manage Risks and Opportunities [Management System].

Additional information can be found in the Project Management Plan [1]

## Corrective Action Process

Information about the Corrective Action Process can be found in the Quality Management Plan [12]

## Independent Evaluation and Verification

Evaluation and Verification Process and required reports are explained in the related Plans. See IVP [7]

## Estimate/Re-Estimate

The initial estimation is from the Bid phase. Re-estimation of remaining work is done during the progress of working packages typically on a monthly period. The method used for estimation is mainly “Expert estimations” based on past experience, educated assumptions and risk considerations. Engineering estimations shall be based on the engineering estimation worksheet.

## Planning

Planning is done in the tool PCM and can be found there with the identification listed in Table 1.

## Value Analysis and Design to Cost

No Value Analysis in the solution. Costs are planned on MP level.

## Peer Reviews

The Peer Reviews in this Solution will follow the Management System,Organize and conduct Reviews, [Management System].

Additional information can be found in the Project Management Plan [1]

# Development Scenario / ZIVD TAILORED DDQS

For the Zalaszentiván Delta Track Project (ZIVD), the standard DDQS framework has been tailored to reflect the specific characteristics of a Hungarian signalling and ETCS deployment project, including customer approval processes, authority interfaces, Designated Body (DeBo) assessments, Independent Safety Assessment activities, Putting Into Operation (PIO) obligations, standby operation requirements, and the phased qualification approach used by Hungarian railway infrastructure projects. The tailoring also reflects the fact that the project is a specific application and integration project based on qualified product baselines, rather than a generic hardware or software development project.

The tailored ZIVD milestone model preserves the DDQS governance principles and decision-gate structure while introducing additional project-specific checkpoints and Hungarian-specific milestone extensions where required. These extensions define the approval packages, authority interactions, design releases, construction readiness confirmations, laboratory and field qualification stages, PIO readiness assessments, DeBo approval milestones, Dark Operation activities, standby-period closure activities and final acceptance prerequisites necessary for successful deployment and certification of the ZIV Delta Interlocking (IXL) and ETCS solutions.

The resulting milestone chain provides a harmonized framework that links project management decision gates with solution-engineering decision gates and ensures consistent control of requirements, architecture, design maturity, application data preparation, verification, validation, certification, deployment and customer acceptance activities. Each milestone defines specific objectives, decision criteria, mandatory evidence, required inputs, expected outputs and approval responsibilities. The Hungarian-specific milestone extensions are explicitly maintained and assessed as part of each review to ensure compliance with customer, operator, authority and certification requirements.

## ZIV Delta milestone list

| *No. | Process | Milestone name | Principal decision focus |
| --- | --- | --- | --- |
| 1 | Manage Project | MP KOM, Project Kick-Off Meeting | Launch the project, communicate the requirements and agree the project-preparation strategy. |
| 2 | DDQS | SOR, Solution Orientation Review | Approve the target architecture, development strategy and technical basis for solution design. |
| 3 | Manage Project | MP LR, Launch Review | Approve the complete Project Management Baseline, resources, schedule and management plans. |
| 4 | DDQS | SRR, Solution Requirements Review, including Approval Plan Package | Approve the requirements baseline and the Hungarian Approval Plan Package, including the required first approval and assessment evidence. |
| 5 | DDQS | SFR, Solution Functional Review, including Preliminary Design Package | Confirm design compliance and release the Preliminary Design Package for submission to the Operator. |
| 6 | DDQS | PDR, Preliminary Design Review, including Operator Approval | Approve the preliminary design, obtain Operator approval and authorize application data preparation. |
| 7 | DDQS | CDR, Critical Design Review, including Start of Installation | Approve the detailed design and construction plans, confirm site and material readiness, finalize data preparation and authorize installation and data-preparation verification. |
| 8 | DDQS | TRR1-LAB, Test Readiness Review 1, Start Laboratory IVVQ | Release the controlled LAB version for internal Hitachi Rail and customer laboratory testing. |
| 9 | DDQS | TRR1-FIELD, Test Readiness Review 1, Start Field IVVQ | Release the customer-approved LAB baseline for field testing and confirm verified field installation. |
| 10 | DDQS | TQR1 / TRR2, Technical Qualification Review 1 and Test Readiness Review 2 | Close integration and verification and confirm that the verified solution is ready for validation in the operational environment. |
| 11 | DDQS | TQR2-1, Initial Validation and Assessment Handover | Complete the first validation evidence set and hand it over to DeBo for authorization to proceed toward PIO. |
| 12 | DDQS / Hungarian deployment gate | FQR-1, Start Dark Operation and PIO | Confirm DeBo approval and all Hungarian operational prerequisites for Dark Operation and Putting into Operation. |
| 13 | DDQS | TQR2-2, Finished PIO and Standby Period | Close PIO and the standby period and update the final validation, quality and safety evidence. |
| 14 | DDQS | FQR-2, Final Qualification Review | Confirm completed validation and external assessment and declare readiness for customer acceptance and transition to support. |
| 15 | Manage Project | MP AR, Acceptance Review for IXL and ETCS | Confirm contractual and customer acceptance, including completion of the Hungarian THO and PIU activities. |
| 16 | Manage Project | MP CR, Closure Review | Confirm completion of project-closing activities and hand over the solution to service and warranty support. |

## Hungarian-specific extensions to the ZIVD Tailored Milestones

- SRR: Approval Plan Package release and approval, first DeBo assessment statement and authority permission, plus authorization to start hardware ordering from the first Mengengerüst.

- SFR: Preliminary Design Package released and submitted to the Operator, with Mengengerüst 1.0 established.

- PDR: Operator approval of the Preliminary Design Package, internal release and customer submission of construction plans, and authorization to start data preparation.

- CDR: Customer-approved construction plans, handed-over work area, delivered material, received work permit, completion of data preparation and start of data-preparation verification.

- TRR1-LAB: A controlled LAB version available for both Hitachi Rail and customer testing.

- TRR1-FIELD: LAB version approved for field use and the field installation verified before field testing.

- TQR2-1: Initial ValRep, QMR and SASC completed and handed over to DeBo to obtain permission for PIO.

- FQR-1: DeBo approval, approved Putting Into Operation technology and trial-operation criteria, track possession, Dark Operation preparation, completed training, operator handbook, station documentation, spare-parts handover and telecommunications PIO readiness.

- TQR2-2: PIO and standby period closed, with SASC, ValRep and QMR updated and the open-point list controlled.

- FQR-2: ISA Report, NoBo ISV and DeBo ISV available for final qualification.

- MP AR: Technical Handover and Putting Into Use completed for IXL and ETCS.

- MP CR: Formal solution handover to service and support.

# System Engineering Support

## Data and Configuration Management

Data and Configuration Management is carried out according to Management System Process, Configuration Management and Planning and Management (Solution),[Management System].

## Confidentiality

The rules as listed in Management System apply.

## Export Control

Export Control is carried out according to Management System Process Control Export [24]..

## Capitalization

Capitalization defined in PCM ATRELOA42

## Measurements and Analysis

Measurements and Analysis is carried out according to Management System Process Measure and Analyse [Management System].

## Technical and non Technical Requirements Management and Control

The requirements are defined in the [3] and are split in the defined solutions.

## Validation of Requirements

Details are defined in the VQP [7]

## Decision Analysis and Resolution

Customer workshops will be coordinated by PDA for decision finding and analysis.

## Subordinate Plans

Not applicable.

## Quality Assurance

The Quality Assurance in this Solution will follow QCI – Process Guarantee quality and manage continuous improvement  [Management System]. Additional information can be found in the Quality Management Plan.

# Approach and Criteria used for Tailoring of the System Engineering Process

The Tailoring Methods are described in Chapter 15 Development Scenario for the respective Phase.

# Certification Support Activity

Refer to Project Safety Plan Document [5]

# Open Items

None

- Criteria for the Selection of Techniques and Measures

With each technique or measure in the tables there is a requirement for each software safety integrity level (SIL). In the version June 2011 of the EN50128, the requirements for software safety integrity levels 1 and 2 are the same for each technique. Similarly, each technique has the same requirements at software safety integrity levels 3 and 4. These requirements can be

“App” this column selects with “Yes” for all relevant "documentation", “technique” or “measure” for the actual solution or “No” if this row isn’t mandatory for the solution.

'M' this symbol means that the use of a technique is mandatory,

'HR' this symbol means that the technique or measure is Highly Recommended for this safety integrity level. If this technique or measure is not used then the rationale for using alternative techniques shall be detailed in the Software Quality Assurance Plan or in another document referenced by the

Software Quality Assurance Plan

'R' this symbol means that the technique or measure is recommended for this safety integrity level. This is a lower level of recommendation than an 'HR' and such techniques can be combined to form part of a package,

'-' this symbol means that the technique or measure has no recommendation for or against being used,

'NR' this symbol means that the technique or measure is positively “Not Recommended” for this safety integrity level. If this technique or measure is used then the rationale behind using it shall be detailed in the Software Quality Assurance Plan or in another document referenced by the Software Quality Assurance Plan.

| DOCUMENTATION | App |  | SIL 4 | References of Doc Type |
| --- | --- | --- | --- | --- |
| Planning |  |  |  |  |
| 1. Software Quality Assurance Plan | Yes |  | HR | QMP |
| 2. Software Quality Assurance Verification Report | Yes |  | HR | PVR |
| 3. Software Configuration Management Plan | Yes |  | HR | CMP |
| 4. Software Verification Plan | Yes |  | HR | IVP |
| 5. Software Validation Plan | Yes |  | HR | VQP |
| Software requirements |  |  |  |  |
| 6. Software Requirements Specification | Yes |  | HR | SSS, OCD |
| 7. Overall Software Test Specification | Yes |  | HR | TCS |
| 8. Software Requirements Verification Report | Yes |  | HR | VCRM |
| Architecture and design |  |  |  |  |
| 9. Software Architecture Specification | Yes |  | HR | SSDD |
| 10. Software Design Specification | Yes |  | HR | SSDD |
| 11. Software Interface Specifications | Yes |  | HR | SSDD |
| 12. Software Integration Test Specification | Yes |  | HR | TCS |
| 13. Software/Hardware Integration Test Specification | Yes |  | HR | TCS |
| 14. Software Architecture and Design Verification Report | Yes |  | HR | SSDD Review Report |
| Component Design |  |  |  |  |
| 15. Software Component Design Specification | No |  | HR | No generic SW development (Coding) in this solution |
| 16. Software Component Test Specification | No |  | HR | No generic SW development (Coding) in this solution |
| 17. Software Component Design Verification Report | No |  | HR | No generic SW development (Coding) in this solution |
| Component Implementation and Testing |  |  |  |  |
| 18. Software Source Code and supporting documentation | No |  | HR | No generic SW development (Coding) in this solution |
| 19. Software Component Test Report | No |  | HR | No generic SW development (Coding) in this solution |
| 20. Software Source Code Verification Report | No |  | HR | No generic SW development (Coding) in this solution |
| Integration |  |  |  |  |
| 21. Software Integration Test Report | Yes |  | HR | Integration TR |
| 22. Software/Hardware Integration Test Report | Yes |  | HR | Integration TR |
| 23. Software Integration Verification Report | Yes |  | HR | Integration TR |
| Overall Software Testing / Final Validation |  |  |  |  |
| 24. Overall Software Test Report | Yes |  | HR | System TR |
| 25. Software Validation Report | Yes |  | HR | Validation Report |
| 26. Tools Validation Report | No |  | HR | Existing Tool Classification is used. |
| 27. Release Note | Yes |  | HR | Version Delivery Description (VDD) |
| Systems configured by application data/ algorithms |  |  |  |  |
| 28. Application Requirements Specification | Yes |  | HR | BoR(ETCS), SSS |
| 29. Application Preparation Plan | Yes |  | HR | DPP |
| 30. Application Test Specification | Yes |  | HR | TCS |
| 31. Application Architecture and Design | Yes |  | HR | SSDD |
| 32. Application Preparation Verification Report | Yes |  | HR | Verification Report (DP) |
| 33. Application Test Report | Yes |  | HR | TR |
| 34. Source Code of Application Data/Algorithms | Yes |  | HR | Application Data is stored in VOB whose locations are listed in Baseline ID Sheet (ETCS) |
| 35. Application Data/Algorithms Verification Report | Yes |  | HR | Verification Report (DP) |
| Software deployment |  |  |  |  |
| 36. Software Release and Deployment Plan | Yes |  | HR | Scope of Changes (SoC, ETCS) |
| 37. Software Deployment Manual | No |  | HR | SW Installation Manuals |
| 38. Release Notes | Yes |  | HR | Version Delivery Description (VDD) |
| 39. Deployment Records | Yes |  | HR | Outside of Hitachi Rail-AT scope as part of PiO activity. SW Installation Reports. |
| 40. Deployment Verification Report | Yes |  | HR | Outside of Hitachi Rail-AT scope as part of PiO activity. SW Installation Reports. |
| Software maintenance |  |  |  |  |
| 41. Software Maintenance Plan | No |  | HR | No SW maintenance after closure of the solution |
| 42. Software Change Records | No |  | HR | No SW maintenance after closure of the solution |
| 43. Software Maintenance Records | No |  | HR | No SW maintenance after closure of the solution |
| 44. Software Maintenance Verification Report | No |  | HR | No SW maintenance after closure of the solution |
| Software assessment |  |  |  |  |
| 45. Software Assessment Plan | No |  | HR | External assessment is outside of SW development process. Scope of independent Safety Assessor. It is |
| 46. Software Assessment Report | Yes |  | HR | AssRep |
| Documents 29, 30 and 31 being HR or R depends on the importance defined in the process and where the verification takes place. E.g. data may only be needed to be verified but tested in the system domain while more functional properties need both test and verification. In this case HR has been marked but can be optional R. |  |

Table A. 1 Lifecycle Issues and Documentation (EN50128, A.1)

| TECHNIQUE/MEASURE | App | SIL 4 |
| --- | --- | --- |
| 1. Defensive Programming | N/A – CSLK ETCS is a Specific Application | HR |
| 2. Fault Detection & Diagnosis |  | HR |
| 3. Error Correcting Codes |  | – |
| 4. Error Detecting Codes |  | HR |
| 5. Failure Assertion Programming |  | HR |
| 6. Safety Bag Techniques |  | R |
| 7. Diverse Programming |  | HR |
| 8. Recovery Block |  | R |
| 9. Backward Recovery |  | NR |
| 10. Forward Recovery |  | NR |
| 11. Retry Fault Recovery Mechanisms |  | R |
| 12. Memorising Executed Cases |  | HR |
| 13. Artificial Intelligence – Fault Correction |  | NR |
| 14. Dynamic Reconfiguration of software |  | NR |
| 15. Software Error Effect Analysis |  | HR |
| 16. Graceful Degradation |  | HR |
| 17. Information Hiding |  | – |
| 18. Information Encapsulation |  | HR |
| 19. Fully Defined Interface |  | M |
| 20. Formal Methods |  | HR |
| 21. Modelling |  | HR |
| 22. Structured Methodology |  | HR |
| 23. Modelling supported by computer aided design and specification tools |  | HR |
| Requirements: 1) Approved combinations of techniques for Software Safety Integrity Levels 3 and 4 are as follows: a) 1, 7, 19, 22 and one from 4, 5, 12 or 21; b) 1, 4, 19, 22 and one from 2, 5, 12, 15 or 21. 2) Approved combinations of techniques for Software Safety Integrity Levels 1 and 2 are as follows: 1, 19, 22 and one from 2, 4, 5, 7, 12, 15 or 21. 3) Some of these issues may be defined at the system level. 4) Error detecting codes may be used in accordance with the requirements of EN 50159. NOTE Technique/measure 19 is for External Interfaces. |  |  |

Table A. 2 - Software Architecture (EN 50128:2011 – A.3 - 7.3)

| TECHNIQUE/MEASURE | App | SIL 4 |
| --- | --- | --- |
| 1. Formal Proof | Refer to IVP [6], TP[2], Ver_Rules Error! Reference source not found. | HR |
| 2. Static Analysis |  | HR |
| 3. Dynamic Analysis and Testing |  | HR |
| 4. Metrics |  | R |
| 5. Traceability |  | M |
| 6. Software Error Effect Analysis |  | HR |
| 7. Test Coverage for code |  | HR |
| 8. Functional/ Black-box Testing |  | M |
| 9. Performance Testing |  | HR |
| 10. Interface Testing |  | HR |
| Requirements: 1) For software Safety Integrity Levels 3 and 4, the approved combination of techniques is 3, 5, 7, 8 and one from 1, 2 or 6. 2) For Software Safety Integrity Level 1 and 2, the approved combinations of techniques is 5 together with one from 2, 3 or 8. NOTE 1 Techniques/measures 1, 2, 4, 5, 6 and 7 are for verification activities. NOTE 2 Techniques/measures 3, 8, 9 and 10 are for testing activities. |  |  |

Table A. 3 - Verification and Testing (EN 50128:2011 – A.5 - 6.2 and 7.3)

| TECHNIQUE/MEASURE | App | SIL 4 |
| --- | --- | --- |
| 1. Static Software Analysis | Yes | HR |
| 2. Dynamic Software Analysis | No | HR |
| 3. Cause Consequence Diagrams | No | R |
| 4. Event Tree Analysis | No | R |
| 5. Software Error Effect Analysis | No | HR |
| Reference documents will be prepared in further milestones of the solution. Requirement: 1) One or more of these techniques shall be selected to satisfy the Software Safety Integrity Level being used. |  |  |

Table A. 4 - Software Analysis Techniques (EN 50128:2011 A.8 - 6.3)

| TECHNIQUE/MEASURE | App | SIL 4 |
| --- | --- | --- |
| 1. Accredited to EN ISO 9001 | Refer to QMP. | HR |
| 2. Compliant with EN ISO 9001 |  | M |
| 3. Compliant with ISO/IEC 90003 |  | R |
| 4. Company Quality System |  | M |
| 5. Software Configuration Management |  | M |
| 6. Checklists |  | HR |
| 7. Traceability |  | M |
| 8. Data Recording and Analysis |  | M |
| Requirement: 1) This table shall be applied to different roles and all phases. |  |  |

Table A. 5 - Software Quality Assurance (EN 50128:2011 A.9 - 6.5)

| TECHNIQUE/MEASURE | App | SIL 4 |
| --- | --- | --- |
| 1. Impact Analysis | No | M |
| 2. Data Recording and Analysis | No | M |
| *Reference documents will be prepared in further milestones of project. |  |  |

Table A. 6 - Software Maintenance (EN 50128:2011 A.10 – 9.2)

| TECHNIQUE/MEASURE | App | SIL 4 |
| --- | --- | --- |
| 1. ADA | N/A | HR |
| 2. MODULA-2 |  | HR |
| 3. PASCAL |  | HR |
| 4. C or C++ |  | R |
| 5. PL/M |  | NR |
| 6. BASIC |  | NR |
| 7. Assembler |  | R |
| 8. C# |  | R |
| 9. JAVA |  | R |
| 10. Statement List |  | R |
| Requirements: 1) The selection of the languages shall be based on the requirements given in 6.7 and 7.3. 2) There is no requirement to justify decisions taken to exclude specific programming languages. NOTE 1 Run-time systems associated with selected languages which are necessary to run application programs should still be justified for usage according to the Software Safety Integrity Level. |  |  |

Table A. 7 - Textual Programming Languages (EN 50128:2011 – A.15)

| TECHNIQUE/MEASURE | App | SIL 4 |
| --- | --- | --- |
| 1. Functional Block Diagrams | N/A | R |
| 2. Sequential Function Charts |  | HR |
| 3. Ladder Diagrams |  | R |
| 4. State Charts |  | HR |

Table A. 8 - Diagrammatic Languages for Application Algorithms (EN 50128:2011 – A.16)

| TECHNIQUE/MEASURE | App | SIL 4 |
| --- | --- | --- |
| 1. Data Modelling | No | HR |
| 2. Data Flow Diagrams | No | HR |
| 3. Control Flow Diagrams | No | HR |
| 4. Finite State Machines or State Transition Diagrams | No | HR |
| 5. Time Petri Nets | No | HR |
| 6. Decision/Truth Tables | No | HR |
| 7. Formal Methods | Yes | HR |
| 8. Performance Modelling | No | HR |
| 9. Prototyping/Animation | No | R |
| 10. Structure Diagrams | No | HR |
| 11. Sequence Diagrams | No | HR |
| Requirements: 1) A modelling guideline shall be defined and used. 2) At least one of the HR techniques shall be chosen |  |  |

Table A. 9 – Modelling (EN 50128:2011 - A.17)

| TECHNIQUE/MEASURE | App | SIL 4 |
| --- | --- | --- |
| 1. Traceability of the concept of the application domain to the classes of the architecture | N/A | HR |
| 2. Use of suitable frames, commonly used combinations of classes and design patterns |  | HR |
| 3. Object Oriented Detailed Design |  | HR |
| Requirement: 1) When using existing frames and design patterns, the requirements of pre-existing software apply to these frames and patterns. NOTE 1 The object-oriented approach presents information differently from procedural approaches, the following list contains recommendations that need specific consideration: - understanding class hierarchies, and identification of the software function(s) that will be executed upon the invocation of a given method (including when using an existing class library); - structure-based testing (Table A.13). Traceability from application domain to class architecture is less important. NOTE 2 For a part of the intended software a frame might exist from pre-existing software that has successfully solved a similar task and that is well known to the development personnel. Then use of that frame is recommended. |  |  |

Table A. 10 - Object Oriented Software Architecture (EN 50128:2011 – A.22)

| TECHNIQUE/MEASURE | App | SIL 4 |
| --- | --- | --- |
| 1. Classes should have only one objective | N/A | HR |
| 2. Inheritance used only if the derived class is a refinement of its basic class |  | HR |
| 3. Depth of inheritance limited by coding standards |  | HR |
| 4. Overriding of operations (methods) under strict control |  | HR |
| 5. Multiple inheritance used only for interface classes |  | HR |
| 6. Inheritance from unknown classes |  | NR |
| Requirements: 1) One class is characterized by having one responsibility, i.e. taking care of closely connected data and the operations on these data. 2) Care is required to avoid circular dependencies between objects. |  |  |

Table A. 11 - Object Oriented Detailed Design (EN 50128:2011 – A.23)

| TECHNIQUE/MEASURE | App | SIL 4 |
| --- | --- | --- |
| 1. Tabular Specification Methods | Refer to IVP [6], | R |
| 2. Application specific language |  | R |
| 3. Simulation |  | HR |
| 4. Functional testing |  | M |
| 5. Checklists |  | M |
| 6. Fagan inspection |  | R |
| 7. Formal design reviews |  | HR |
| 8. Formal proof of correctness (of data) |  | HR |
| 9. Walkthrough |  | HR |
| Requirements: 1) For Software Safety Integrity Level 1 and 2 an approved combination of techniques is 1 and 4. 2) For Software Safety Integrity Level 3 and 4 the approved combinations of techniques are 1, 4, 5 and 7 or 2, 3 and 6. NOTE The description of the reference D.29 is on programs while technique 8 in this context applies to formal proof of the correctness of data. |  |  |

Table A. 12 - Data Preparation Techniques (EN 50128:2011 A.11 - 8.4)

# END OF DOCUMENT