PMP and SEMP

ELEKTRA PV INT 2.11.0

ELEKTRA Product Line Engineering

ELEKTRA

International

| APPROVAL |  |  |
| --- | --- | --- |
|  | Name and Role/Job Title | Esignature |
| Written by | Robert Strauß SEM |  |
| Verified by | Christian Janneschitz QAM |  |
| Approved by | Krist Ndue HoEJR |  |

| LOG OF CHANGES |  |  |  |
| --- | --- | --- | --- |
| Revision | Date | Author | Change Description |
| 01 | 2023-07-23 | Robert Strauß | Initial Edition for milestone SOR |
| 02 | 2024-01-12 | Robert Strauß | Update due to CCB |
| 03 | 2024-10-22 | Robert Strauß | Update due to CCB2 |
| 04 | 2025-07-08 | Robert Strauß | Update due to CCB3 |

Contents

1.	SCOPE	8

1.1	Identification	8

1.1.1	General	8

1.1.2	WBS managed as Solution	8

1.1.3	WBS managed as Work Packages	8

1.1.4	Other component versions this engineering solution is based on	9

1.2	System overview	10

1.3	Key points	12

1.3.1	Milestones for Solution	12

1.3.2	Deliverables	12

1.4	Relation with other plans	13

1.5	Document version history	13

1.5.1	Edition 01	13

1.5.2	Edition 02	13

1.5.3	Edition 03	13

1.5.4	Edition 04	14

2.	References and terms	15

2.1	Referenced documents	15

2.2	Process basis	15

2.3	Standards and procedures	16

2.4	Terms, abbreviations and acronyms	17

2.4.1	Role abbreviations	17

2.4.2	Terms, abbreviations and acronyms	18

3.	Solution engineering and development process	20

3.1	Organization of solution engineering	20

3.1.1	Solution core team	20

3.1.2	Solution team	21

3.1.3	External project roles	22

3.1.4	Configuration Control Board (CCB)	22

3.1.5	Subcontractors	23

3.2	System engineering supplies	23

3.3	Input data	23

3.4	Preconditions / Related solutions	23

3.5	Technical objectives	24

3.6	Detailed First Level WBS for Work Packages	24

3.7	Special need for training of system engineering team	24

3.8	Constraints / Risks	24

3.9	Work Contained	25

3.10	Work not contained	25

3.11	Responsibility Assignment Matrix	25

3.12	Tools and Facilities	26

3.12.1	Management and Documentation Tools	26

3.12.2	Code Building Tools	27

4.	Process Control	28

4.1	Control of Solution Development	28

4.1.1	Deviation	28

4.1.2	Metrics	28

4.2	Monitoring and Control of Solution Engineering Activities	30

4.2.1	Periodic Internal Reviews and Meetings	30

4.2.2	Milestone Reviews and Audits	30

4.2.3	Reporting	30

4.3	Critical Technologies	31

4.4	Risk and Opportunities Control	31

4.5	Corrective Action Process	31

4.6	Independent Evaluation and Verification	31

4.7	Estimate/Re-Estimate	31

4.8	Planning	31

4.9	Value Analysis and Design to Cost	31

4.10	Peer Reviews	31

5.	Development scenario and tailoring of the System Engineering Process	32

5.1	Tailoring for this Solution (DDQS phases)	32

5.1.1	Orient the Solution	32

5.1.2	Design the Solution	32

5.1.3	Develop the Solution	32

5.1.4	Integrate and Verify the Solution	32

5.1.5	Validate the solution	33

5.2	Tailoring of Documentation Management	33

5.3	Tailoring of milestones	33

5.3.1	Manage Project milestones	33

5.4	Tailoring of role assignments	33

5.4.1	Role of IVVQM	33

5.4.2	Role of Verifier (VER) according CENELEC EN 50128 and EN 50129	33

5.4.3	Role of DM	34

5.5	Tailoring of the monitoring of project progress within an agile development environment	34

6.	System Engineering Support	36

6.1	Data and Configuration Management	36

6.2	Confidentiality	36

6.3	Export Control	36

6.4	Capitalization	36

6.5	Measurements and Analysis	36

6.6	Technical and Non-technical Requirements Management and Control	36

6.7	Validation of Requirements	36

6.8	Decision Analysis and Resolution	36

6.9	Subordinate Plans	37

6.10	Quality Assurance	37

6.11	Certification Support Activity	37

6.12	HSE Plan	37

APPENDIX A	Criteria for the Selection of Techniques and Measures	38

List of Tables

Table 1: Solution Identification	8

Table 2: WBS managed as Solution	8

Table 3: WBS managed as Work Packages	8

Table 4: Other component versions	9

Table 5: Milestones	12

Table 6: Deliverables	13

Table 7 : Referenced Documents	15

Table 8 : Standards and Procedures	16

Table 9 : Role abbreviations	17

Table 10 : Terms, Abbreviation and Acronyms	18

Table 11: Core team	20

Table 12: Team	21

Table 13: External project roles	22

Table 14: CCB	22

Table 15: Preconditions	23

Table 16: Detailed WBS	24

Table 17: Management and Documentation Tools	26

Table 18: Code Building Tools	27

Table 19: Metrics	28

Table 20: Reviews and Meetings	30

List of Figures

Figure 1: Product Breakdown Structure	11

Figure 2: Manage the Product Policy (MPP)	32

Figure 3: Manage Project (PRJ)	32

Figure 4: Develop and Qualify the Solution (DDQS)	32

Figure 5: Agile Process according to Agile Definition SMP [S24]	35

# SCOPE

The combined PSEMP, Project Management Plan (PMP) and System Engineering Management Plan (SEMP) describe the organisation, work packages, milestones and application of the Management System DDQS process release number 2023-06-30.

This Solution delivers ELEKTRA 2 product version International INT 2.11.0 (short PV INT 2.11.0) which realizes features and improvements according to the Business Plan Decision Review [MPP-DR] for the Hungarian and Bulgarian market.

## Identification

### General

Table 1: Solution Identification

| Cost collector: | 100023326 |
| --- | --- |
| Solution: | ATRENOB03 |
| Project category: | A0 |

### WBS managed as Solution

Table 2: WBS managed as Solution

| WBS | Identification | SEM | SIL | Initial Product Version | Target Product Version | Target date |
| --- | --- | --- | --- | --- | --- | --- |
| ATRENOB03-E0 | (ELEKTRA) International | R. Strauß / EJR | SIL4 | INT 2.10.0 | INT 2.11.0 | Milestone FQR, see section 1.3.1 |

### WBS managed as Work Packages

A detailed view on all WBS elements is listed in section 3.6. If a WBS below is not in scope of this Solution (i.e. no change is planned on that WBS element), the initial version (and unchanged target version) is stated anyway.

Table 3: WBS managed as Work Packages

| Solution: | ATRENOB03-E0 |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| WBS | Ident. | WPM | Initial Version | Target Version | Target date |  |
| ATRENOB03-E0.WP3.2.[WP-ID] | ELEKTRA | R. Strauss / EJR | INT_23.02 | INT_24.00 | Milestone TQR2 |  |
| ATRENOB03-E0.WP3.2. [WP-ID].OST | OREST | T. Neiger / EJT | 15.02 | 15.04 | Milestone TQR1 |  |
| ATRENOB03-E0.WP3.2. [WP-ID].EBO | EBO2 | G. Barna / EJM | INT_23.02 | INT_24.00 | Milestone TRR1 |  |
| ATRENOB03-E0.WP3.2. [WP-ID].EEC | NIC | K. Aichner / EPR | HU_1.0.6 | HU_1.0.7 | Milestone TRR1 |  |
|  | SEC | K. Aichner / EPR | INT_2.0.1 | INT_2.1.0 | Milestone TRR1 |  |

Remark: Regarding development and release of SEC components (HW and SW) see remark in chapter 1.2.

### Other component versions this engineering solution is based on

Table 4: Other component versions

| Product / Component |  | Version |
| --- | --- | --- |
| ELEKTRA 2 International product version |  | PV INT 2.11.0 |
| ELEKTRA 2 baseline version |  | INT_24.00 |
| VDU version |  | EBO2_INT_24.00 |
| MMI-Setup version |  | 3.2 |
| SEC version |  | SEC_INT_2.1.0 |
| consists of | EEC SW ITC version *) | 3.3.0 |
|  | EEC SW GEN version *) | 3.3.0 |
|  | EEC HW ITC version *) | 2.1.0 |
|  | SEC HW GEN version | 2.3.0 |
| NIC version |  | NIC_HU_1.0.7 |
| consists of | EEC components | see note below *) |
|  | NIC HW GEN version | 1.0.4 |
| ELEKTRA 2 International HW-Interfaces |  | included |
| Computing Hardware |  | MEN-D6/D10 |
| The ELEKTRA 2 International product version is based on ELEKTRA 2 Generic System product version |  | PV GEN 2.19.10 |

*) Note: Group identifier (see [CMP]) NIC HU and SEC INT use the same EEC components EEC SW ITC, EEC SW GEN and EEC HW ITC.

## System overview

This Solution provides a safe and highly reliable solution to control the railway operation. The objective of this Solution is to upgrade the existing functionality of product ELEKTRA International and data preparation tool OREST with the scope as defined as follows:

- Scope of Change [SoC] contains features, change requests and defect corrections which are planned to be released.

Remark: Regarding change request PELINT-4564 “[CR] SEC GEN 2.5.0 Integration”: The SEC components (HW and SW) to be developed by solution SEC 2.5.0 (ATRENOB05-E0 EL-INT SEC HU, see [PSEMP-SEC250]) are planned to be delivered by solution SEC 2.5.0 ready for integration with ELEKTRA International. 
For this solution is planned to perform the integration (System- / Integration- Test) of these SEC components (HW and SW) with ELEKTRA PV INT 2.11.0 only.	
No SEC HW development is planned by this solution.	
No SEC SW development is planned regarding eBlock functionality by this solution with the exception of feature CELSEC-1298 “[FL:SEC-INT:FEA:0008] Support of Block Signals” which is financed by this solution, but delivered by solution SEC 2.5.0.	
The release of the SEC components (HW and SW) is planned by solution SEC 2.5.0, after delivery of the Test Reports about successfully integration by this solution.	
For preconditions and related solutions see section 3.4. For delivered content and schedule of SEC 2.5.0 see [PSEMP-SEC250].

Remark: According [DVa] the necessary cyber security measures for ELEKTRA International have been analysed and the delivery is planned by ELEKTRA PV INT 2.12.0. I.e. no cyber security plan, security report and security case will be delivered by ELEKTRA PV INT 2.11.0.

The initial and target versions of this solution and their work packages for this engineering project are listed in Table 2 to Table 3. The product ELEKTRA International is described in System Description [SysDesc].

The Product Breakdown Structure for ELEKTRA International consists of different configuration items according [CMP] shown in Figure 1.

Figure 1: Product Breakdown Structure

Note: Additional identifiers for groups of configuration items are used as mentioned below, in any case the included list of delivered configuration items are defined in detail. This group identifier is not part of the above-mentioned product structure, but it consists of a set of delivered configuration items from the above-mentioned product structure:

- NIC_HU_1.0.7
Summary of delivered configuration items relevant for NIC in market Hungary, including EEC SW ITC 3.3.0 (based on EEC SW GEN 3.3.0) and EEC HW ITC 2.1.0 (based on NIC HW GEN 1.0.4).

- SEC_INT_2.1.0
Summary of delivered configuration items relevant for SEC in market Hungary, including EEC SW ITC 3.3.0 (based on EEC SW GEN 3.3.0) and EEC HW ITC 2.1.0 (based on SEC HW GEN 2.3.0).

## Key points

### Milestones for Solution

Table 5: Milestones

| Milestone | Target Date | Lead |
| --- | --- | --- |
| Business Plan Decision Review (BP DR) | Defined on level MPP | PLM |
| Kick Off (KOM) | See tailoring chapter 5.3.1 | PM |
| Solution Orientation Review (SOR) | 31.07.2023 | SEM |
| Launch Review (LR) | 11.08.2023 See tailoring chapter 5.3.1 | PM |
| Development Launch Decision Review (DL DR) | Defined on level MPP | PLM |
| Solution Requirement Review (SRR) | 23.11.2023 | SEM |
| Solution Functional Review (SFR) | 18.04.2024 | SEM |
| Preliminary Design Review 1 (PDR-1) | 19.08.2024 | SEM |
| Critical Design Review 1 (CDR-1) | 19.08.2024 | SEM |
| Preliminary Design Review 2 (PDR-1) | 01.10.2024 | SEM |
| Critical Design Review 2 (CDR-2) | 01.10.2024 | SEM |
| Test Readiness Review 1-1 (TRR1-1) | 28.10.2024 | IVM |
| Test Readiness Review 1-2 (TRR1-2) | 08.11.2024 | IVM |
| Technical Qualification Review 1 (TQR1) | 13.08.2025 | SEM |
| Test Readiness Review 2 (TRR2) | 13.08.2025 | SEM |
| Technical Qualification Review 2 (TQR2) | 04.09.2025 | SEM |
| Final Qualification Review (FQR) | 31.10.2025 | SEM |
| Acceptance Review (AR) | See tailoring chapter 5.3.1 | PM |
| Deployment Decision Review (DP DR) | Defined on level MPP | PLM |
| Closure Review (CR) | See tailoring chapter 5.3.1 | PM |

### Deliverables

For Solution (Element) final date see Table 2. Additional deliverables in scope of this engineering project are listed below:

Table 6: Deliverables

| Deliverable | Completion Date |
| --- | --- |
| Data preparation rules / directives. | Milestone TQR1 |
| ClearCase views for customer data preparation containing delivered baseline and associated tools. | Milestone TQR2 |
| “Components of the Generic System” in case of generic changes. | Milestone TRR1 |
| Update of the customer documents "Maintenance and Repair" in case of changes. | Milestone TQR1 |

## Relation with other plans

See Documentation Plan [DoP].

## Document version history

### Edition 01

Initial edition.

### Edition 02

Update department identifier (delete leading ‘T’).

Chapter 1.1.4 - Table 4 and chapter 1.2: update version of NIC HW GEN and PV GEN.

Chapter 1.2: update remark regarding cyber security.

Chapter 1.3.1: update new target date of milestones PDR till FQR.

Chapter 2.1 - Table 7: update edition/version of referenced documents.

Chapter 2.4.2: add JPS and MDS.

Chapter 3.1 - Table 11: update VER name; Table 12: update names (SW Eng. ELEKTRA and EBO2); Table 14: merged responsible HoD for RM/VER with OREST, and for HoD Project Engineering,

Chapter 3.7: add 3rd CC-developer and new Verifier for training.

Chapter 3.10: add that no cyber security plan, security report, security case will be delivered (is part of successor PV INT 2.12.0).

### Edition 03

Change to Hitachi template.

Chapter 1.3.1: add milestone splitting PDR / CDR / TRR1and update target date.

Chapter 2.1 - Table 7: update edition/version of referenced documents.

Chapter 2.3 - Table 8: update version/revision of referenced documents.

Chapter 3.1 - Table 11: update SEM deputy name; Table 12: update names (SW Eng. ELEKTRA and OREST, EC-SubIT, CCB-SubIT); Table 14: merged responsible

Chapter 3.4: update completion date.

Chapter 3.7: update CC-developers for training.

Chapter 3.12.2 - Table 18: update tool versions.

### Edition 04

Chapter 1.3.1: update milestones TQR1, TQR2, FQR according CCB3 decision.

Chapter 2.1 - Table 7: update edition/version of referenced documents.

Chapter 2.3 - Table 8: update version/revision of referenced documents.

Chapter 2.4.2: add SP-ID, removed TAT, TOL.

Chapter 3.1 - Table 11: update names; Table 12: update names.

# References and terms

## Referenced documents

The relevant version of a document is referenced in the Documentation Plan [DoP]. Several planning documents are concurrent in progress until milestone SOR, therefore the edition 01 is referenced of Documentation Plan / Process Verification Report. Until milestone FQR the Documentation Plan / Process Verification Report for this Solution will be updated and tracked within the Version in SharePoint see SP-ID [DoP].

Table 7 : Referenced Documents

| Id | Nr./Title | Reference | Version |
| --- | --- | --- | --- |
| [DoP] | Documentation Plan (DoP) | 3BU 15000 9187 ADAPA | 01 |
|  |  | SP-ID: JESTKFHXKKEY-660377445-48 | 2.0 |
| [RiskReport] | Risk Report | SP-ID: JESTKFHXKKEY-660377445-46 | 4.0 |
| [EngDB] | Engineering Dashboard | SP-ID: JESTKFHXKKEY-660377445-42 | 8.0 |
| [QMP] | Quality Management Plan, ELEKTRA 1.x & 2.x | 3BU 15000 5244 QMAPA | 07 |
| [SP] | Safety Plan, ELEKTRA 2.x | 3BU 15000 0602 DUAPA | 06 |
| [SoC] | Scope of Change (SoC) | 3BU 15000 9187 QEAPA | 06 |
| [DVa] | Design Validation approval (DVa) | 3BU 00603 0176 DEAPA | 02 |
| [ToolClassSW] | Software Development Tool Classification | 3BU 15000 5135 AAAPA 3BU 15000 5135 190EN | 27 02 |
| [CMP] | Configuration Management Plan, ELEKTRA | 3BU 15000 3338 QMAPA | 10 |
| [MS-Report] | Milestone Report Solution | SP-ID: JESTKFHXKKEY-660377445-44 | 2.0 |
| [MPP-DR] | MPP Decision Review ELEKTRA International (PV INT 2.11.x) | 3BU 00603 0181 BCAPA | 01 |
| [SysDesc] | System Description Interlocking System ELEKTRA International | 3BU 15000 9010 EDAPA | 12A |
| [VDD-HW] | Version Delivery Description, ELEKTRA Hardware | 3BU 15000 5225 ELAPA | 39 |
| [PSEMP-SEC250] | PSEMP SEC 2.5.0, ELEKTRA International | 3BU 62500 0050 DPAPA | 03 |

## Process basis

The project is set up with the Management System, release number 2023-06-30 as process basis. Changes in this process basis (e.g. adaptation to a new release of Management System) have to be analysed, especially regarding the impact on already existing work products, and have to be documented and approved.

## Standards and procedures

Table 8 : Standards and Procedures

| Nr./Title | Publishing Date/ Reference | Version/ Revision |
| --- | --- | --- |
| - IRIS Certification rules:2020 based on ISO/TS 22163:2017 | 2017 | n/a |
| - EN 50128:2011 + A1:2020 + A2:2020 Railway application – Communication, signalling and processing systems – Software for railway control and protection systems | 2011/2020 | n/a |
| - EN 50129:2018 + AC:2019 Railway applications – Communication, signalling and processing systems – Safety related electronic systems for signalling | 2018/2019 | n/a |
| - ISO 9001 | 2015 | n/a |
| - EN 50126-1:2017 – Railway Applications – The Specification and Demonstration of Reliability, Availability, Maintainability and Safety (RAMS) – Part 1: Generic RAMS Process | 2017 | n/a |
| - EN 50126-2:2017 – Railway Applications – The Specification and Demonstration of Reliability, Availability, Maintainability and Safety (RAMS) – Part 2: Systems Approach to Safety | 2017 | n/a |
| - Management System Process Manage Risks and Opportunities | Part of 0001-0050019330 (87200984-00-PRJ-GRP-EN) (Chapter 8.6) | 2023-06-30 |
| - Management System Process Manage Project | 0001-0050019330 (87200984-00-PRJ-GRP-EN) | 2023-06-30 |
| - Minimum Requirements for the configuration management implementation | 87100077-CFG-GRP | 007 |
| - Management System Process 6.1 DDQ-SW - Design develop and qualify the Software solution | 0001-0050019355 (87202125-00-DDQ-GRP-EN) | 2023-06-30 |
| - Management System Process Validate the Solution | Part of 0001-0050019360 (87202127-00-DDQ-GRP-EN) | 2023-06-30 |
| - Management System Process Integrate and Verify the Solution | Part of 0001-0050019360 (87202127-00-DDQ-GRP-EN) | 2023-06-30 |
| - Management System Process Design the Solution | Part of 0001-0050019360 (87202127-00-DDQ-GRP-EN) | 2023-06-30 |
| - Management System Process 9.7 CFG - Manage Configuration | 0001-0050019454 (87202424-00-CFG-GRP-EN) | 2023-06-30 |
| - Management System Process 9.3 Control Export | 0001-0050019409 (87299999-00-EXP-GRP-EN) | 2023-06-30 |
| - Management System Guarantee quality and manage continuous improvement | 0001-0050019226 (87200214-00-QCI-GRP-EN) | 2023-06-30 |
| - Protection of Group Information | 87201725-GOV-GRP-EN | 005 |
| - Personal Data Protection Policy | 87212828-GOV-GRP-EN | 001 |
| - Project Life Cycle | 83530275-DDQ-AUT-EN | 005 |
| - Document Management Rules | 83530061-DOC-AUT-EN | 013 |
| - Milestone Template Solutions | 83530019-DDQ-AUT-EN | 011 |
| - Document List and Review Matrix for engineering projects | 83530224-DOC-AUT-EN | 010 |
| - HSE Instruction | 83530048-HSE-AUT-DE | 019 |
| - Agile Definition SMP | 83530312-DDQ-AUT-EN | 001 |

## Terms, abbreviations and acronyms

### Role abbreviations

Table 9 : Role abbreviations

| ARC | Architect |
| --- | --- |
| CM | Configuration Manager |
| DM | Document Manager |
| DPM | Data Preparation Manager |
| HoD | Head of Discipline |
| IVM | Integration and Verification Manager |
| IVVQM | Integration, Verification, Validation and Qualification Manager |
| PDA | Project Design Authority |
| PLA | Product Line Architect |
| PLM | Product Line Manager |
| PSM | Project Security Manager |
| QAM | Quality Assurance Manager |
| RAM-AM | Reliability, Availability, Maintainability Assurance Manager |
| RE | Requirements Engineer |
| RM | Requirements Manager |
| TM | Test Manager |
| SAM | Safety Assurance Manager |
| SEM | Solution Engineering Manager |
| SM | Senior Management |
| VAL | Validator |
| VER | Verifier |
| WPM | Work Package Manager |

### Terms, abbreviations and acronyms

Table 10 : Terms, Abbreviation and Acronyms

| BCWS | Budgeted Cost of Work Scheduled |
| --- | --- |
| CBB | Contract Budget Baseline |
| CCB | Configuration Control Board |
| CDR | Critical Design Review |
| CENELEC | European Committee for Electrotechnical Standardization |
| CHARM | Change and Request Management |
| CR | Change Request |
| DDQS | Design, Develop and Qualify the Solution |
| EDM | ELEKTRA Delivery Model |
| EEC | “ELEKTRA 4.0 Element Controlling” Remark: EEC is the umbrella term for the new way of controlling outdoor elements, including NIC, SEC |
| EL1 | ELEKTRA Generation 1 |
| EL2 | ELEKTRA Generation 2 |
| ESM | Electronic Storage Media |
| EV | Earned Value |
| FEA-ID | Feature Identifier from Feature List |
| FQR | Final Qualification Review |
| GEN | Generic |
| HW | Hardware |
| JPS | Juridical Protocol Service |
| IFS | Interfaces |
| IVV | Integration, Verification and Validation |
| KOM | Kick of Meeting |
| M | Mandatory |
| MDS | Monitoring and Data collection System |
| MPP | Manage Product Policy |
| N/A | Not applicable |
| NIC | Neighbour Interface Controller, successor of the RIC |
| O | Optional |
| PCM | Primavera Core Model |
| PCR | Problem Change Request |
| PDR | Preliminary Design Review |
| PEP | Personnel Efforts Planning |
| PiO | Put in Operation |
| PMP | Project Management Plan |
| QMP | Quality Management Plan |
| RAMS | Reliability, Availability, Maintainability and Safety |
| SE | Solution Element |
| SEC | Single Element Controller |
| SEMP | System Engineering Management Plan |
| SFR | Solution Functional Review |
| SIL | Safety Integrity Level |
| SOR | Solution Orientation Review |
| SP-ID | SharePoint Document Identifier |
| SRR | Solution Requirement Review |
| SubIT | Subsystem Integration Test |
| SW | Software |
| TQR | Technical Qualification Review |
| TRR | Test Readiness Review |
| WBS | Work Breakdown Structure |
| WP | Work Package |
| WPD | Work Package Description |

# Solution engineering and development process

The Solution will be conducted according to Management System 2023-06-30 (see also 2.2). As the Management System is continuously improving, it has to be mentioned, that in the devolution of the Solution, for newly created documents within this project, the respective valid templates have to be used according to the up-to-date Management System 2023-06-30 version. For maintenance and extension of existing documents the previously used template may remain.

## Organization of solution engineering

The description of the roles mentioned below can be found on the Management System Portal.

### Solution core team

Table 11: Core team

| Role | Resource | Deputy Resource |
| --- | --- | --- |
| PLM | K. Schnabl / MP | W. Fuß / MP |
| PDA | A. Nemeth / EJR | n/a |
| PM / SEM | R. Strauß / EJR | K. Ndue / EJR |
| IVM | S. Bako / EJR | A. Simon / EJR |
| VER | H. Walenta / EJS see **) below table | n/a |
| SAM | R. Büger / RS | C. Sünder / RS |
| QAM | C. Janneschitz / QA | F. Rotter / QA |
| VAL | A. Bayramoglu / RV | P. Satlek / RV |
| RM | G. Eber / EJT | I. Miler / EJT |

**) The verification according CENELEC of all documents is performed throw reviews by the roles defined in the Document List and Review Matrix for engineering projects [S22]. The role VER is not executed by a single person. The VER activities are distributed to following roles:

- Process Verification: is made by QAM

- Final document Verification: is made by RM

- Software/Code Verification: is made by ARC

- Deliverables Verification: is made by IVM

- Enabling systems Verification: is made by CM

- Lifecycle phases Verification: is made by VER

- Collection of Verification results in Verification-report: is made by VER

### Solution team

Table 12: Team

| Role | Resource | Deputy Resource |
| --- | --- | --- |
| PLA | W. Fuß / MP | K. Schnabl / MP |
| ARC | P. Kovacs / EJR | A. Nemeth / EJR |
| CM | J. Cutig / EJT | G. Kocsis / EJR |
| DM | see *) below table | n/a |
| DPM | R. Kiss / EJT | E. Müller / EJT |
| RAM-AM | F. Moser / RR | M. Scheuer / RR |
| Software Engineer ELEKTRA | T. Heckenast / EJR L. Joo / EJR B. Molnar / EJR T. Horvath / EJR P. Hornyak / EJR R. Kun / EJR R. Prikler / EJR T. Ruzsovits / EJR | n/a |
| Tester ELEKTRA | G. Kocsis / EJR A. Karner / EJR B. Sari / EJR I. Hegyi / EJR G. Reif / EJR V. Feher / EJR R. Baranczo / EJR D. Devai / EJR | n/a |
| (E)EC-SubIT Testteam | G. Schild / EJR (EC) L. Raslan / EPR (EEC) L. Kritzl / EJR (EEC) | n/a |
| CCB-SubIT Testteam | D-M. Preoteasa / ROM M. Stan / ROM V. Voicu / ROM G. A. Cioraneanu / ROM | n/a |
| Software Engineer EBO2 | G. Barna / EJM M. Boronyai / EJM S. Bodor / EJM | n/a |
| Software Engineer OREST | S. Krasny / EJT T. Neiger / EJT S. Szili-Kis / EJT M.-B. Nemeth / EJT G. Simon /EJT M. Pasztor / EJT P. Gangli / EJT A. Alscuti / EJT D. Molnar / EJT L. Pocs / EJT E. Abd Almajeed Shebli Elshebli / EJT N. Yaneva / EJT | n/a |
| Roles (SAM, VAL, VER, SW/HW Engineer) regarding EEC are part of Solution SEC GEN 2.5.0 see [PSEMP-SEC250]. | n/a | n/a |

*) The role DM is not executed by a single person. The major DM activities are distributed to following roles:

- new ANV: can be obtained by SEM

- Document Index: is made by CM or SEM

- Formal check at release of a document: is made by QAM

- Other DM activities: are made by author of the document

### External project roles

Table 13: External project roles

| Role | Resource | Deputy Resource |
| --- | --- | --- |
| Safety Assessor | T. Schürer / Arsenal RACE | n/a |

### Configuration Control Board (CCB)

Table 14: CCB

| Role | Resource | Comment | M/O |
| --- | --- | --- | --- |
| PLM | see Table 11 | Budget, schedule, scope | M |
| SEM | see Table 11 |  | M |
| PDA | see Table 11 |  | M |
| SAM | see Table 11 |  | M |
| IVM | see Table 11 |  | O |
| VAL | see Table 11 |  | M |
| QAM | see Table 11 |  | M |
| HoD Route Control Projects | K. Ndue / EJR | ELEKTRA Development & Test resources | M |
| HoD Traffic Management Projects | G. Grossmayer / EJM | EBO2 resources | O |
| HoD CAE Data Toolset | S. Krasny / EJT | RM, VER, OREST resources | O |
| HoD Project Engineering | G. Schmidmayr / EJ | for priority conflicts regarding resources in EJ | O |
| HoD Architecture, Technology and Innovation | H. Kantz / EPR | EEC resources | O |
| Head of Engineering | M. Vana / E | for priority conflicts regarding resources in E | O |
| PM HU Program | A. Zalezak / B | Financing by operative projects | O |
| Head of Solution Design | A. Paul / ESD | Conflicts regarding PCRs from customer projects point of view | O |

Other project team members are invited to the CCB as needed.

### Subcontractors

Not applicable in this project.

## System engineering supplies

Any reuse of a finished or purchased product will be stated in the Design Validation approval [DVa].

## Input data

See Table 4.

## Preconditions / Related solutions

Table 15: Preconditions

| Deliverable | Completion Date | Provider / comment |
| --- | --- | --- |
| ELEKTRA PV INT 2.10.0 (milestone TQR2) | 07.08.2023 | ATRENOA98 EL-INT 22.12 |
| Release of developer resources | 01.03.2023 | ATRENOA98 EL-INT 22.12 |
| Release of test resources | 01.07.2023 | ATRENOA98 EL-INT 22.12 |
| Prototype HW SEC 2.5, ordering of HW for baseline integration tests possible | 30.09.2024 | ATRENOB05 EL-INT SEC HU 2.5 |
| EEC SW 3.3.0 (milestone TRR1), can be used for SW Integration | 30.09.2024 | ATRENOB05 EL-INT SEC HU 2.5 |
| JPS 1.0 (ESM successor = ESM2) delivery (FQR) | E02.2025 | EJM |
| MDS 3.2 (Webride successor) delivery (FQR) | 15.07.2024 | EJM |

## Technical objectives

The technical objective of this Solution is to upgrade the existing functionality of product ELEKTRA International and data preparation tool OREST with developing change requests according Scope of Change [SoC]. Those change requests shall be developed in a way to reuse it for all customers of product ELEKTRA International (currently on Hungarian and Bulgarian market) if applicable.

## Detailed First Level WBS for Work Packages

Table 16: Detailed WBS

| WBS element ID | WBS element name | WBS element manager | Comments |
| --- | --- | --- | --- |
| ATRENOB03-E0.AC | Allocated Cost, Engineering Cost transfer | SEM |  |
| ATRENOB03-E0.OC | Other contractual cost other | SEM |  |
| ATRENOB03-E0.WP3.2.KMS | Key Milestones | SEM |  |
| ATRENOB03-E0.WP3.2.GC | General Costs | SEM | Travel, other costs |
| ATRENOB03-E0.WP3.2.BLENG | Baseline engineering | SEM | PDA, ARC, SEM, TM, CM, RM, VAL, SAM, VER, QAM, SM, Regression tests, Data preparation, DDT |
| ATRENOB03-E0.WP3.2.EBLOCK | Work package: eBlock between ELEKTRA incl. track code support, SEC GEN 2.5.0 integration | SEM | See [SoC] |
| ATRENOB03-E0.WP3.2.ESM2 | Work package: Integration of ESM2 (JPS), MDS | SEM | See [SoC] |
| ATRENOB03-E0.WP3.2.LPCR | Work package: Legacy PCRs | SEM | See [SoC] |

## Special need for training of system engineering team

Training on the job is planned in 2023/2024 for

- for L. Joo, R. Prikler and T. Ruzsovits (new CC-developers) by P. Kovacs and A. Nemeth (experienced ELEKTRA developer) and by department EJR;

No additional training for the Solution team is required.

## Constraints / Risks

Constraints which are not already considered in the [RiskReport] are listed here.

- None.

## Work Contained

- Engineering of the scope mentioned in section 1.2 according to the applying parts of the relevant standards listed in section 2.3.

- Delivery of the baseline documentation, including the Safety Cases.

- Delivery of the items listed in section 0.

- Coordination and execution of Factory Acceptance Tests (Customer labor-/integration- tests), and if a resolution of detected item during FAT is part of this project will be defined in the evaluation meeting. I.e. if not blocking then item can be moved to future baselines.

- Assessment Certification for this solution. Details have to be documented in Section 5.1.5 Validate the solution.

## Work not contained

While the work contained is already stated in section 3.9, the following topics are explicitly mentioned as not part of this solution in order to sharpen the responsibility:

- Coordination and agreements with non-Hitachi-internal customers.

- Data preparation of non-testing railway stations.

- On-site test (on-site access after milestone TQR1 then on-site test will be transferred to customer project).

- Installation.

- Industrialisation of HW components.

- Any HW, product or solution development not mentioned in section 1.1.2 or 1.1.3.

- Any other kind of customer- / user-documentation as described in section 3.9. The following examples are all in responsibility of PDAs provided by department “Solution Design (ESD)”:

  - Update of the user document “User Manual Interlocking Bulgaria".

  - Update of the user document “User Manual Interlocking Hungary”.

  - Update of the documents “Functional Requirement Specification" for Bulgaria and “[DE] Anforderungsspezifikation” for Hungary

- Translation of documents from previous baselines into English.

- Translation of customer documents into customer languages (Bulgaria, Hungary).

- Training of new and external (Romanian, Hungarian) employees.

- Delivery of cyber security plan, security report and security case.

## Responsibility Assignment Matrix

The responsibilities of the roles at a Milestone Review can be seen in Milestone Template Solutions [S21].

The milestone review TQR2 confirms the successful completion of product validation and the readiness of all needed elements for customer acceptance and that the Solution is ready for Assessment according to CENELEC. The PDA confirms with the approval to milestone TQR2 that the delivered solution meets his/her expectations.

The milestone review FQR confirms that the Design, Development and Qualification activities including Assessment according to CENELEC are complete and that the Solution is ready for production, deployment and transition to support.

## Tools and Facilities

The following subsections provide a rough overview of the project tool setup. For version information and tool classification see document [ToolClassSW].

### Management and Documentation Tools

Table 17: Management and Documentation Tools

| Tool Category | Tool | Note |
| --- | --- | --- |
| Project Management | Primavera PCM |  |
| Task Management | TIPI |  |
| Requirements Management | DOORS/RMF |  |
| Management Traceability | DOORS/RMF |  |
| Configuration Management | ClearCase Git |  |
| Change Management | CHARM |  |
| Documentation Management | ClearCase DWF Team Online SharePoint |  |
| Documentation Generation | DOORS RMF Java Doc MS Office |  |
| Build environment ELEKTRA | ClearCase ClearMake |  |
| Build environment EBO2 | Git Maven Hudson |  |
| Build environment EEC | Git Maven BitBucket Jenkins |  |
| Build environment OREST | Git ANT and Maven Sonar Jenkins |  |
| Build environment ELEPRO | ADA Compiler ClearCase |  |
| IVV Management | DOORS MS Excel |  |

### Code Building Tools

Table 18: Code Building Tools

| Tool Category | Tool | Version | Note |
| --- | --- | --- | --- |
| Compiler | CHILL | 2.3.12 |  |
|  | GNU C/C++ | 7.3.0-plf2.4 | According to document 3BU_15000_5135_AAAPA |
|  | JAVA | 1.8 |  |
|  | PAMELA | 3.06 |  |
| IVV | GCOV | 7.3.0-plf2.4 | According to document 3BU_15000_5135_AAAPA |
|  | EPS | 05.29 |  |
|  | COTO | 01.31 |  |
|  | Audit Tools | 05.13 |  |

# Process Control

## Control of Solution Development

The solution elements and assigned responsibilities are listed in Table 3.

### Deviation

The development of a Solution has to be planned and executed according to the DDQS Processes of Management System. Deviation to the description in Project Life Cycle [S19] is described in section 5.

### Metrics

The used metrics for control of the engineering process are identified in the Engineering Dashboard [EngDB].

The tailoring for this dashboard is listed below:

Table 19: Metrics

|  | Sheet | Tailoring |
| --- | --- | --- |
|  | Actions & Decisions | Used - no deviation. |
|  | Stability of Team Velocity | Not used. See Note 5 below. |
|  | Visibility Point Burnup | Not used. See Note 5 below. |
|  | Code Quality | Not used. |
|  | Code Reuse | Not used. |
|  | Defect management | Not used. |
|  | Documentation | Not used. |
|  | Finance | Used. See Note 1 below. |
|  | Interface testing progress | Not used. |
|  | IVV Test Writing | Not used. |
|  | Master Plan | Used - no deviation. |
|  | Milestones | Used - no deviation. |
|  | OBS | Used - no deviation. |
|  | PCR (Problem Change Request) | Used. See Note 2 below. |
|  | Quality | Used. Data provided by QAM. |
|  | RAMS | Optional. Data provided by RAM-AM and SAM. |
|  | Release content progress | Optional. Not only features are tracked, but also legacy PCRs which are part of the scope as defined in section 1.2. |
|  | Remaining work burndown | Not used. |
|  | Requirement Analysis | Used. See Note 3 below. |
|  | Requirement Flowdown | Not used. |
|  | Sizing & critical performance | Not used. |
|  | Technical Risks | Used - no deviation. |
|  | Validate & qualify test progress | Not used. |
|  | Verification testing progress | Used. See Note 4 below. |
|  | WBS | Used - no deviation. |
|  | Workload | Used - no deviation. |
|  | Note 1: Guideline: - “BCWS Planned Spend” is the monthly planned costs of work. This value can be determined from PCM. It is the defined/updated at the time the CBB is defined or updated. - “Forecast” is the spending forecast from the last month with actuals to the end of the project (before this period it has to be empty). - “EV” is not used. |  |
|  | Note 2: Guideline: This metric deals with PCRs found in the phase “Integrate and Verify the Solution”. Hence no baseline can be given ahead. The “Raised Forecast” may be predicted after a few months of this phase from past data. |  |
|  | Note 3: Guideline: Only the table "requirements chart data" is filled out, where the - "Total number of Req.": is the sum of all approved requirements at the time of the reporting. The reporting is done every month - "Baseline": a new baseline is created, when a new release of the SSS is done and a new release label is generated in DOORS - "Analysis forecast": specifies the sum of current and new requirements. - Either a value in "Baseline" or in the "Analyses forecast" is filled out except in the current month, where both fields are filled out. Additionally to be filled out are: - "Analyzed Req.": sum of all requirements, which are analyzed and not changed - "Req. to be clarified": sum of requirements, which are currently not approved, new or changed, may not be the sum of the below attributes - "Obsolete Req": sum of requirements, which will be set to descoped - "Modified Req": sum of changed requirements - "New Req": sum of new requirements Requirements characterization can be generated via DOORS, via the menu "TRSS-AT" -> "Simple Functions" -> "KPI" -> "Input for Req. analysis tab". |  |
|  | Note 4: Guideline: Field “Req. conformity (%)” may be used as a percentage of tested and verified items of the scope defined in [SoC]. |  |
|  | Note 5: Guideline: The monitoring of project progress within an agile development environment requires a set of metrics defined in the Agile Definition SMP [S24] document sections 9.2.1 ‘Stability of Team Velocity’ and 9.2.2 ‘Visibility Point Burnup’ and is expected by senior management to be displayed during the PPPRs. Furthermore, the tailoring of the monitoring of project progress within an agile development environment in chapter 5.5 must be taken into consideration to get an adequate information basis for the KPIs. |  |

## Monitoring and Control of Solution Engineering Activities

### Periodic Internal Reviews and Meetings

Table 20: Reviews and Meetings

| Meeting | Responsible | Attendees | Frequency | Objectives |
| --- | --- | --- | --- | --- |
| periodically Core Team Meeting | SEM | “Solution core team”, ARC, WPM(s) Only on demand: CM | (Bi-)weekly | Project status and action points. |
| Risk and opportunity review | SEM | SEM, PLM, PDA, IVM, SAM, ARC, QAM | Quarterly or on demand |  |
| Resource review | SEM | SEM, HoD Route Control Projects | monthly | Check utilisation and additional needs of solution team. |
| Cost tracking | Project controller | SEM, HoD Route Control Projects, Project Controller | monthly | Report of costs and progress to Financial Control Director. |
| Periodically Performance Project Review (PPPR) | SEM | SEM, HoD Route Control Projects, HoD Project Engineering, HoD Engineering, Program Manager HU | monthly | Report of costs and progress, KPI dashboard, Progress Matrix, required decisions from SM to HoD Project Engineering, HoD Engineering |

### Milestone Reviews and Audits

Milestone reviews are done according Milestone Template Solutions [S21]. Quality Audits will be conducted through the QAM – see [QMP]. Safety Audits will be conducted through the SAM – see [SP].

### Reporting

Reporting is done via the Engineering Dashboard [EngDB] and Progress Matrix.

## Critical Technologies

Not applicable in this project.

## Risk and Opportunities Control

The Risk and Opportunities Control in this Solution will follow the Management System Process Manage Risks and Opportunities [S7] and is monitored in the [RiskReport].

## Corrective Action Process

Information about the Corrective Action Process can be found in the [QMP].

## Independent Evaluation and Verification

Independent evaluation and verification will be done by

- the verifier and domain experts upon instruction of the verifier (VER);

- the validator (VAL);

- the safety assurance manager (SAM).

## Estimate/Re-Estimate

The initial estimation is either an input for the phase “Orientation the Solution” or is done or verified during this phase. Re-estimation of remaining work is done during the progress of working packages typically on a monthly period. The method used for estimation is mainly “Expert estimations” based on past experience, educated assumptions and risk considerations.

## Planning

Planning is done in the tool PCM and can be found there with the identification listed in Table 1.

## Value Analysis and Design to Cost

Value Analysis and Design to Cost is done by the Engineering Dashboard [EngDB].

## Peer Reviews

The Peer Reviews in this Solution will follow the Minimum Requirements for the configuration management implementation [S9]. An overview of mandatory Documents and Reviewer has to be done according to Document List and Review Matrix for engineering projects [S22].

# Development scenario and tailoring of the System Engineering Process

This development process follows the initialisation by Management System process Manage Product Policy (MPP) as described in Project Life Cycle [S19].

Figure 2: Manage the Product Policy (MPP)

The Product Line Engineering (PLE) approach is applicable if there is a need to perform product evolution or product development without a concrete BID or if an enhancement, respectively change of a product is used for several customer contracts or markets. In this case PLE is a substitute for the process Manage Bid and guides the project over the whole project life cycle. The Product Line Manager (PLM) starts the PLE process with a Business Plan Decision Review (BP DR) and triggers the DDQS for product development.

The project is conducted following the Management System processes Manage Project (PRJ) and Design, Develop and Qualify the Solution (DDQS) and their interfaces according to Project Life Cycle [S19].

Figure 3: Manage Project (PRJ)

Figure 4: Develop and Qualify the Solution (DDQS)

## Tailoring for this Solution (DDQS phases)

### Orient the Solution

No other deviation to the description in Project Life Cycle [S19].

### Design the Solution

No deviation to the description in Project Life Cycle [S19].

### Develop the Solution

No deviation to the description in Project Life Cycle [S19].

### Integrate and Verify the Solution

No deviation to the description in Project Life Cycle [S19].

### Validate the solution

The Assessment Certification according to CENELEC is needed for this product version. No other deviation to the description in Project Life Cycle [S19].

## Tailoring of Documentation Management

The tailoring of the Product Line Engineering (PLE) is used as described in Project Life Cycle [S19].

- The PMP and SEMP is combined in one document PSEMP.

The naming convention for the name “Firstname Lastname” of the author, verified by, approver of a document can also be “F. Lastname”.

No other deviation to the description in Document Management Rules [S20].

## Tailoring of milestones

### Manage Project milestones

The tailoring of the Product Line Engineering (PLE) is used as described in Project Life Cycle [S19]. The Manage Project milestones are replaced by the Manage Product Policy milestones.

- Kick Off replaced by Business Plan Decision Review.

- Launch Review replaced by Development Launch Decision Review, in case the scope of change has no deviation between Development Launch Decision Review and Launch Review.

- Acceptance Review performed by a planned customer acceptance test.

- Closure Review replaced by Deployment Decision Review.

## Tailoring of role assignments

### Role of IVVQM

The role IVVQM is not executed by a single person. The major IVVQM activities are distributed to other roles:

- Integration: is made by IVM

- Verification: is made by IVM

- Validation: is made by VAL

- Qualification: is made by VAL (in case of HW development)

### Role of Verifier (VER) according CENELEC EN 50128 and EN 50129

The verification according CENELEC of all documents is performed throw reviews by the roles defined in the Document List and Review Matrix for engineering projects [S22]. The role VER is not executed by a single person. The VER activities are distributed to other roles:

- Process Verification: is made by QAM

- Final document Verification: is made by RM

- Software/Code Verification: is made by ARC

- Deliverables Verification: is made by IVM

- Enabling systems Verification: is made by CM

- Lifecycle phases Verification: is made by VER

- Collection of Verification results in Verification-report: is made by VER

### Role of DM

The role DM is not executed by a single person. The major DM activities are distributed to other roles:

- new ANV: can be obtained by SEM

- Document Index: is made by CM or SEM

- Formal check at release of a document: is made by QAM

- Other DM activities: are made by author of the document

## Tailoring of the monitoring of project progress within an agile development environment

Remark: No SEC or NIC development is planned by this solution, therefor this tailoring is not used.

This chapter affects the agile working activities for the system components SEC and NIC.

The monitoring of project progress within an agile development environment requires a set of metrics defined in the Agile Definition SMP [S24] document sections 9.2.1 ‘Stability of Team Velocity’ and 9.2.2 ‘Visibility Point Burnup’ and is expected by senior management to be displayed during the PPPRs. These metrics are the basis for decision making and shall be reported by the team’s WPM or Product Owner after every sprint.

The generation of these metrics was automated in Excel (download at https://e2.at.gts/confluence/download/attachments/108463228/Agile_Metrics_Template.xlsm?api=v2), yet it expects some Jira setup in order to function correctly and to deliver insightful information. The expectations are presented below.

- A Scrum Board is defined in Jira and the team works in sprints.

- Estimations are filled in the Jira field ‘Story Points’, regardless of their real unit (complexity, days, function points etc.).

- Every issue is assigned to (at least) 2 different FixVersions (Jira Release): one for the complete project or baseline (e.g. INT_24.00) and one indicating the specific deliverable (e.g. INT_24.00-PDR, INT_24.00-Lab1).

Figure 5: Agile Process according to Agile Definition SMP [S24]

Please note that on the example above all ‘Implementation Epics’ are linked to the ‘Deliverable/Milestone 3’, but some are also linked to the ‘Deliverable/Milestone 2’ (since the latter is just an intermediary deliverable, e.g. a Lab release, while the former represents the Management System milestone which includes all ‘Implementation Epics’).

# System Engineering Support

## Data and Configuration Management

Data and Configuration Management is carried out according to Management System Process 9.7 CFG - Manage Configuration [S14], Document Management Rules [S20] and the specific Configuration Management Plan [CMP].

## Confidentiality

The rules as listed in Protection of Group Information [S17] apply.

## Export Control

Export Control is carried out according to Management System Process 9.3 Control Export [S15].

## Capitalization

Capitalization is handled in the context of the related Manage Product Policy process.

## Measurements and Analysis

See section 4.

## Technical and Non-technical Requirements Management and Control

For Requirement Management the tool DOORS is used. The Requirements Manager ensures that requirements are

- uniquely identified

- unambiguous, testable and consistent

- traced from origin through all systems

- have all changes managed

The Requirements Manager manages changes throughout the life of the project. If requirements change, the impact will be reflected in the project plans, work products, and activities. Any inconsistencies between these customer- and/or system requirements and project plans, work products, and activities will be identified and resolved.

## Validation of Requirements

The validation is done in accordance with the Validation Qualification plans as listed in Documentation Plan [DoP].

## Decision Analysis and Resolution

Decision analysis and resolutions are part of design and review processes. The results are documented in design documents, review reports and in this document.

## Subordinate Plans

There are no subordinate plans.

## Quality Assurance

The Quality Assurance in this Solution will follow Management System Guarantee quality and manage continuous improvement [S16]. Additional information can be found in the Quality Management plans as listed in Documentation Plan [DoP].

## Certification Support Activity

See Safety Management plans as listed in Documentation Plan [DoP].

## HSE Plan

The local requirements of the HSE Management and the measures resulting from it for the environment and protection of the employee’s health are described in the HSE Instruction [S23].

An HSE evaluation should be considered if for example an engineer is at the station for PiO or Test. No hardware development activities are planned by this Solution. Therefore, no separate HSE Product Plan is necessary.

Criteria for the Selection of Techniques and Measures

With each technique or measure in the tables there is a requirement for each software safety integrity level (SIL). In the version June 2011 of the EN50128, the requirements for software safety integrity levels 1 and 2 are the same for each technique. Similarly, each technique has the same requirements at software safety integrity levels 3 and 4. These requirements can be

“App” this column selects with “Yes” for all relevant "documentation", “technique” or “measure” for the actual project or “No” if this row isn’t mandatory for the project.

'M' this symbol means that the use of a technique is mandatory,

'HR' this symbol means that the technique or measure is Highly Recommended for this safety integrity level. If this technique or measure is not used then the rationale for using alternative techniques shall be detailed in the Software Quality Assurance Plan or in another document referenced by the Software Quality Assurance Plan.

'R' this symbol means that the technique or measure is recommended for this safety integrity level. This is a lower level of recommendation than an 'HR' and such techniques can be combined to form part of a package,

'-' this symbol means that the technique or measure has no recommendation for or against being used,

'NR' this symbol means that the technique or measure is positively “Not Recommended” for this safety integrity level. If this technique or measure is used then the rationale behind using it shall be detailed in the Software Quality Assurance Plan or in another document referenced by the Software Quality Assurance Plan.

Table A1 Lifecycle Issues and Documentation (EN50128, A.1)

| DOCUMENTATION | App | SIL 4 | References of Doc Type |
| --- | --- | --- | --- |
| Planning |  |  |  |
| 1. Software Quality Assurance Plan | Yes | HR | QMP |
| 2. Software Quality Assurance Verification Report | Yes | HR | QMR |
| 3. Software Configuration Management Plan | Yes | HR | CMP |
| 4. Software Verification Plan | Yes | HR | IVP |
| 5. Software Validation Plan | Yes | HR | VQP |
| Software requirements |  |  |  |
| 6. Software Requirements Specification | Yes | HR | SSS |
| 7. Overall Software Test Specification | Yes | HR | Test Plan |
| 8. Software Requirements Verification Report | Yes | HR | VoR and review reports of SSS documents |
| Architecture and design |  |  |  |
| 9. Software Architecture Specification | Yes | HR | SSDD |
| 10. Software Design Specification | Yes | HR | SSDD |
| 11. Software Interface Specifications | Yes | HR | SSDD |
| 12. Software Integration Test Specification | Yes | HR | TCS |
| 13. Software/Hardware Integration Test Specification | Yes | HR | TCS |
| 14. Software Architecture and Design Verification Report | Yes | HR | Verification Report |
| Component Design |  |  |  |
| 15. Software Component Design Specification | Yes | HR | SDD |
| 16. Software Component Test Specification | Yes | HR | SSCTR |
| 17. Software Component Design Verification Report | Yes | HR | Review reports of design documents |
| Component Implementation and Testing |  |  |  |
| 18. Software Source Code and supporting documentation | Yes | HR | ClearCase, GIT |
| 19. Software Component Test Report | Yes | HR | SSCTR |
| 20. Software Source Code Verification Report | Yes | HR | SSCTR |
| Integration |  |  |  |
| 21. Software Integration Test Report | Yes | HR | Integration Test Report |
| 22. Software/Hardware Integration Test Report | Yes | HR | Integration Test Report |
| 23. Software Integration Verification Report | Yes | HR | Verification Report |
| Overall Software Testing / Final Validation |  |  |  |
| 24. Overall Software Test Report | Yes | HR | ∑ Test Reports |
| 25. Software Validation Report | Yes | HR | Validation Report |
| 26. Tools Validation Report | Yes | HR | Tools classification report, handling of TACs in Verification Report |
| 27. Release Note | Yes | HR | VDD |
| Systems configured by application data/ algorithms |  |  |  |
| 28. Application Requirements Specification | No | HR | Not applicable since this is a generic application development. The customization of the application data for a specific application is not part of this development. |
| 29. Application Preparation Plan | No | HR |  |
| 30. Application Test Specification | No | HR |  |
| 31. Application Architecture and Design | No | HR |  |
| 32. Application Preparation Verification Report | No | HR |  |
| 33. Application Test Report | No | HR |  |
| 34. Source Code of Application Data/Algorithms | No | HR |  |
| 35. Application Data/Algorithms Verification Report | No | HR |  |
| Software deployment |  |  |  |
| 36. Software Release and Deployment Plan | Yes | HR | CMP |
| 37. Software Deployment Manual | Yes | HR | VDD |
| 38. Release Notes | Yes | HR | VDD |
| 39. Deployment Records | Yes | HR | VDD |
| 40. Deployment Verification Report | Yes | HR | Review Report of VDD |
| Software maintenance |  |  |  |
| 41. Software Maintenance Plan | Yes | HR | Feature List |
| 42. Software Change Records | Yes | HR | CHARM, DOORS |
| 43. Software Maintenance Records | Yes | HR | CHARM |
| 44. Software Maintenance Verification Report | Yes | HR | PCR Evaluation Report |
| Software assessment |  |  |  |
| 45. Software Assessment Plan | No | HR | Not applicable, External assessment is outside of PV development; therefore, no evidence can be given. |
| 46. Software Assessment Report | Yes | HR | External assessment report if product version will be assessed |
| Documents 29, 30 and 31 being HR or R depends on the importance defined in the process and where the verification takes place. E.g. data may only be needed to be verified but tested in the system domain while more functional properties need both test and verification. In this case HR has been marked but can be optional R. |  |  |

Table A2 Software Requirements Specification (EN 50128, A.2)

| TECHNIQUE/MEASURE | App | SIL 4 | Remark |
| --- | --- | --- | --- |
| 1. Formal Methods (based on a mathematical approach) | No | HR | Method is not applied. See requirement 2) at the bottom of this table. For this product “structured methodology” is chosen as applied technique. |
| 2. Modelling | No | HR | Method is not applied. See requirement 2) at the bottom of this table. For this product “structured methodology” is chosen as applied technique. |
| 3. Structured methodology | Yes | HR | Based on requirements tool DOORS |
| 4. Decision Tables | No | HR | Method is not applied. See requirement 2) at the bottom of this table. For this product “structured methodology” is chosen as applied technique. |
| Requirements: 1) The Software Requirements Specification shall include a description of the problem in natural language and any necessary formal or semiformal notation. 2) The table reflects additional requirements for defining the specification clearly and precisely. One or more of these techniques shall be selected to satisfy the Software Safety Integrity Level being used. |  |  |  |

Table A3 Software Design and Implementation (EN 50128, A.4)

| No | TECHNIQUE/MEASURE | Applied (Yes/No) | SIL 4 | Ref |  |
| --- | --- | --- | --- | --- | --- |
| 1 | Formal Methods | No | HR | Method is not applied. For this product “structured methodology” is chosen as applied technique. |  |
| 2 | Modelling | Yes | HR | Validation Report |  |
| 3 | Structured methodology | Yes | HR | Design Documents |  |
| 4 | Modular Approach | Yes | M | Design Documents |  |
| 5 | Components | Yes | HR | Software Source Code Test Report, Design Documents. |  |
| 6 | Design and Coding Standards | Yes | M | Coding Standards, Software Source Code Test Report |  |
| 7 | Analysable Programs | Yes | HR | Software Source Code Test Report |  |
| 8 | Strongly Typed Programming Language | Yes | HR | CHILL and JAVA are strongly typed languages. |  |
| 9 | Structured Programming | Yes | HR | Applied by coding rules and; CHILL and JAVA programming languages, Software Source Code Test Report |  |
| 10 | Programming Language | Yes | HR | Textual Programming Languages |  |
| 11 | Language Subset | Yes | HR | Coding Rules GNUCHILL |  |
| 12 | Object Oriented Programming | ELEKTRA: No EBO2/EEC: Y | R | Table A.22 D.57 |  |
| 13 | Procedural programming | Yes | HR | CHILL and JAVA programming languages |  |
| 14 | Metaprogramming | No | R |  |  |
| Requirements: 1) An approved combination of techniques for Software Safety Integrity Levels 3 and 4 is 4, 5, 6, 8 and one from 1 or 2. 2) An approved combination of techniques for Software Safety Integrity Levels 1 and 2 is 3, 4, 5, 6 and one from 8, 9 or 10. 3) Metaprogramming shall be restricted to the production of the code of the software source before compilation. |  |  |  |  |

END OF DOCUMENT

The HW- components, interfaces and Outdoor Elements conventional are listed in VDD ELEKTRA Hardware 0

For tailoring of milestones, see chapter 5.3

SEM of this Solution takes over the functions of the PM.